## MASTER 23.24
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: |  | Clinical Lead: |  |  | Pathway Manager:
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
Faster Diagnosis (including BPTP) and Operational Improvement
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
Patient Engagement and Involvement, Experience of Care
Research
Workforce and Education
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Acute Oncology
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Acute Oncology |  | Clinical Lead: Konstantinos Kamposioris |  |  | Pathway Manager: Jane Cronin
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening) | [6 empty] | 2023-05-12
N/A
Faster Diagnosis (including BPTP) and Operational Improvement
N/A
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Consider improved pathways for patients presenting acutely from treatment or disease related acute episodes. |  | (1) Data from 01/22 to 02/23 from Christie Hotline to be collated in line with Christie BI Team to show whether there is a geographical variation in access to Acute Oncology Services. (2) Working alongside GM Genomic Cancer Hub, explore ways to improve the utilisation of cancer genome testing for CUP Patients with feedback through the CUP Sub-Group as a standing agenda item at AO Pathway Board. (3) Scope whether virtual clinics would assist with the management of acute oncology patients by auditing the requirement in each of the AO Services in GM, Mid/East Cheshire. (4) Utilising the experience of the Supportive Care team at The Christie, explore whether similar services could operate locally by providing information and education on The Christie clinic at the Acute Oncology Education Event. | Konstantinos Kamposioras Claire Mitchell Konstantinos Kamposioras / Jane Cronin Jane Cronin | 31/03/2024 31/03/2024 31/03/2024 30/06/2023
| Comprehensive access to cancer intelligence to understand inequalities & evaluate progress through Tableau |  | 1) Identify KPI's for AO Data. Pilot to be undertaken in Bolton with GM Cancer BI Team and Bolton BI Team to extract KPI data automatically. 2) Acute Oncology Data Sub-Group to agree KPI's and roll out initially to other sites which utilise Somerset. | Claire DeMarcoMasetti / David Holderness Claire DeMarcoMasetti / David Holderness | 31/03/2024 31/09/2024 |  |  | Business Intelligence Team paused pilot due to system pressures - awaiting date for resumption of pilot.
Patient Engagement and Involvement, Experience of Care
| Ensure that service users are included in all areas of AO Work programme and pathway board. |  | Ensure that there is a minimum of 2 x service user representative members of the AO pathway board supported by AO Small Community. | UI Manager | 2024-03-31
| Ensure that service users are included in all areas of AO Work programme and pathway board. |  | Ensure that there is service user representation in all work streams and sub-groups of the board | UI Manager | 2024-03-31
Research
| Deliver an education & engagement event to promote excellent AO practice across GM & promote the work of the AO Pathway Board |  | Education & engagement event to be delivered and evaluation to be undertaken and presented to pathway board. | Jane Cronin / Gina Maderna | 2023-07-31
| Develop resources for primary care on cancer emergencies and how to recognise acute side effects of treatment. |  | (1) Working with Primary Care Lead and Early Diagnosis Team, deliver a presentation at Cancer Forum to educate GP's to recognise acute side effects of anti-cancer treatment that may result in an emergency presentation and combine a patient impact video. (2) Presentation to be recorded and uploaded to Gateway C with a fast facts and infographic to be developed. | Konstantinos Kamposioras / Jane Cronin / Sarah Taylor / Lauren Kelly Lauren Kelly / Jane Cronin | 31/03/2024 31/03/2024
| Raise awareness of MSCC signs and symptoms in primary care & secondary care |  | Working with the GM Cancer Academy, assist with the identification of subject matter experts to develop the following modules:- (a)What is MSCC & Red Flags (b)Treatment options - a debate between surgeon & oncologist (c)Rehabilitation Interventions | Jane Cronin / Gina Madera | 2024-03-31
| Raise awareness of Acute Oncology to improve patient outcomes and experience |  | Regular communications through the Pathway Board news updates to include links to additional resources created that are cross-cutting, e.g., MSCC module | Konstantinos Kamposioras / Jane Cronin / | 2024-03-31
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Breast
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Breast |  | Clinical Lead: Clare Garnsey |  |  | Pathway Manager: Claire Goldrick
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Suspected Cancer Referral Form: Annual review of referral form to ensure all relevant clinical information captured. | NA | Form reviewed and approved by Pathway Board and shared with Early Diagnosis team to be uploaded to Primary Care systems. | Claire Goldrick | 2023-12-31 |  | 2023-05-15
| ETIP - Endocrine Therapy Improvement Plan Risk Reducing Endocrine Therapy Toolkit: Launch regional toolkit to support Family History teams to increase the number of women at moderate/high risk of breast cancer offered and prescribed risk reducing endocrine therapy | No | Toolkit for Tamoxifen, Anastrozole and Raloxifene approved by Pathway Board and uploaded to GM Cancer website including: - Algorithms - Patient Information Leaflets (Plain English, Easy Read and transcribed into other languages) - Prescription requests - Assessment documents for FH team | Clare Garnsey/ Claire Goldrick | 2023-06-30 |  | 2023-05-15
|  |  | Deliver launch meeting in April 2023 for all new GPwER and Family History nurses in GM | Clare Garnsey/ Claire Goldrick | 2023-04-30 | Complete | 2023-05-15
|  |  | Communication with Primary Care colleagues to raise awareness of ETIP and prescription request letters that will be received through PCN network | Clare Garnsey/ Claire Goldrick | 2023-06-30 |  | 2023-05-15
|  |  | Monitoring implementation: Develop and share document to collate numbers of patients offered and prescribed risk reducing endocrine therapy | Clare Garnsey/ Claire Goldrick | 2023-06-30 |  | 2023-05-15
|  |  | Define parameters of audit to be completed by Bolton Trust with follow-up telephone calls at 3, 12 and 24 months to assess acceptability and patient experience | Clare Garnsey/ Claire Goldrick | 2023-06-30 |  | 2023-05-15
|  |  | Continue to monitor implementation and provide ongoing support for FH nurses and monitor the utility, including: - Quarterly meetings - Review documentation - Gather feedback using questionnaires - Facilitate further education sessions and peer support | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Continue to engage with the Breast Cancer Screening Programme | NA | Continue to attend programme board meetings and GM Cancer and Breast Screening meetings regularly to share best practice, information on current programme and address workforce and capacity issues jointly | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
Faster Diagnosis (including BPTP) and Operational Improvement
| Continue 24 month programme of work to implement the mastalgia pathway across Greater Manchester (November 2022 - November 2024) | No | Develop and ratify mastalgia pathway supporting documentation including: - Patient Information - Standard Operating Procedure - ASPIRE service evaluation - Guidelines for triage of mastalgia clinic | Claire Robinson/ Claire Goldrick/ Clare Garnsey | 2023-07-31 |  | 2023-05-15
|  |  | Develop and approve ASPIRE national service evaluation metrics and data to support all Trusts evaluate the mastalgia pathway implementation | Claire Robinson/ Claire Goldrick/ Clare Garnsey | 2024-03-31 |  | 2023-05-15
|  |  | Develop and approve overall evaluation plan | Claire Robinson/ Claire Goldrick/ Clare Garnsey | 2023-07-31 |  | 2023-05-15
|  |  | Develop, pilot and review feedback mechanism from Secondary Care to Primary Care to include links to education materials previously developed | Claire Robinson/ Claire Goldrick/ Clare Garnsey | 2023-07-31 |  | 2023-05-15
|  |  | Regular communication with Primary Care and Locality Manager colleagues on implementation of mastalgia pathway, education and algorithm materials through Primary Care Network bulletins and other engagement events | Claire Robinson/ Claire Goldrick/ Clare Garnsey | 2024-03-31 |  | 2023-05-15
| Implementing Breast Best Practice Timed Pathway for Breast Cancer suspected cancer referrals and symptomatic referrals as per pathway guidelines | No | Assess current compliance and barriers to implementation through meetings with clinical and operation leads. - Working with FDS team within the alliance to address system fragility and barriers to delivery - Host individual meetings with clinical and operational teams to develop an implementation plan including: - Workforce development - Symptomatic referral clinics such as under 40s and men | Clare Garnsey/ Claire Goldrick/ Karen Hodgson | 2023-07-31 |  | 2023-05-15
| Addressing GIRFT report recommendations on Breast re-excision rates | NA | Attend workshop to ascertain current position in implementation of GIRFT recommendations on breast re-excision rates and work with operational delivery team to develop any necessary workstreams to address variation | Clare Garnsey/ Claire Goldrick/ Lisa Galligan-Dawson | 2023-07-31 |  | 2023-05-15
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Participate in national pan-alliance Breast oncology working group to address system fragility | NA | Attend regular working group meetings of pan-alliance working group including: - Contributing to the development of a joint document to raise awareness of oncology service fragility - Prepare and contribute to engagement and education sessions to share best practice | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Develop Model of Care for Breast Cancer oncology services including Secondary Breast Cancer to address service fragility | NA at this time | Complete regional capacity-demand scoping to address system fragility to form more detailed Model of Care strategy for Breast oncology services | Clare Garnsey/ Claire Goldrick | 2023-07-31 |  | 2023-05-15
|  | NA | Support the development of and ratify crib sheets summarising new Systemic Anti-Cancer Therapies. To include information on regimen, common side effects and patient eligibility | TBC/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| GM regional Breast Cancer guidelines | NA | Review and update regional guidelines for management of Breast Cancer | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Liver Metastases MDT referral pathway review | NA | Review findings from HPB service audit into the referral guidelines and address any changes/updates needed to guidelines | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Genetic Testing pathway | NA | Audit the use of the genetic testing guidelines and share results with pathway board members to address any issues identified | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
Personalised Care | Personalised Stratified Follow-Up: ensuring implementation of PSFU to ensure standardisation and quality of pathway for patients | NA | Review current status of PSFU pathways across GM including: - HNAs - PSFU protocols Review and address any gaps in more detail once review completed. | Andrea Webber/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. |  | Review deep dives of performance data (when provided by Personalised Care team) and support with development of action plans to increase performance | Andrea Webber/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Standardise and implement use of Treatment Summaries: |  | Review existing Treatment Summary templates to ensure standardisation of information and equity of access for patients | Andrea Webber/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| GM collation of HWB services information – identifying any Breast Cancer specific gaps |  | Agree any appropriate actions following review of current practice | Miranda Breen/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Genomics: Whole Genome Sequencing | NA | Supporting the implementation of WGS for eligible Breast Cancer patients when available. Working with Genomic Laboratory Hub to share consent process and identify any additional education needs for clinical teams | Simran Dhaliwal | 2024-03-31 |  | 2023-05-15
Patient Engagement and Involvement, Experience of Care
| Ensure appropriate PPIE representation for all board work programmes | N/A | To ensure each project has a PPIE representative on the task and finish group where appropriate including: - ETIP - Mastalgia Pathway - Education | Claire Goldrick | 2024-03-31 |  | 2023-05-15
| GM Cancer Alliance to support Metastatic Breast Cancer conference organised by METUPUK | NA | Provide clinical expertise, organisational support and attendance at the MBC conference | Clare Garnsey/ Claire Goldrick/ Claire O'Rourke | 2023-06-30 |  | 2023-05-15
Research
| Improving equity of access to research across Greater Manchester | NA | Engage with research clinical lead and wider GM Breast research leads to discuss how to improve equity of access to research for patients across the region | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
Workforce and Education
| Develop a comprehensive education and evaluation plan to support GPwER pilot | NA | Develop and share supporting documentation for GPwER onboarding and training, including: - Induction checklist - E-learning schedule - Clinical experiences log - Job planning and clinical experience checklists - Competency Framework (aligned to ASCEND) | Claire Robinson/ Claire Goldrick/ Clare Garnsey | 2023-06-30 |  | 2023-05-15
|  |  | Develop evaluation plan for GPwER pilot and approve through GM Cancer governance structure and continue to explore further funding/sustainability plans to extend the pilot |  | 2023-07-31 |  | 2023-05-15
|  |  | Develop, share and collate regular surveys to recruited GPwER regarding job satisfaction, training and education needs |  | 2024-03-31 |  | 2023-05-15
|  |  | Regular peer support sessions and education sessions |  | 2024-03-31 |  | 2023-05-15
| Regional face to face education day | NA | Hold regional full day education day for all members of the Secondary Care multidisciplinary team | Claire Goldrick/ Clare Garnsey/ Cancer Academy | 2023-11-30 |  | 2023-05-15
| Breast Cancer CNS Forum | NA | Facilitate quarterly meetings for CNS forum to include education element and peer support | Claire Liu/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
|  |  | Develop regional breast cancer development education days to encourage career development | Claire Liu/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| ETIP - Endocrine Therapy Improvement Plan: continuing to support implementation of toolkit and wider ETIP Programme | NA | Explore further and develop Primary/Secondary Care information/education needed to further address HRT queries | Clare Garnsey/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
|  |  | Provide clinical and service user expertise and guidance to support Cancer Academy education module development for patients taking endocrine therapy | Clare Garnsey/ Claire Goldrick | 2023-11-30 |  | 2023-05-15
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Colorectal
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Colorectal |  | Clinical Lead: Roger Prudham/Chelliah Selvasekar |  |  | Pathway Manager: Rachel Allen
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
General / Cross-cutting
| Develop a GM core standards / model of care document for lower GI service. |  | Formal document of core standards drafted. | Roger Prudham, Chelliah Selvasekar, Ali Jones, Louise Roberts | 31/03/2024
| Support Clinical Outcomes Data Strategy for Cancer Group to understand the needs of the pathway board with respect to clinical outcomes data. |  | Metrics to be agreed and endorsed by the Pathway Board. | Jenna Lane / John Moore | 31/03/2024
Early Diagnosis and Prevention (including screening)
| Continue to work with key partners to support public messaging and engagement to ultimately increase public awareness of cancer symptoms and encourage timely presentation (including screening). |  | Engagement in Bowel Cancer Awareness month (April). Resources shared across Trusts via Pathway Board. Engagement in symptom awareness communications all year round. | Anna Perkins | 31/03/2024 |  |  | Separate GM Cancer Communication Work Programme available with more in-depth detail.
| Support implementation of FIT guidance to ensure all lower GI referrals are accompanied by a faecal immunochemical test (FIT) result, where clinically appropriate in order to expedite patients through the colorectal cancer pathway, informing decisions about onward investigation. For example, clinically defining the cohorts of patients not applicable to FIT; addressing clinicians still scoping patients with a negative FIT result. |  | Engagement in FIT Task & Finish Group groups to support all FIT related initiatives requiring Pathway Board input. RA / RP attending FIT monthly T&F Group. Pathway Board updates provided. | Rachel Allen / Ali Jones | 31/03/2024
| Explore innovative approaches to the use of FIT in the lower GI pathway e.g. 'FIT in the community' vending machine concept. |  | Innovative concept scoped and shared with relevant stakeholders as appropriate for further progression/testing. Innovation funding bid submitted. | Roger Prudham / Ali Jones | 31/03/2024
| Engage with Lynch Syndrome project, providing clinical/secondary care guidance and subject-matter expertise as appropriate. |  | Standing agenda item on Pathway Board meetings as an opportunity for clinical discussion/contributions appropriate. Information shared with Pathway Board members as appropriate throughout lifetime of project. | Ali Jones / Sophie Walker | 31/03/2024 |  |  | Project is to ensure Lynch Syndrome testing is in place for all patients with colorectal cancer, improving the identification and management of the syndrome.
| Engage with Colon Capsule Endoscopy (CCE) project (national pilot), providing clinical/secondary care guidance and subject-matter expertise as appropriate. |  | Standing agenda item on Pathway Board meetings as an opportunity for clinical discussion/contributions appropriate. Information shared with Pathway Board members as appropriate throughout lifetime of project. | Ali Jones / Sophie Walker | 31/03/2024 |  |  | Project is to enable the roll-out of the Colon Capsule Endoscopy national pilot.
| Clinical lead to continue to attend and engage with Endoscopy Network Clinical Reference Group. |  | Regular attendance and engagement in meetings, feeding back to Pathway Board members. | Roger Prudham | 31/03/2024
| Annual review of suspected lower GI referral form with reminder to Pathway Board re: the importance of feeding back evidence of practices failing to comply with the agreed GM referral form. |  | Pathway Board to endorse referral form and share with ED Team ready for system upload by December 2023. | Rachel Allen / Sarah Taylor / Ali Jones | 31/12/2023
| Identify Director of Public Health to join the Pathway Board, representing all GM DPHs. Work with individual to reduce prevalence/incidence of locally advanced disease. |  | DPH identified and engaged in work of Pathway Board. Plan of action outlined by end of Q3 focusing on prevention of bowel cancer. | Rachel Allen / Ali Jones | 01/09/2023
| Identify topics for primary care education for delivery via Gateway C. |  | Design and delivery of Gateway C modules as appropriate. | Lauren Kelly / Ali Jones | 31/03/2024
Faster Diagnosis (including BPTP) and Operational Improvement
| Understand the delivery of the histopathology HODs service in relation to colorectal cancer in GM and the KPIs. |  | Pathology representative from Pathway Board identified to understand the service and the KPIs and what is not being met. Feed back progress to Recovery Panel. | Shailesh Agrawal | 31/03/2024
| Work alongside the FDS Programme Team to review the lower GI BPTP and support Trust delivery of BPTP milestones. |  | Collaboration with FDS team. Progress updates to be provided at Pathway Boards. | Sue Sykes / Karen Hodgson / Rachel Allen | 31/03/2024
| Host a BPTP workshop in collaboration with the FDS Programme team, facilitating regional discussion to identify barriers to compliance and develop regional solutions to improve performance. Outcomes and further plans to follow. |  | Workshop organised, discussion facilitated, outcomes captured. Suite of interventions identified and shared with Pathway Board for implementation. | Sue Sykes / Karen Hodgson / Rachel Allen | 31/09/2024
| Engage with SQD Project, beginning to scope out how single queue may potentially assist with the diagnostic waits in particular CTC. |  | Engagement with the project, providing clinical/secondary care guidance and subject-matter expertise as appropriate. Progress updates to be provided at Pathway Boards. | Sarah Hulme | 2024-03-31
| Review current triage STT pathways considering all forms of colonic imaging. Develop standardised GM colonic imaging pathway (to point of diagnosis). Scope of this to include imaging of the colon: CTC / CCE / endoscopy. |  | Pathways developed and endorsed by Pathway Board for implementation. | Rhidian Bramley / Jenna Lane / Roger Prudham | 2024-03-31
| Engage with CTC Pathway Redesign project, supporting specifically with the triage straight to test for CTC and advising and agreeing on the appropriate patient cohort for this. |  | Engagement with the project, providing clinical/secondary care guidance and subject-matter expertise as appropriate. Progress updates to be provided at Pathway Boards. Pathway developed and endorsed by Pathway Board for implementation. | Rhidian Bramley / Jenna Lane / Roger Prudham | 2024-03-31
| Support implementation of defined CTC Pathway across GM. |  | CTC Pathway implemented across GM. | Rhidian Bramley / Jenna Lane / Roger Prudham | 2024-03-31
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Address local access to colonic stenting for patients in a timely manner. |  | Baseline assessment of current provision complete with clear plan for improvement communicated to Pathway Board. | Rachel Allen | 2024-03-31
| Reduce variation in neoadjuvant radiotherapy treatment in rectal cancer patients undergoing resection, ensuring evidence-based local radiotherapy policies are in place. |  | Current performance breakdown shared. Improvement plan identified to address any variation. | Claire Arthur / Chelliah Selvasekar | 2024-03-31
| Review stoma reversal rates across the region, mapping to national standard (NBOCA data) to identify outliers. Work to inform future quality improvement piece. |  | Stoma reversal rates reviewed. Findings presented to Pathway Board with recommendations for future improvement work outlined. | Chelliah Selvasekar | 2024-03-31
| Patient Stratified Follow Up (PSFU): Review current PSFU pathway in line with updated guidance. |  | PSFU pathway reviewed and endorsed by Pathway Board. | Andrea Webber/ Rachel Allen / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2024-03-31
| Patient Stratified Follow Up (PSFU): Once PSFU pathway developed and built on infoflex, Pathway Board to support with promotion of use of system with clinical teams |  | All communications produced by PC team disseminated within Trusts and CNS groups. | Andrea Webber/ Rachel Allen / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2024-03-31
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. |  | Deep dives of performance data reviewed (when provided by PC team). Development of action plans to increase performance supported. | Andrea Webber/ Rachel Allen / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2024-03-31
| HNAs & Personalised Care Support Plans for all patients: Endorse and support GM standards developed for HNAs & PCSPs to ensure standardisation of quality for all patients. |  | Final standards developed and endorsed by Pathway Board. | Andrea Webber/ Rachel Allen / Amanda Coop / Sarah Sykes / Cheryl Pickup | 31/03/2024
| Standardise and implement use of Treatment Summaries: Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | New Treatment Summary templates developed (if required), approved at Pathway Board and disseminated through appropriate Trust forums. Updates by exception provided by PC team around low utilisation. | Rachel Allen / Amanda Coop / Sarah Sykes / Cheryl Pickup | 31/03/2024
| GM collation of HWB services information: Identify any tumour specific gaps for colorectal. |  | HWB self-assessment completed and appropriate representatives engaged in T&F Group to agree and progress with an action plan responding to any gaps. | Miranda Breen / Rachel Allen / Amanda Coop / Sarah Sykes / Cheryl Pickup | 31/03/2024
| Genomics: Continue to map out current patient pathway and identify current testing arrangements in each Trust to understand baseline position and identify solutions to common problems within pathway. |  | Update on findings and proposed solutions for improvement in turnaround times to be presented at June Pathway Board, seeking PB endorsement. | Simran Dhaliwal | 30/06/2023
| Genomics: Implement solutions across each Trust to ultimately reduce the turnaround time for genomics testing. |  | Solutions implemented across all Trusts with agreed ongoing-monitoring of progress provided to the Pathway Board. | Simran Dhaliwal | 31/03/2024
| Review approach to advanced pelvic surgery in GM (colorectal). |  | Approach reviewed. Surgical model endorsed by Pathway Board. | Chelliah Selvasekar | 2024-03-31
| Review of NBOCA data and the performance of GM with respect to emergency colorectal cancer presentation and management. This will be used to inform a future project focusing on the process, management and outcomes in emergency colorectal cancer management as a project, using real time data collection. |  | Review conducted, data analysed, and report published and shared with Pathway Board with identified actions for improvement. | Ajit Oberoi / Chelliah Selvasekar | 2024-03-31
Patient Engagement and Involvement, Experience of Care
| Patient representatives to attend and contribute to Pathway board meetings and identified workstreams/projects, raising issues and areas of concern from the colorectal cancer small community. |  | Active representation on Pathway Board and active small community. Small community meets 4 x year and input into Pathway Board discussions. | Jessica Carroll | Ongoing
Research
| Connect with Clinical Lead for Research and GM Cancer regarding how to plan for 2023/24 to increase % of patients in trials. |  | Colorectal Pathway Board Research Lead and GM Cancer Clinical Lead for Research to meet in Q1 (23/24) to plan for 2023/24 to increase % of patients in trials. | Kalena Marti | 2024-03-31
Workforce and Education
| Re-establish CNS Forum with nominated CNS chair & deputy. | n/a | CNS Forum re-established led by nominated CNS. First meeting to be hosted by Q2. | Rachel Allen / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2024-03-31
| Collaborate with The Christie to contribute to BIDA oncology meeting focusing on BAME communities in January/February 2024. |  | Joint BIDA oncology meeting held Q4 2024, collaborating with The Christie. | Mr Amit Sinha | 2024-03-31
| Promote the use of the digital staff passport within colorectal cancer services to support working as a network / development opportunities. |  | Communication around digital staff passport shared with Trust teams via the Pathway Board. Profile of passport raised during Pathway Board meetings (agenda item). Passport concept incorporated into relevant workstreams e.g. review of colonic stenting. | Jess Docksey / Clinical Leads / Rachel Allen | 2024-03-31
| Promote GM CNS Away Days (July & October), ensuring representation from colorectal CNSs. |  | Invitations for GM CNS Away Days cascaded to colorectal CNSs with active participation from colorectal CNSs at the events. | Rachel Allen / Amanda Coop | 2024-03-31
| Develop and deliver webinar on Anal Cancers. |  | Webinar designed, produced and delivered to interested healthcare professionals. | Rebecca Halstead / Molly Pipping | 2024-03-31
| Develop and deliver eLearning module on Appendiceal Cancer. |  | eLearning module designed, produced and delivered to interested healthcare professionals. | Rebecca Halstead / Molly Pipping | 2024-03-31
| Conduct audit to review capacity / demand to understand whether GM has the required surgical workforce for colorectal cancer. |  | Audit conducted and findings presented to Pathway Board with clear recommendations. | Jess Docksey | 2024-03-31
| Develop colorectal specific capability framework for CNSs aligned to the ACCEND framework working with Practice Educator. |  | Framework developed and endorsed by Pathway Board for adoption across GM Trusts. | Molly Pipping / new Practice Educator | 2024-03-31
| Develop Skills Lab focusing on stoma care. |  | Skills lab content designed, produced and delivered to interested healthcare professionals. | Molly Pipping / new Practice Educator | 2024-03-31
| Host GM Colorectal Pathway Board education event in Q4 to raise the profile of colorectal cancer; share the vision for the future; and showcase the work of the Pathway Board / GM Cancer in respect of colorectal cancer. |  | Education event designed, promoted and delivered for those with an interest in colorectal cancer. | Molly Pipping / Jess Docksey | 2024-03-31
| MDT reform: 1) develop, pilot and evaluate at least one Standard of Care (safe, clinically protocoled pathway) for a defined patient group. |  | SoC/Protocol developed, piloted for 6 months, and evaluated with findings and recommendations presented to Pathway Board for consideration. | Jess Docksey | 2024-03-31
| MDT reform: 2) test implementation of the patient impact statement at one Pilot site (The Christie). |  | Pilot site confirmed. Patient impact statement piloted for 6 months and evaluated with findings and recommendations presented to Pathway Board for consideration. | Jess Docksey / Chelliah Selvasekar | 2024-03-31
| MDT reform: 3) Promote the use of patient resources (infographic and animation) to inform patients of the role of the MDT within their care planning. |  | Patient resources shared with Trust teams via the Pathway Board. Team supported to embed patient resources within services through appropriate channels, such as, patient information protocols and Trust Communication Teams. Baseline survey conducted and repeated after 6 months to measure awareness and usage. | Jess Docksey / Rachel Allen / Roger Prudham / Chelliah Selvasekar | 2024-03-31
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Gynaecology
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Gynaecology |  | Clinical Lead: Nadia Ali-Ross |  |  | Pathway Manager: Eden Tagg
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Develop algorithms for primary care for 2ww referrals - post menopausal bleeding. |  | To develop an algorithm to inform a clinical decision making support tool in primary care to support quality of referrals | Sarah Taylor / Nadia Ali Ross / Suku George | 410624 |  | 2023-03-30
| Develop algorithms for primary care for 2ww referrals - post coital bleeding |  | To develop an algorithm to inform a clinical decision making support tool in primary care to support quality of referrals | Sarah Taylor / Nadia Ali Ross / Suku George | 2024-03-31 |  | 2023-03-30
| Raising awareness of cervical screening |  | To drill down further into data on poor uptake of cervical smears at practice level. To identify the areas to inform an action plan to target hard to reach groups and areas of poor uptake and look into alternate communication methods to patients for smear reminders. | Coral Higgins / Dan Clarke | 2023-12-31 |  | 2023-03-31
| IOTA scan training roll out project for primary and secondary care |  | To arrange a meeting with community scan providers and secondary care to discuss IOTA scan template to create a plan to roll out training across GM. | Nadia Ali Ross / Jim Wolfe / Sarah Taylor | 2023-12-31 |  | 2023-03-30
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | Nadia Ali Ross | 2023-12-31 |  | 2023-03-30
Faster Diagnosis (including BPTP) and Operational Improvement
| Develop BI quarterly dashboard for BPTP / FDS |  | To inform parameters for BI dashboard as outlined by CQUIN guidance and to approve at pathway board | Eden Tagg / Susan Sykes | 2023-12-31 |  | 2023-03-30 | To d/w BI team re: timeframe
| BPTP Workshop - To host a BPTP workshop to review what is going well, system learning and where improvements can be made. | N/A | Delivery of BPTP workshop in ... Workstreams to be implemented following workshop to work on improvements in line with National FDS standard (to add in specifics in next few months) | Eden Tagg | 2023-12-31 |  | 2023-03-30
| Include Mid/East Cheshire performance at pathway board |  | To include and to be presented at pathway board meeting. | Karen Hodgson / Susan Sykes | 2023-04-25 | Completed
| Review of one stop PMB provision |  | Scope where one stop clinics already exist and gaps. | Karen Hodgson / Susan Sykes
| Review of transvaginal ultrasound and hysteroscopy work force |  | To identify training requirements across GM to inform gap analysis of training requirements. To develop workforce to enable both transvaginal ultrasound and hysteroscopy to take place at one appointment. | Karen Hodgson / Susan Sykes
| LA to GA conversion rates for hysteroscopy / colposcopy |  | To understand the conversion rate and reasons | TBC
| Review CARP policy |  | To review the CARP policy to reduce delays on patient treatment decisions | Lisa Galligan Dawson Eden Tagg Lorraine Raymond | 2023-12-31 |  | 2023-03-30
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Patient Stratified Follow Up: Work with GM Personalised Care team to develop infoflex system for gynaecology. |  | Pathway Board to endorse final protocol pathway, inputting into the design review sessions and approve the final uploaded protocol on infoflex. PSFU pathway tested on infoflex by Board members and feedback shared with PC team. | Andrea Webber Jim Wolfe Sabine Forranton | 2023-12-31 |  | 2023-03-30
| Patient Stratified Follow Up (PSFU): Once PSFU pathway developed and built on infoflex Board to support with promoting use of system with clinical teams |  | Disseminate any comms produced by PC team within Trusts and CNS groups. Ensure representation at 1-2 learn & share sessions (post infoflex go live) to be held with civic post go live for ‘users’ to feedback any issues/updates required | Andrea Webber Jim Wolfe Sabine Forranton | 2023-12-31 |  | 2023-03-30
| HNAs & Personalised Care Support Plans for all patients: Endorse and support GM standards developed for HNAs & PCSPs to ensure standardisation of quality for all patients |  | Final standards developed and endorsed by Pathway Board. |  | 2023-12-31 |  | 2023-03-30
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. |  | Review deep dives of performance data (when provided by PC team) and support with development of action plans to increase performance |  | 2023-12-31 |  | 2023-03-30
| Standardise and implement use of Treatment Summaries: Begin review of existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | All treatment summaries collated ready for review beyond March 2023. New treatment summary templates identified where required. Information shared with Personalised Care team. |  | 2023-12-31 | Completed endometrial, need to review PIFU not used for cervical and ovarian treatment summaries may need to review PIFU when appropriate | 2023-03-30
| GM collation of HWB services information – identify any tumour specific gaps: |  | Complete HWB self-assessment and have appropriate representatives be part of a task&finish group to agree and progress with an action plan responding to any gaps. |  | 2023-12-31 |  | 2023-03-30
| Genomics: Engage with Personalised Care team to mobilise the GM Genomics Project. Begin to map out current patient pathway and identify current testing arrangements in each Trust to understand baseline position. |  | Pathway Board lead for genomics to be identified. Awaiting specific action from Simran | Simran Dhaliwal | 2023-12-31 |  | 2023-03-30
Patient Engagement and Involvement, Experience of Care
| Ensure appropriate PPIE representation for all board work programmes. | N/A | To ensure each project has a PPIE representative on the task and finish group where appropriate. | Eden Tagg | 2024-03-31 |  | 2023-03-14
| To establish a ovarian small community. | N/A | To establish a ovarian small community. | Becky Cook | 2024-03-31 |  | 2023-03-14
| To establish a endometrial small community. | N/A | To establish a endometrial small community. | Becky Cook | 2024-03-31 |  | 2023-03-14
Research
| Encourage research and innovation by improving entry of patients into trials. |  | Increase % of patients in trials as shown in the quarterly research report. promote clinic trials in all MDTs/access to trials, link in with David Thomson. | Andrew Clamp | 2023-12-31 |  | 2023-03-30
| Regular updates of Galleri trial to pathway board |  | To provide updates of the Galleri trial to pathway board with interim data analysis. | Sophie Walker | 2023-09-01
Workforce and Education
| Gynaecology Education Event - To host an education event to discuss the future of Gynaecological cancer pathways across Greater Manchester | N/A | Delivery of the education event. Review of survey monkey following event to help guide future events. | Eden Tagg Molly Pipping | Date postponed due to strikes | New Date June confirmed | 2023-03-14
| Develop pathways for primary care educational resources. |  | To share pathway information as per early diagnosis section. | Sarah Taylor / Nadia Ali Ross / Suku George
| MDT Reform - SMDT Protocolisation (Level 1 and 2) - To reduce the burden on MDT by protocolising low risk cancers (low risk xxxx) out of the SMDT setting to be triaged directly into a clinic as these cancers do not need oncological input. | N/A | To develop a GM wide protocol for cases to be discussed in SMDT. Audit of number of cases + types of cases being discussed in MDT. To identify small patient group that can be discussed outside of MDT. |  | 2024-03-31 |  | 2023-03-14
| Digital Staff Passport - Promote the use of the digital staff passport to support working as a network/development opportunities | N/A | Pathway board to support promotion of the digital staff passport across the system by sharing examples of use and identifying/supporting any staff groups that come forward wishing to advance digital passport use | Eden Tagg | 2024-03-31 | Paused by NHSE, resume when advised | 2023-03-14
| GM Cancer CNS Away Day | N/A | To support the planning and delivery of the GM Cancer CNS Away Day - Dates to be confirmed | Molly Pipping / Jack Quinn | TBC |  | 2023-03-14
| Vaginal Examination Skills Lab - To support the development of a vaginal examination, building on the atlas produced in 22/23 - skills lab with GM Cancer Academy | EIA to be completed. | Delivery of the Vaginal examination skills lab. | Suku George / Nadia Ali Ross | 2024-03-31 |  | 2023-03-14
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Haem Oncology
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Haemato-Oncology |  | Clinical Lead: Suzanne Roberts |  |  | Pathway Manager: Eden Tagg
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Haematology Pathway board event - early diagnosis - no screening program as such but trying to promote with early diagnosis. |  | Pathway Board Event to be delivered targeting local PCNs who do not attend through attendance logs | Eden Tagg / Suzanne Roberts | 2023-05-17
| Building Clinical Support Tools for Serum Free Light Chain Blood tests |  | Development of Clinical Support tool for Serum Free Light Chains | Suzanne Roberts | 2023-12-31
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | Suzanne Roberts | 2023-12-31
| NSS - Attend focus groups and work with Myeloma UK on early diagnosis |  | Attend focus groups with Myeloma UK and note suggestions to improve early presentation. | Suzanne Roberts | 2023-12-31
Faster Diagnosis (including BPTP) and Operational Improvement
| Audit lymphoma pathway - audit to be completed April and presented at April board. Local BPTP refresh for all of GM - try and link in with national development for haem. In the absence of national standards. Build contacts wider than GM. |  | To inform an action plan to improve BPTP across GM | Suzanne Roberts | 2023-09-01
| Single queue diagnostics - Single queue interventional radiology. |  | Arrange to meet with Sarah Hulme regarding update to radiology biopsies and single queue time frame. | Sarah Hulme / Lisa Galligan Dawson | 2024-03-31
| Direct booking for PET scans |  | PET CT scan policy to be reviewed / single queue diagnostics | Sarah Hulme / Lisa Galligan Dawson | 2023-12-31
| Review Pathway Navigators across the board for haem. Business cases failed previously. (only tumour site without pathway nav or after care coord) |  | To identify gaps in pathway navigators and consider how to reduce admin delays in haematology pathways including the use of pathway navigators. | TBC | 2023-12-31
| Haematology BPTP Workshop - To host a BPTP workshop to review what is going well, system learning and where improvements can be made. | N/A | Delivery of Haematology BPTP workshop. Workstreams to be implemented following workshop to work on improvements in line with National FDS standard (and as per Haem - to add in specifics in next few months) | Eden Tagg / Suzanne Roberts / Sue Sykes / Karen Hodgson | TBC |  | 2023-03-14
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Patient Stratified Follow Up: Work with GM Personalised Care team to develop, Board members to help test PSFU pathway on infoflex. Pathways approved, and in process of being built on infoflex. |  | Pathway Board to endorse final protocol pathway, inputting into the design review sessions and approve the final uploaded protocol on infoflex. PSFU pathway tested on infoflex by Board members and feedback shared with PC team. | Suzanne Roberts | 2023-12-31
| Patient Stratified Follow Up (PSFU): Once PSFU pathway developed and built on infoflex Board to support with promoting use of system with clinical teams |  | Disseminate any comms produced by PC team within Trusts and CNS groups. Ensure representation at 1-2 learn & share sessions (post infoflex go live) to be held with civic post go live for ‘users’ to feedback any issues/updates required | Suzanne Roberts | 2023-12-31
| HNAs & Personalised Care Support Plans for all patients: Endorse and support GM standards developed for HNAs & PCSPs to ensure standardisation of quality for all patients |  | Final standards developed and endorsed by Pathway Board. | CNS Forum - Lyndsey Hayes | 2023-12-31
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. |  | Review deep dives of performance data (when provided by PC team) and support with development of action plans to increase performance | CNS Forum - Lyndsey Hayes | 2023-12-31
| Standardise and implement use of Treatment Summaries: Begin review of existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | All treatment summaries collated ready for review beyond March 2023. New treatment summary templates identified where required. Information shared with Personalised Care team. | Suzanne Roberts | 2023-12-31
| GM collation of HWB services information – identify any tumour specific gaps: |  | Complete HWB self-assessment and have appropriate representatives be part of a task&finish group to agree and progress with an action plan responding to any gaps. | CNS Forum - Lyndsey Hayes | 2023-12-31
| Genomics: Engage with Personalised Care team to mobilise the GM Genomics Project. Begin to map out current patient pathway and identify current testing arrangements in each Trust to understand baseline position. |  | Genomics project to be standing agenda item moving forward. Pathway Board lead for genomics identified. Update to be provided at March Pathway Board on progress. | Simran Dhaliwal | 2023-12-31
Patient Engagement and Involvement, Experience of Care
| User reps to be involved in personalised care - small community for each tumour specific patient with different needs |  | Develop a Haematology small community | Becky Cook | 2023-12-31
CNS group | Patient involvement in MDT and how do we bring patient voice into MDT 'what's important to you?' question (MDT reform how overwhelmed are MDTs?' |  | Share patient charter? Discuss with CNS forum whether patient MDT questions can be asked prior to MDT. | Jack Quinn | 2023-12-31
Research
| On going - concentrated on central sites not out at DGHs - cannot open same volume of trials. Work force issues. Satellite clinic set ups - Christie / MFT research nurses / clinical fellow. Funding! Cannot recruit for clinical trials for 1 year. Require proof that trusts would pick this up (Reoccurring costs) SACT commissioning to work closer with solid tumour |  | To continue to recruit to trials and link in with David Thomson. |  | 2023-12-31
Workforce and Education
| Education event May to focus on early diagnosis. |  | Deliver education event and review post education survey to inform future events |  | 2023-05-17
| Education for MDT coordinators |  |  | Molly Pipping / Jack Quinn | 2023-12-31
| MDT reform: 1) develop, pilot and evaluate a minimum of 1 standard of care pathway, 2) support implementation of the patient impact statement, and 3) promote the use of patient resources (infographic and animation) |  | Identify small patient group to apply a standard of care to. | Suzanne Roberts | 2023-12-31
| Promote the use of the digital staff passport to support working as a network / development opportunities |  | Promote Staff Passport |  | 2023-12-31 | Paused by NHSE, to resume when advised
| GM CNS away day |  | Deliver CNS away day | Molly Pipping | 2023-04-26
| Delivery Gateway C Webinar - Rare cancers e.g. anaplastic large cell lymphoma |  | Deliver Webinar | Suzanne Roberts
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Head & Neck
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Head and Neck |  | Clinical Lead: David Thomson |  |  | Pathway Manager: Eden Tagg
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | David Thomson | 2024-03-31
| Develop Dental Algorithm for primary care. |  | To develop an algorithm to inform a clinical decision making support tool in primary care to support quality of referrals | David Thomson | 2024-03-31
| Refreshing the oral cancer guide for dentists |  | Oral Cancer guide reviewed, updated and shared widely with any supporting education identified and created. | Emma Hall Scullen | 2024-03-31
| Early exploration into data relating to health inequalities relating to head and neck presentation. |  | Request for data and audit shared. | David Thomson | 2024-03-31
| Link with OG pathway board regarding dysphagia algorithm |  | To match wording for both head and neck and OG if appropriate | Eden Tagg | 2024-03-31
| Develop simple algorithm for throat presentations in primary care. |  | To develop an algorithm to inform a clinical decision making support tool in primary care to support quality of referrals | David Thomson | 2024-03-31
Faster Diagnosis (including BPTP) and Operational Improvement
| Develop primary care resources - patient leaflet |  | To co-produce with service users a patient leaflet explaining the diagnostic pathway, helping to manage expectations and offer reassurance.
| Explore the role of ERS in the referral triage process and to understand RAS categories (Thyroid, neck lump, pain etc) |  | Ensure that subsite labels, Choose and Book and HSC205 categories are all consistent to achieve more focussed triage process. To support right clinic right time and maximise clinic capacity | Eden Tagg | 31/09/2023
| Improve subsite incompleteness |  | To monitor tableau subsite data for completeness. Issues around completeness are to be communicated to sites with clear action for improvement. | Eden Tagg / Laura Elliot | 2023-05-30
| Step down pathway for patients with throat presentations (initial telephone calls?) |  | Improve pathway efficiency, reduced two week wait, wait across GM. (50% can be stepped down at an early stage) developed. Support triage process to capture patients who can be stepped down |  | 2024-03-31
| BPTP Workshop - To host a BPTP workshop to review what is going well, system learning and where improvements can be made. | N/A | Delivery of BPTP workshop in ... Workstreams to be implemented following workshop to work on improvements in line with National FDS standard (to add in specifics in next few months) | Eden Tagg | 2024-03-31
| FNA under ultrasound guidance training |  | To deliver FNA training to radiologists and surgeons to improve time to diagnosis. |  | 2023-05-17
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Patient Stratified Follow Up: Work with GM Personalised Care team to develop, review & approve head and neck specific PSFU protocol pathway. Board members to help test PSFU pathway on infoflex. |  | Pathway Board to endorse final protocol pathway, inputting into the design review sessions and approve the final uploaded protocol on infoflex. PSFU pathway tested on infoflex by Board members and feedback shared with PC team. | Andrea Webber | 2024-03-31
| Patient Stratified Follow Up (PSFU): Once PSFU pathway developed and built on infoflex Board to support with promoting use of system with clinical teams |  | Disseminate any comms produced by PC team within Trusts and CNS groups. Ensure representation at 1-2 learn & share sessions (post infoflex go live) to be held with civica post go live for ‘users’ to feedback any issues/updates required | Andrea Webber | 2024-03-31
| HNAs & Personalised Care Support Plans for all patients: Endorse and support GM standards developed for HNAs & PCSPs to ensure standardisation of quality for all patients |  | Final standards developed and endorsed by Pathway Board. | Andrea Webber | 2024-03-31
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. |  | Review deep dives of performance data (when provided by PC team) and support with development of action plans to increase performance |  | 2023-12-31
| Standardise and implement use of Treatment Summaries: Begin review of existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | All treatment summaries collated ready for review beyond March 2023. New treatment summary templates identified where required. Information shared with Personalised Care team. |  | 2024-03-31
| GM collation of HWB services information – identify any tumour specific gaps: |  | Complete HWB self-assessment and have appropriate representatives be part of a task&finish group to agree and progress with an action plan responding to any gaps. |  | 2024-03-31
| Genomics: Continue to map out current patient pathway and identify current testing arrangements in each Trust to understand baseline position and identify solutions to common problems within pathway. |  | Update on findings and proposed solutions for improvement in turnaround times to be presented at June Pathway Board, seeking PB endorsement. | Simran Dhaliwal | 2023-06-30
| Genomics: Implement solutions across each Trust to ultimately reduce the turnaround time for genomics testing. |  | Solutions implemented across all Trusts with agreed ongoing-monitoring of progress provided to the Pathway Board. | Simran Dhaliwal | 2024-03-31
Patient Engagement and Involvement, Experience of Care
| To further engage with the head and neck small community and continue to recruit. |  | To further engage and develop relationships with the head and neck small community to inform future projects. | Becky Cook | 2024-03-31
| ? Engage small community when looking at health inequalities head and neck data |  | Engaged and included patient representative. |  | 2024-03-31
Research
| Encourage research and innovation by improving entry of patients into trials. |  | Increase % of patients in trials as shown in the quarterly research report. promote clinic trials in all MDTs/access to trials and link in with David Thomson as clinical lead for research. |  | 2023-12-31 |  | 2023-03-30
| Regular updates of Galleri trial to pathway board |  | To provide updates of the Galleri trial to pathway board with interim data analysis. | Sophie Walker | 2023-09-01
| Ensure appropriate PPIE representation for all board work programmes. | N/A | To ensure each project has a PPIE representative on the task and finish group where appropriate. | Eden Tagg | 2024-03-31 |  | 2023-03-14
Workforce and Education
| MDT Reform - Implementation of the patient impact statement. To develop a GM wide patient impact statement to be used across the system. | EIA to be completed. | Development and implementation of patient impact statement. | Jack Quinn | 2024-03-31 |  | 2023-03-14
| GM Cancer CNS Away Day | N/A | To support the planning and delivery of the GM Cancer CNS Away Day - Dates to be confirmed | Molly Pipping | TBC |  | 2023-03-14
| Digital Staff Passport - Promote the use of the digital staff passport to support working as a network/development opportunities | N/A |  | Eden Tagg | 2024-03-31 | Paused by NHSE, to resume when advised
| FNA training |  | To deliver FNA training | Jarod Hamner | 2023-05-17
| Evaluate the physician associate pilot |  | Evaluation produced and shared widely with plan identified. |  | 2024-03-31
| Gateway C Webinar on dysphagia |  | To deliver a webinar on dysphagia | David Thompson | 2024-03-31
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## HPB
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Hepato-Pancreato-Biliary |  | Clinical Lead: Thomas Satyadas |  |  | Pathway Manager: Claire Goldrick
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Suspected Cancer Referral Form: Annual review of referral form to ensure all relevant clinical information captured. | NA | Form reviewed and approved by Pathway Board and shared with Early Diagnosis team to be uploaded to Primary Care systems. | Claire Goldrick | 2023-12-31 |  | 2023-05-15
| Supporting the EUROPAC study and implementation of high-risk surveillance for hereditary Pancreatic cancer to meet NG85 NICE guidance | NA | Attend NHS England cancer programme kick-off meetings to determine the alliance responsibilities in supporting the EUROPAC study to further develop action plan to include sharing communication with Primary and Secondary Care. | Claire Goldrick/ Sophie Walker | 2023-05-31 |  | 2023-05-15
| Reviewing NHS England cancer programme tumour site review | NA | Review and discuss Pancreatic cancer tumour site review to understand any potential areas of focus for the pathway board work programme. Including clinical decision making tools. | Claire Goldrick/ Sophie Walker | 2023-07-31 |  | 2023-05-15
| Supporting the delivery of NHS England cancer programme Liver cancer surveillance project | No | Establish regular communication methods with Early Diagnosis team and steering group for ODN project and wider alliance deliverables for Liver surveillance programme. Confirm pathway board responsibilities following steering group first meeting. | Claire Goldrick/ Sophie Walker | 2023-07-31 |  | 2023-05-15
Faster Diagnosis (including BPTP) and Operational Improvement
| Implementing HPB Best Practice Timed Pathway for suspected HPB cancer as per pathway guidelines | NA | Review current compliance to BPTP through developing key milestone data reflecting the patient pathway in a dashboard | Thomas Satyadas/ Claire Goldrick | 2023-07-31 |  | 2023-05-15
|  |  | Host a BPTP workshop with clinical and operation leads to understand current compliance and barriers to develop an implementation plan to improve concordance with the pathway. To include: - Referral pathways and form - Triage processes - Utilisation of Ambulatory Care - Utilisation of NSS pathways - Consultant upgrades and identifying Emergency Department diagnoses - Diagnostic bundles - Clinical triage - Standardise patient information | Thomas Satyadas/ Claire Goldrick/ Sue Sykes | 2023-06-30 |  | 2023-05-15
|  |  | Identify key radiology contacts and Emergency Department/ Acute Oncology leads to develop protocol for identifying Pancreatic Cancer and referring to specialist MDT | Thomas Satyadas/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
|  |  | Continue to engage with Pancreatic Cancer UK through attending regular Optimal Care Pathway events and meetings | Thomas Satyadas/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
|  |  | Review current pathways and processes for consultant upgrades and rapid pathways to identify opportunities to improve time to first diagnostic test. Utilising data from audit completed in 2022. | Thomas Satyadas/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Referral Management: Develop and implement standardised feedback letter to improve referral quality | NA | Develop, pilot and review feedback mechanism from Secondary Care to Primary Care | Claire Robinson/ Claire Goldrick/ Clare Garnsey | 2023-07-31 |  | 2023-05-15
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. | NA | Review deep dives of performance data (when provided by Personalised Care team) and support with development of action plans to increase performance | Andrea Webber/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Standardise and implement use of Treatment Summaries: | NA | Review existing Treatment Summary templates to ensure standardisation of information and equity of access for patients. Create and approve any templates necessary | Andrea Webber/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| GM collation of HWB services information – identifying any Breast Cancer specific gaps | NA | Agree any appropriate actions following review of current practice | Miranda Breen/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Genomics | NA | Work with genomic project team to identify any HPB specific projects or tests available and develop implementation plan | Simran Dhaliwal | 2023-08-31 |  | 2023-05-15
| Liver Metastases Referral Pathway | NA | Conduct audit of numbers of patients referred to MDT for discussion following implementation of liver metastases referral pathway. Share results with HPB and Breast pathway boards | Thomas Satyadas/ Claire Goldrick | 2023-10-31 |  | 2023-05-15
| GM regional HPB Cancer guidelines | NA | Review and update regional guidelines for management of HPB Cancers | Thomas Satyadas/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
Patient Engagement and Involvement, Experience of Care
| Ensure appropriate PPIE representation for all board work programmes | N/A | To ensure each project has a PPIE representative on the task and finish group where appropriate. Work with PPIE team to assess whether a small community can be established | Claire Goldrick | 2024-03-31 |  | 2023-05-15
Research
| Improving equity of access to research across Greater Manchester | NA | Engage with research clinical lead and wider GM HPB research leads to discuss how to improve equity of access to research for patients across the region. Review results of Ancora pilot and continue to explore opportunities to discuss research further within the MDT | Thomas Satyadas/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
Workforce and Education
| Regional face to face education day | NA | Hold regional full day education day for all members of the Secondary Care multidisciplinary team | Claire Goldrick/ Thomas Satyadas/ Cancer Academy | 2023-12-31 |  | 2023-05-15
| HPB CNS Forum | NA | Facilitate quarterly meetings for CNS forum to include education element and peer support | Claire Goldrick | 2024-03-31 |  | 2023-05-15
|  | NA | Approve and communicate PERT related information and education to Primary Care colleagues through PCN bulletin | Claire Goldrick | 2023-07-31 |  | 2023-05-15
|  | NA | Develop, approve and share HPB education slides for Acute Oncology pathway board | Claire Goldrick | 2023-07-31 |  | 2023-05-15
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Lung
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Lung |  | Clinical Lead: Matthew Evison / Louise Brown (from 01/07/2023) |  |  | Pathway Manager: Jane Cronin
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening) | [6 empty] | 2023-05-10
| Early Diagnosis in symptomatic Lung Cancers - implementing & evaluating new, innovative ways into the lung cancer pathway |  | (1) Evaluation of the Self Referral Chest X-Ray (SRCXR) Pilot to be presented to the pathway board. (2) Expand the SRCXR pilot into a GM Programme that includes a lung symptom concern hotline, SRCXR & proactive safety netting after a normal Chest X-Ray in a single GM Service. (3) Evaluate the integration of AI CXR interpretation of CXR's in a GM Wide Pilot and present to pathway board. | Sarah Lyon / Rehan Naseer TBC TBC | 2024-03-31
| Increase knowledge and confidence in primary care in spotting signs & symptoms of lung cancer in never-smokers. |  | Deliver an education session for primary care on the signs & symptoms of lung cancer in never-smokers at a Cancer Forum Event to include the Ruth Strauss Foundation | Matt Evison | 2023-06-30 | Complete
| Increase knowledge and confidence in primary care in spotting signs & symptoms of lung cancer. |  | Refresh the Gateway C Webinar on Lung Cancer and develop new fast facts to be uploaded onto the Greater Manchester Gateway C Website. | Clinical Lead | 2024-03-31
| Inform and support patients when referred onto a lung cancer pathway (2WW) |  | Patient information leaflet co-produced with Pathway Board GP Representative, Localities (commissioners) & Service Users. To be uploaded to GP System by Early Diagnosis Team | Jane Cronin | 2024-03-31
| Expand the Targeted Lung Health Checks Programme and ensure sufficient diagnostic and treatment service capacity to meet this new demand. |  | Ensure that Targeted Lung Health Checks' deliverables align with Lung Pathway Board deliverables around symptomatic lung pathways by regular updates to the pathway board by the Targeted Lung Health Check Programme. | Clinical Lead / Oliver Butterworth | 2024-03-31
Faster Diagnosis (including BPTP) and Operational Improvement
| Prioritise the expansion of a single specialist cancer diagnostics digital platform across the GM Cancer system. To design, build, integrate, provide education and implement a digital platform across all trusts in Greater Manchester with all referrers able to book directly into all available appointments across GM to deliver a single Q service |  | Pathway Board to support the design, implementation, evaluation & ongoing expansion of the Single Q Service by providing representation, as required, in diagnostic sub-groups with any relative actions for the pathway board to be presented at pathway board and agreed. | Clinical Lead / Jane Cronin | 2024-03-31
| Develop, ratify & implement a new reflex testing protocol (reflex testing saves 8 days in the pathway on average) that includes a "rapid neoadjuvant pathway" |  | New Reflex Testing Protocol to be ratified by the Pathway Board | Matt Evison / Mayuri Basnet | 2024-03-31
| Complete self-assessment & action plans at individual locality and GM-wide against the GM Model of Care |  | a) Gap analysis to be undertaken in each of the providers with Pathway Board Trust Representatives to assist with data collection for baseline audit by liaising with departments within the Trust who are able to supply the data b) Gap analysis to be undertaken in primary care in 5 key areas as outlined in the Lung Model of Care. c) Pathway Board Trust Representatives to participate and co-ordinate appropriate attendance at site visits across 10 hospitals. This will assist the Lung Improvement Group to utilise the gap analysis to create action plans for each Trust to implement the recommendations in the Lung Model of Care. | Trust Representatives Ali Jones Trust Representatives | 31/03/2024 31/03/2024 31/03/2024
| Complete NHS England ctDNA pilot |  | Report GM results into pathway board and oversee adoption, if funded by NHSE. | TBC
| Expand the One-Stop Lung Cancer Clinic to provide a neoadjuvant chemo-immunotherapy & surgery pathway & broader multi-modality treatment service with appropriate evaluation of impact. |  | (1) Sub-group to be formed to scope workforce, pathology, MDT requirements to optimise access to adjuvant/neoadjuvant treatments in line with NICE recommendations and deliver new treatments that significantly improve survival. (2) Lung Pathway Board Molecular Sub-group to be formed to develop updated reflex testing protocol and deliver the optimal pathway. | Matt Evison / Jane Cronin Mayuri Basnet
| Implement a new "Rapid Small Cell Pathway" in Greater Manchester |  | Secure funding and support to test & evaluate a Rapid Small Cell pathway for Greater Manchester. | TBC
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Expansion of Prehab4Cancer programme |  | Evaluation of Prehab4Cancer programme to cover patients with Stage III & IV disease who are on active treatment and for patients who have had surgery before commencing adjuvant treatment to be presented at Pathway Board. | TBC | 2024-03-31
| Patient Stratified Follow Up (PSFU): Once Personalised Stratified Follow Up pathway developed and built on infoflex Board to support with promoting use of system with clinical teams |  | (1) Disseminate any communications produced by Personalised Care team within Trusts and Clinical Nurse Specialist groups (2) Ensure representation at 1-2 learn & share sessions (post infoflex go live) to be held with Civica for ‘users’ to feedback any issues/updates required | PWB Personalised Care Representative / Miranda Breen | 2024-03-31
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. |  | Review deep dives of performance data (when provided by Personalised Care team) and support with development of action plans to increase performance | PWB Personalised Care Representative / Andrea Webber | 2024-03-31
| Standardise and implement use of Treatment Summaries: Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | If currently in use Personalised Care team will update by exception PWBs which show low utilisation numbers | PWB Personalised Care Representative & Andrea Webber | 2024-03-31
| GM collation of HWB services information – identify any tumour specific gaps: |  | Complete HWB self-assessment and have appropriate representatives be part of a task&finish group to agree and progress with an action plan responding to any gaps. | PWB Personalised Care Representative & Miranda Breen | 2024-03-31
Patient Engagement and Involvement, Experience of Care
| Expand the Lung Cancer Small Community to contribute to Lung Pathway Boards, sub-groups and input into all aspects of the pathway. |  | Attendance by the 3 representatives at the PWB and their input into the PWB discussions/actions, and 2-way sharing information between the Pathway Board and the small community | User Involvement Manager | 2024-03-31
Research
| Publication of GM Cancer Lung Pathway Board Research / Audit / Pilots |  | (1) GM Reflex Testing and Genomic Pathway Audit, downstream effects & ctDNA Pilot. (2) Implementation of a one stop lung cancer clinic evaluation. (3) Prehab in curative intent oncology treatments. (4) Prehab in patients undergoing palliative SACT. (5) SRCXR Pilot (6) AI-CXR Pilot | Pathway Board Membership | 2024-03-31
Workforce and Education
| Educational models driven by workforce need to be developed and launched through GM Cancer Academy |  | (1) Utilising the Lung Education Event, scope the main topics of education required. (2) Identify subject matter experts to provide clinical expertise to assist with developing 10 modules to educate the non-medical workforce in Lung Cancer. | Molly Pipping Jane Cronin | 31/03/2024 31/03/2024
| MDT Reform |  | (1) Audit of number of patients not requiring discussion at MDT following implementation of MDT Standards of care to be presented to pathway board. (2) Support implementation of the patient impact statement. (3) Promote the use of patient resources (infographic & animation). | Gina Madera / Jane Cronin Gina Madera / Emma Halkyard / Jane Weir Gina Madera / Emma Halkyard / Jane Weir | 31/03/2024 31/03/2024 31/03/2024
| To support the recruitment, retention and succession planning of the Lung Nursing workforce and improve patient experience |  | Lung CNS Caseload Project to be scoped across GM with links to the national work being undertaken by LCNS | Emma Halkyard/ Jane Weir / Gina Madera | 2024-03-31
| GM Clinical Nurse Specialist away day |  | Promote and support the GM Clinical Nurse Specialist away day to inform and educate the GM Lung Nursing Workforce. | Jane Cronin | 2024-03-31
| Non-medical Referral for imaging pilot to support earlier diagnosis |  | Pathway Board to support the expansion of non-medical imaging requests by advising on wider appropriate workforce rollout. | Clinical Lead | 2024-03-31
| Support the development of a lung specific capability framework for non-medical workforce |  | Identify subject matter experts to support the development of a tumour specific capability framework aligned to ACCEND for the non-medical workforce. | Gina Madera / Jane Cronin | 2024-03-31
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Neuro-oncology
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Neuro-Oncology |  | Clinical Lead: Catherine McBain |  |  | Pathway Manager: Claire Goldrick
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Suspected Cancer Referral Form: Annual review of referral form to ensure all relevant clinical information captured. | NA | Form reviewed and approved by Pathway Board and shared with Early Diagnosis team to be uploaded to Primary Care systems. | Claire Goldrick | 2023-12-31 |  | 2023-05-15
Faster Diagnosis (including BPTP) and Operational Improvement
| MDT Reform: Supporting the Neuro-oncology regional service to implement Patient Pass | NA | Provide communications to relevant stakeholders to raise awareness of the roll-out of Patient Pass referral system for MDT. Facilitate presentations at relevant pathway boards e.g. Acute Oncology | Catherine McBain/ Claire Goldrick | 2023-07-31 |  | 2023-05-15
| Monitoring Faster Diagnosis compliance | NA | Monitor compliance to key Cancer Waiting Time Standards and escalate any issues or areas of improvement if applicable | Claire Goldrick | 2023-03-31 |  | 2023-05-15
| Referral Management: developing clinical decision making tools to improve referral quality and patient pathways | NA | Develop, ratify and implement clinical decision making tools for Primary Care colleagues to aid referral practices for patients presenting with headaches | Catherine McBain/ Claire Goldrick | 2023-12-31 |  | 2023-05-15
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. | NA | Review deep dives of performance data (when provided by Personalised Care team) and support with development of action plans to increase performance | Andrea Webber/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Standardise and implement use of Treatment Summaries: | NA | Review existing Treatment Summary templates to ensure standardisation of information and equity of access for patients. Create and approve any templates necessary. Review recording of PC elements within CWP and Somerset and agree reporting mechanisms. | Andrea Webber/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| GM collation of HWB services information – identifying any Neuro-oncology specific gaps | NA | Agree any appropriate actions following review of current practice. | Miranda Breen/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Delivering equitable Neuro-rehabilitation services to patients in GM | NA | Review current Neuro-oncology rehabilitation provision across GM and facilitate further discussion on findings and any appropriate action. | Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Improving Clinical Outcome Data | NA | Meet with clinical outcome data leads within alliance to establish current data collection and gaps/barriers to inform wider programme. | Jenna Lane/ Catherine McBain/ Claire Goldrick | 2023-06-30 |  | 2023-05-15
Patient Engagement and Involvement, Experience of Care
| Ensure appropriate PPIE representation for all board work programmes | N/A | To ensure each project has a PPIE representative on the task and finish group where appropriate. Work with PPIE team to assess whether a small community can be established | Claire Goldrick | 2024-03-31 |  | 2023-05-15
Research
| Development of a regional Neuro-oncology Pathology working group to address: - Improving equitable access to research - Standardising pathology data and metrics to support service development - Ensuring equitable access to Whole Genome Sequencing and other genomic testing | NA | Establish Neuro-oncology Pathology working group and arrange monthly meetings with representatives from research, pathology and genomics. | Catherine McBain/ Claire Goldrick | 2023-03-31 |  | 2023-05-15
|  |  | Establish baseline metrics for research studies, pathology (including tissue banking) and genomic testing to be produced at quarterly meetings | Catherine McBain/ Claire Goldrick | 2023-06-30 |  | 2023-05-15
Workforce and Education
| British Neuro-Oncology Society 2023 | NA | Support the Neuro-oncology team to deliver BNOS 2023 event. Ensure GM Cancer Alliance representation and support is provided to clinical team. | Claire Goldrick | 2023-07-31 |  | 2023-05-15
| Support regional education for brain metastases | NA | Contribute to the development of and ratify AO module on brain metastases for Cancer Academy. Support communications around Brain Metastases education day. | Jane Cronin/ Gina Madera - Cancer Academy/ Claire Goldrick | 2024-03-31 |  | 2023-05-15
| Continence guidelines to support patients with brain tumours | NA | Work with Cancer Academy to develop education and protocol for supporting patients with brain tumours in relation to continence. | Catherine McBain/ Claire Goldrick/ Cancer Academy | 2024-03-31 |  | 2023-05-15
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Oesophagogastric
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Oesophagogastric |  | Clinical Lead: Javed Sultan |  |  | Pathway Manager: Alexandra Riley
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Public Awareness Campaign - To raise awareness of oesophago-gastric cancer symptoms and promote timely presentations to the GP. | EIA to be completed | Delivery of awareness campaign. Increase proportion of referrals from specific GP practises. Qualitative evaluation on symptom knowledge and understanding risks. | Javed Sultan Alex Riley | 2024-03-31 |  | 2023-07-03
| Health Inequalities - To establish a baseline picture of deprivation and outcomes for oesophageal cancers across Greater Manchester. | N/A | Creation of database holding health inequalities data surrounding oesophageal cancers. | Javed Sultan | 2023-06-30 |  | 2023-07-03
| Dysphagia Algorithm - To support the implement the use of the dysphagia algorithm in primary care. | N/A | Implementation of algorithm. Re-audit | Sarah Taylor | 2024-03-31 |  | 2023-07-03
| Dyspepsia Algorithm - To support the implement the use of the dyspepsia algorithm in primary care. | N/A | Implementation of algorithm. Re-audit | Sarah Taylor | 2024-03-31 |  | 2023-07-03
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | Javed Sultan | 2023-12-31 |  | 2023-07-03
| Cytosponge - The OG Pathway Board will receive regular updates on the progression of this project and will assist in addressing any issues with delivery. The Pathway Board will also support the production of proposals for BAU commissioning. | N/A | The OG Pathway Board will receive regular updates on the progression of this project and will assist in addressing any issues with delivery. The Pathway Board will also support the production of proposals for BAU commissioning. | Sophie Walker | 2024-03-31 |  | 2023-07-03
| Gateway C Webinar - To discuss the assessment of Dysphagia and Dyspepsia, promote the use of the algorithms and raise awareness. | N/A | Delivery of Gateway C Webinar | James Britton | 2024-03-31 |  | 2023-07-03
Faster Diagnosis (including BPTP) and Operational Improvement
| Single Queue Diagnostics - To support the development and implementation of the use of single queue diagnostics for EUS/EUS FNA and PET CT Scanning across Greater Manchester for Oesophago-gastric patients. | EIA to be completed | To support the development of the single queue diagnostics services. To ensure appropriate representation from pathway board members within the working groups for each diagnostic. | Sarah Hulme Richard Keld (EUS) | 2024-03-31 |  | 2023-07-03
| One Stop Clinic - To develop and launch a One Stop Clinic for high risk patients to see a multidisciplinary team in one visit. | EIA to be completed | Launch of one stop clinic in March 2024. | Javed Sultan | 2024-03-31 |  | 2023-07-03
| OG BPTP Workshop - To host a BPTP workshop to review what is going well, system learning and where improvements can be made. | N/A | Delivery of OG BPTP workshop in March 2023. Workstreams to be implemented following workshop to work on improvements in line with National FDS standard. Deliverables to be updated following workshop and priority actions. | Alex Riley | 2023-06-30 |  | 2023-07-03
| Transnasal Endoscopic Diagnostics Service - To develop a TNE service across Greater Manchester to support TWW diagnostic capacity. | EIA to be completed | Implementation of TNE service. Evaluation of service. | James Britton | 2024-03-31 |  | 2023-07-03
| Biomarker Pathway - To confirm PDL-1 testing pathway for Greater Manchester Patients. To improve administrative processes across Greater Manchester to ensure timely and appropriate treatment to patients. | N/A | Implementation of the use of the Christie PDL-1 pathway (subject to UKAS accreditation in April 2023). Development of biomarker pathway to be embedded across Greater Manchester. | Stephen McGrath Was Mansoor | 2023-06-30 |  | 2023-07-03 | UKAS have postponed their visit to accredit the testing at the Christie due to workforce issues. We are awaiting a new date for inspection.
| Post RT Dilatation Protocol - To develop a GM protocol for Post Radiotherapy Strictures and the use of dilatation. | EIA to be completed | Development and publication of protocol. | James Britton | 2024-03-31 |  | 2023-07-03
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Patient Stratified Follow Up (PSFU): Once PSFU pathway developed and built on infoflex Board to support with promoting use of system with clinical teams | N/A | Disseminate any comms produced by PC team within Trusts and CNS groups. Ensure representation at 1-2 learn & share sessions (post infoflex go live) to be held with civica post go live for ‘users’ to feedback any issues/updates required. | Michelle Eden Andrea Webber | 2023-09-30 |  | 2023-07-03
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. | N/A | Review deep dives of performance data (when provided by PC team) and support with development of action plans to increase performance. | Michelle Eden Andrea Webber | 2024-03-31 |  | 2023-07-03
| Standardise and implement use of Treatment Summaries: Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. | N/A | Develop TS template (if required), approve and disseminate through appropriate Trust forums. If currently in use PC team will update by exception PWBs which show low utilisation numbers. | Michelle Eden Andrea Webber | 2024-03-31 |  | 2023-07-03
| Review of Trust HWB services: Trusts to review self-assessment action plans and complete HWB survey. | N/A | HWB self-assessment action plans reviewed. Survey shared with Trusts and responses collated with gaps requiring action identified. Information collated and shared with Personalised Care team ready for their analysis beyond March 2023. | Michelle Eden Miranda Breen | 2023-06-30 |  | 2023-07-03
| GM collation of HWB services information – identify any tumour specific gaps: | N/A | Complete HWB self-assessment and have appropriate representatives be part of a task&finish group to agree and progress with an action plan responding to any gaps. | Michelle Eden Miranda Breen | 2023-09-30 |  | 2023-07-03
Patient Engagement and Involvement, Experience of Care
| Ensure appropriate PPIE representation for all board work programmes. | N/A | To ensure each project has a PPIE representative on the task and finish group where appropriate. | Alex Riley | 2024-03-31 |  | 2023-07-03
Research
| Sarong Trial - To support the worldwide Sarong Trial during the GM elements at Salford Care Organisation to trial the development of a CT follow up protocol. | N/A | Update reports to be shared with pathway board. | Javed Sultan | 2024-03-31 |  | 2023-07-03
Workforce and Education
| GM Cancer CNS Away Day | N/A | To support the planning and delivery of the GM Cancer CNS Away Day - Dates to be confirmed | Alex Riley Molly Pipping | 2023-10-31 |  | 2023-07-03
| MDT Reform - Implementation of Low Grade Dysplasia SoC across Greater Manchester | N/A | To implement the use of the Low Grade Dysplasia SoC across Greater Manchester following pilot at NEC. | James Britton | 2024-03-31 |  | 2023-07-03
| MDT Reform - Implementation of the patient impact statement. To develop a GM wide patient impact statement to be used across the system. | EIA to be completed. | Development and implementation of patient impact statement. | Lead Needed | 2024-03-31 |  | 2023-07-03
| MDT Reform: Promote the use of patient resources (infographics and animation). | N/A | To share resources widely through PWB and OG network. | Lead Needed | 2024-03-31 |  | 2023-07-03
| Gateway C Webinar - To discuss the assessment of Dysphagia and Dyspepsia, promote the use of the algorithms and raise awareness. | N/A | Delivery of Gateway C Webinar | James Britton | 2024-03-31 |  | 2023-07-03
| Feeding Tube Skills Lab - To support the development of a feeding tube skills lab with the GM Cancer Academy | N/A | Delivery of feeding tube skills lab | Kellie Owen Molly Pipping | 2024-03-31 |  | 2023-07-03
| Dietetic Care at the Christie - To support the Christie in bolstering and sustaining their dietetic care team for oesophago-gastric cancer. | N/A | Review of dietetic service support at the Christie | Lead needed | 2024-03-31 |  | 2023-07-03
| ACCEND - To support the development of a tumour specific capability framework aligned to ACCEND for the non-medical workforce. | N/A | Ongoing review of the delivery of the ACCEND programme including promotion and uptake. | Trust Representatives | 2024-03-31 |  | 2023-07-03
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Psych Support
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Psychological Support and Mental Health |  | Clinical Lead: |  |  | Pathway Manager: Michelle Leach
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
Faster Diagnosis (including BPTP) and Operational Improvement
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
Deliver the Alliances psychosocial development plan | Work with mental health commissioning lead and the 2 key mental health providers within the LTC arm of the Talking Therapies services to move the project to initiation | NA | Project initiated | Pod McDonnell | 30.06.23 |  | 2023-04-03
Deliver the Alliances psychosocial development plan | Recruit to Project manager post and work up project documentation including EIA. Note SDF funding applies to 0.5WTE of an 8a project manager the remaining 0.5WTE and other project costs have been funded by Macmillan. | No | Recruitment completed | Michelle Leach | 31.07.23 |  | 2023-04-03
Deliver the Alliances psychosocial development plan | Macmillan NHSE Psycho-Oncology working group | No | Attend sub-group meetings and act as advisory body | Dan Anderson |  |  | 2023-04-03
Deliver the Alliances psychosocial development plan | psychosocial aspects of late effects of treatment | No | Group to act as clinical reference for creation of an action plan for psychosocial late effects of cancer (personalised care/supportive oncology) by March 2024 | Miranda Breen | 31.03.24 |  | 2023-04-03
Patient Engagement and Involvement, Experience of Care
Research
| Continue as part of the group looking at the use of psilocybin to aid cancer related distress from UoM. | No | Attend meetings and use pathway board as advisory capacity | Dan Anderson |  |  | 2023-04-03
Workforce and Education
| Level 2 training - Trial first pilot | No | First face to face session delivered | Anne Crook | 30.04.23 |  | 2023-04-03
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Sarcoma
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Sarcoma |  | Clinical Lead: Amit Kumar |  |  | Pathway Manager: Alexandra Riley
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| Establish Sarcoma advice and guidance | NA | Take forward MFT plan by October 2023 | Amit Kumar | 2023-10-31 |  | 2023-07-03
| Improve suspected cancer referral forms (SCR) | NA | Review and return any changes to ED by Dec 2022 | Amit Kumar | 2023-12-31 |  | 2023-07-03
| Audit 3rd party scan for quality | NA | Audit by MFT Sarcoma service by March 2024 with feedback to locality teams | Amit Kumar | 2024-03-31 |  | 2023-07-03
Faster Diagnosis (including BPTP) and Operational Improvement
| Create BPTP for Sarcoma | NA | Create by May 2023 | Amit Kumar | 2023-05-31 |  | 2023-04-03
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Patient Stratified Follow Up: Work with GM Personalised Care team to develop, review & approve sarcoma specific PSFU protocol pathway. Board members to help test PSFU pathway on Infoflex. | NA | Pathway Board to endorse final protocol pathway, inputting into the design review sessions and approve the final uploaded protocol on Infoflex. PSFU pathway tested on Infoflex by Board members and feedback shared with PC team. | Michelle Leach/Amit Kumar | 2023-09-30 |  | 2023-07-03
| HNAs & Personalised Care Support Plans for all patients: Endorse and support GM standards developed for HNAs & PCSPs to ensure standardisation of quality for all patients | NA | Final standards developed by Personalised Care Leads Forum shared with Pathway Board for endorsement and support with encouraging implementation within clinical teams across GM |  | 2024-03-31 |  | 2023-07-03
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. | NA | Review deep dives of performance data (when provided by PC team) and support with development of action plans to increase performance |  | 2023-03-31 |  | 2023-07-03
| Standardise and implement use of Treatment Summaries: Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. | NA | Christie – EoTS in use for radiotherapy patients. Develop EoTS template for Plastics. MFT – develop EoTS template with T&O supported by the PC team and UI. |  | 2023-06-30 |  | 2023-07-03
| GM collation of HWB services information – identify any tumour specific gaps: | NA | Complete HWB self-assessment and have appropriate representatives be part of a task&finish group to agree and progress with an action plan responding to any gaps. |  | 2023-09-30 |  | 2023-07-03
Patient Engagement and Involvement, Experience of Care
| Overhaul patient experience survey utilising governance knowledge from GM Cancer | NA | Create easier to complete survey by July 2023 | Helen Murray/Anna Perkins | 2023-07-31 |  | 2023-07-03 | Some changes recommended by PPIE representatives. Survey gone back through small community for review. To be rediscussed at Q2 PWB.
Research
Workforce and Education
| Create Module for cancer academy in conjunction with the WF&E team | NA | prepare content and provide personnel for any filming by Aug 2023 | Amit Kumar | 2023-07-31 |  | 2023-07-03 | Minimal responses to workforce need survey. Further promotion of survey and meetings arranged to review other ways of obtaining information with education team.
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Skin
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Skin |  | Clinical Lead: Stephanie Ogden |  |  | Pathway Manager: Jane Cronin
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening) | [6 empty] | 2023-05-12
| Deliver a "Sun awareness week" campaign - May 3rd - 9th 2023 |  | Working with the GM Cancer Communications Team, provide key messaging to targeted population to deliver a communications plan for Sun Awareness week utilising social media, and MEN article with evaluation of campaign to be presented to pathway board. | Stephanie Ogden / Jane Cronin | 2023-09-30 | Complete
| Raise public awareness of signs and symptoms of skin cancer including sun safety and skin cancer prevention |  | Develop a communications strategy with the GM Cancer Comms team supported by data to target specific, high risk, groups and deliver a communications plan including attendance at a GM specific, targeted public event with evaluation to be shared with pathway board. | Stephanie Ogden / Jane Cronin | 2024-03-31
| Scope a Sun Awareness Accredited Programme in GM Schools utilising a national SKCIN accreditation programme |  | Working alongside Public Health Teams scope what is already delivered on sun awareness in early years foundation stage, Key Stage 1 & Key Stage 2 with a view to piloting the SKcin Accredited Programme in 10 early years & Key Stage 1 & 2 settings across GM in 24/25. To be presented at pathway board. | Stephanie Ogden / Jane Cronin | 2024-03-31
| Review and update of suspected skin cancer referral form (HSC205) in collaboration with commissioning and primary care colleagues. |  | Form to be reviewed and agreed by the pathway board and revised form uploaded to system. | Jane Cronin | 2023-12-31
Faster Diagnosis (including BPTP) and Operational Improvement
| Improve the quality of 2 week wait referrals in primary care |  | (a) Promote the use of dermatoscopes in primary care by presenting at a Primary Care Network Cancer Lead Meeting to encourage use of dermatoscopic imaging in primary care (b) Assist with the development of a Clinical Decision Support Tool which links to the infographic and faster facts to be utilised in primary care by providing clinical input. | Stephanie Ogden / Lauren Kelly Stephanie Ogden / Lauren Kelly | 31/03/2024 31/03/2024
| Increase the identification of Seb K & AK in primary care and reduce 2 Week Wait referrals |  | 1) Pathway Board to provide quarterly revision to messaging to enable Gateway C Module to be promoted quarterly through Primary Care Network bulletin. 2) Support and attend an in person education event on identification of common skin lesions that can be managed through primary care such as Seborrheic Keratosis & Actinic Keratosis with an online resource to be developed from the education event and uploaded to GM Cancer Academy. 3) Assist with the development of a Seborrheic Keratosis & Actinic Keratosis Toolkit by providing clinical input to support the education of primary care and to be launched at the Seb K / AK Education Event. | Stephanie Ogden / Lauren Kelly Stephanie Ogden / Lauren Kelly / Ellen McWilliams Stephanie Ogden / Lauren Kelly / Ellen McWilliams | 31/03/2024 31/03/2024 31/03/2024
| Design and implement teledermatology for suspected skin cancer referrals |  | (1) Working with the GM Dermatology Transformation Programme and having representation across the workstreams of that group to ensure implementation of teledermatology across GM. (2) GM Dermatology Transformation Programme Model of Care to be presented at the pathway board with potential Pathway Board actions to be agreed. | Ali Jones / Paul Keeling / Karen Hodgson / Steph Ogden / Jane Cronin Paul Keeling / GM Derm Group / Pathway Board | 31/03/2024 30/06/2023
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. |  | Review deep dives of performance data (when provided by Personalised Care team) and support with development of action plans to increase performance | Stephanie Ogden / PWB Personalised Care Rep / Miranda Breen | 2024-03-31
| Standardise and implement use of Treatment Summaries: Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | Develop Treatment Summary template (if required), approve and disseminate through appropriate Trust forums. | PWB Personalised Care Rep / Andrea Webber | 2024-03-31
| GM collation of HWB services information – identify any tumour specific gaps: |  | Complete HWB self-assessment and have appropriate representatives be part of a task & finish group to agree and progress with an action plan responding to any gaps. | PWB Personalised Care Rep / Miranda Breen | 2024-03-31
Patient Engagement and Involvement, Experience of Care
| Develop a GM Dementia Skin Pathway to improve patient experience during cancer treatment |  | GM Dementia Pathway to be developed, presented and agreed at pathway board. | Pratap Dutta / Lorraine Burgess | 2024-03-31
| Improve the follow up pathway by formalising a Shared Care Protocol between the Melanoma Team, Plastics and Dermatology. |  | Utilising the NICE guidelines and working with colleagues in plastics, melanoma & dermatology to agree and ratify a new Shared Care Protocol at pathway board. | Stephanie Ogden / Emma Mitchell | 2024-03-31
| Expand the Skin Cancer Small Community to contribute to Skin Pathway Boards, sub-groups and input into all aspects of the pathway. |  | Attendance by the 2 representatives at the PWB and their input into the PWB discussions/actions, and 2-way sharing information between the PWB and the small community | User Involvement Manager | 2024-03-31
Research
| Research to be considered throughout the pathway |  | Pathway Board Research Lead to feedback quarterly on trials report/uptake and engagement of Trusts to partake. | Patricio Serra | 2024-03-31
Workforce and Education
| Deliver an education & engagement event to promote excellent Skin practice across GM & promote the work of the Skin Pathway Board |  | (a) Scoping to be undertaken to understand what education is required in Skin Cancer Services in Secondary Care. (b) Education & engagement event to be delivered and evaluation to be undertaken and shared with the pathway board. (c) Virtual education resource for the Cancer Academy to be developed from the education event. | Jane Cronin / Gina Madera Jane Cronin / Gina Madera Gina Madera | 31/03/2024 31/03/2024 31/03/2024
| Support the future dermatology workforce by exploring different roles |  | (a) Ongoing evaluation of the Physician's Associate role to be undertaken to understand if this is a model that can assist with the workforce pressures in dermatology (b) If required, support the identification and development of new innovative workforce models for skin cancer through the GM Dermatology Transformation Programme by providing clinical input to the workforce sub-group. | Jane Cronin / Gina Madera Steph Ogden / Gina Madera / Suzanne Lilley | 31/03/2024 31/03/2024
| MDT Reform |  | (a) Support implementation of the patient impact statement through the CNS Network by presenting at Skin CNS Network meeting. (b) Promote the use of patient resources (infographic & animation). | Amanda McQueen / Jess Docksey Jane Cronin / Jess Docksey | 31/03/2024 31/03/2024
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review

## Urology
Greater Manchester Cancer Pathway Board Work Programme 2023.2024
GM Cancer Pathway Board: Urology |  | Clinical Lead: Sotonye Tolofari |  |  | Pathway Manager: Alexander Riley
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver) | EQIA completed (n/a, yes or no) | Measure SMART (the output/ evidence that the deliverable is completed) | Responsibility - Named lead i.e. a PWB member/ designated lead | Completed by end of (month/year) In year, i.e. by 31/3/24 | RAG Status once complete, add 'complete' to green RAG status & keep on the work prog. | Date last updated (monthly) | Comments add only if RAG status is amber/red (include mitigation/any plans in place)
Early Diagnosis and Prevention (including screening)
| National Prostate Cancer Case Finding Pilot/Black Men's Health Awareness Campaign - To raise awareness of prostate cancer in at risk groups across Greater Manchester (black african caribbean men over the age of 45 and men over the age of 45 with a family history of prostate cancer) . To provide education to primary care. To aid early diagnosis of prostate cancer. | Yes | Delivery of mobile outreach clinics across Greater Manchester. Project evaluation in line with NHSE evaluation guidance supported by NECS. Local evaluation to include qualitative research on change of behaviours in at risk communities for both patients and primary care networks. | Sot Tolofari (Clinical Lead) Millie Wadley (PM) | 410624 |  | 2023-07-03
| Prostate Cancer Awareness Events - To host prostate cancer awareness events for the Jewish and Transgender communities, tackling health inequalities, using resources learnt from the National Prostate Cancer Case Finding Pilot. | Yes | Delivery of educational awareness events. User feedback questionnaires to be completed. | Sot Tolofari (Clinical Lead) Millie Wadley (PM) | 2024-03-31 |  | 2023-07-03
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | Sot Tolofari | 2023-12-31 |  | 2023-07-03
| Public Awareness Campaign for Haematuria - To raise awareness and propensity to act on haematuria in line with the national tumour site review guidelines. | EIA to be completed. | Delivery of public awareness campaign. Comms hits. User feedback. | Amar Mohee | 2024-03-31 |  | 2023-07-03
| Gateway C Webinar - To discuss the assessment of haematuria and TWW Referrals associated with Bladder and Renal Cancers. | N/A | Delivery of Gateway C Webinar. | Sotonye Tolofari | 2024-03-31 |  | 2023-07-03
| EGFR Audit - To carry out an audit on the numbers of TWW referrals coming into the system that had a normal eGFR versus an eGFR greater than 60 in light of the removal of eGFR from the TWW referral criteria. | N/A | Audit results to be completed by September 2023 prior to the TWW referral form review date to guide whether eGFR is required or not. | Jeremy Oates Anas Hattab | 2023-09-30 |  | 2023-07-03
Faster Diagnosis (including BPTP) and Operational Improvement
| Centralised and Protocolised MR Reporting - In order to improve our FDS for prostate cancer, we need rapid MR appointment and reporting prior to prostate biopsy. The best way to achieve this would be through a centralised MR hub where reports can be undertaken within 24hrs utilising protocolised reporting methods. | N/A | To agree on MR reporting protocol. To implement GM wide MR reporting. Long term impact on FDS for prostate pathway. | Anas Hattab | 2024-03-31 |  | 2023-07-03
| Prostate BPTP Workshop - To host a BPTP workshop to review what is going well, system learning and where improvements can be made. | N/A | Delivery of Prostate BPTP workshop in July 2023 Workstreams to be implemented following workshop to work on improvements in line with National FDS standard. Deliverables to be updated following workshop and priority actions. | Alex Riley | 2023-07-31 |  | 2023-07-03
| TURBT Hub - Currently failing to meet FDS target on bladder pathway primarily due to delays on histology. To create a centralised pathway where TURBT's can be undertaken at a single site within GM in order to alleviate the pressure on base hospitals on getting patients operated on in a timely fashion. Collaboration required across GM to try to improve the bladder FDS and 62 day position. | EIA to be completed. | Service implementation and delivery of TURBT Hub. Service utilisation of TURBT Hub. Long term impact on FDS for bladder pathway. | James Dyer | 2024-03-31 |  | 2023-07-03
| TULA - To embed TULA pathway across Greater Manchester to aid delivery of treatment of cancers in timely manner. | N/A | Audit of TULA procedures across Greater Manchester from September 2021 to September 2023. Delivery of TULA education session in June 2023. Evaluation report to be published outlining benefits of TULA including patient benefits, system benefits and health economics. | Alex Hoyle Matthew Liew | 2023-09-30 |  | 2023-07-03
Treatments and Care (including Personalised Care, Genomics, Treatment Variation - GIRFT)
| Patient Stratified Follow Up (PSFU): Once PSFU pathway developed and built on infoflex Board to support with promoting use of system with clinical teams | N/A | Disseminate any comms produced by PC team within Trusts and CNS groups. Ensure representation at 1-2 learn & share sessions (post infoflex go live) to be held with civica post go live for ‘users’ to feedback any issues/updates required. | Prostate - Ruth Conroy Bladder - James Dyer Renal - Stephen Bromage Andrea Webber | 2023-09-30 |  | 2023-07-03
| HNAs & Personalised Care Support Plans for all patients: provide guidance when/if needed based on deep dives of data & performance. | N/A | Review deep dives of performance data (when provided by PC team) and support with development of action plans to increase performance. | Sally Botham Laura Jones Andrea Webber | 2024-03-31 |  | 2023-07-03
| Standardise and implement use of Treatment Summaries: Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. | N/A | Develop TS template (if required), approve and disseminate through appropriate Trust forums. If currently in use PC team will update by exception PWBs which show low utilisation numbers. | Prostate - Ruth Conroy Bladder - James Dyer Renal - Stephen Bromage Andrea Webber | 2023-06-30 |  | 2023-07-03
| Review of Trust HWB services: Trusts to review self-assessment action plans and complete HWB survey. | N/A | HWB self-assessment action plans reviewed. Survey shared with Trusts and responses collated with gaps requiring action identified. Information collated and shared with Personalised Care team ready for their analysis beyond March 2023. | Sally Botham Laura Jones Miranda Breen | 2023-06-30 |  | 2023-07-03
| GM collation of HWB services information – identify any tumour specific gaps: | N/A | Complete HWB self-assessment and have appropriate representatives be part of a task&finish group to agree and progress with an action plan responding to any gaps. | Sally Botham Laura Jones Miranda Breen | 2023-09-30 |  | 2023-07-03
| Genomics: Continue to map out current patient pathway and identify current testing arrangements in each Trust to understand baseline position and identify solutions to common problems within pathway. |  | Update on findings and proposed solutions for improvement in turnaround times to be presented at Pathway Board, seeking PB endorsement. | Simran Dhaliwal | 2023-06-30 |  | 2023-07-03 | Delays in getting this started due to awaiting clinical leadership. Now progressing, meetings in place. To be presented at September pathway board.
| Genomics: Implement solutions across each Trust to ultimately reduce the turnaround time for genomics testing. |  | Solutions implemented across all Trusts with agreed ongoing-monitoring of progress provided to the Pathway Board. | Simran Dhaliwal | 2024-03-31 |  | 2023-07-03
Patient Engagement and Involvement, Experience of Care
| Ensure appropriate PPIE representation for all board work programmes. | N/A | To ensure each project has a PPIE representative on the task and finish group where appropriate. | Alex Riley | 2024-03-31 |  | 2023-07-03
| To increase representation for all tumour sites at small community. | N/A | To ensure equal representation for all tumour sites at the small community forum. | Jessica Carroll | 2024-03-31 |  | 2023-07-03
Research
| Remote PSA Sampling - To run a research project to establish the clinical correlation between microsampling kits and serum sampling for PSA surveillance patients. | EIA to be completed. | Completion of research project by March 2024 including publication of evaluation report. | James Osborne Angelos Tselos | 2024-03-31 |  | 2023-07-03
| To write and publish an evaluation report on the Prostate Cancer Case Finding Project. | N/A | Publication of report. | Sot Tolofari Ashwin Sachdeva | 2024-03-31 |  | 2023-07-03
| To write and publish an evaluation report on the TULA service model. | N/A | Publication of report. | Alex Hoyle Matt Liew | 2023-09-30 |  | 2023-07-03
Workforce and Education
| Urology Education Event - To host an education event to discuss the future of urological cancer pathways across Greater Manchester | N/A | Delivery of the education event. Review of survey monkey following event to help guide future events. | Alex Riley Molly Pipping | 2023-06-30 | Complete | 2023-07-03
| Gateway C Webinar - To discuss the assessment of haematuria and TWW Referrals associated with Bladder and Renal Cancers. | N/A | Delivery of Gateway C Webinar. | Sotonye Tolofari | 2023-10-31 |  | 2023-07-03
| GM Cancer CNS Away Day | N/A | To support the planning and delivery of the GM Cancer CNS Away Day - Dates to be confirmed | Alex Riley Molly Pipping | 2023-10-31 |  | 2023-07-03
| MDT Reform - SMDT Protocolisation (Level 1 and 2) - To reduce the burden on MDT by protocolising low risk cancers (low risk prostate, bladder and renal cancer) out of the SMDT setting to be triaged directly into a clinic as these cancers do not need oncological input. | N/A | To develop a GM wide protocol for cases to be discussed in SMDT. Audit of number of cases + types of cases being discussed in MDT. | Euan Green | 2024-03-31 |  | 2023-07-03
| Review guidance on what should be discussed at level 1 and level 2 MDT's. | N/A | To create guidance of cases to be discussed at Level 1 and Level 2 MDT's across the city. Audit the number and type of cases in SMDT meeting guidance. | Maria Serra | 2024-03-31 |  | 2023-07-03
| MDT Reform - Implementation of the patient impact statement. To develop a GM wide patient impact statement to be used across the system. | EIA to be completed. | Development and implementation of patient impact statement. | Lead Needed | 2024-03-31 |  | 2023-07-03
| MDT Reform: Promote the use of patient resources (infographics and animation). | N/A | To share resources widely through PWB and Urology networks | Lead Needed | 2024-03-31 |  | 2023-07-03
| Catheterisation Skills Lab - To support the development of a catheterisation skills lab with GM Cancer Academy | EIA to be completed. | Delivery of the catheterisation skills lab. | Lead Needed | 2024-03-31 |  | 2023-07-03
RAG status | On track, if complete add 'complete' to the green RAG status
Behind but have measures in place to get back on track
Won't complete within timeframe, of concern and requires review