## Lists
Progress
Not started
On track
Delayed progress
Major concerns
Complete

## MASTER 25.26
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: xx/xx/xxxx
GM Cancer Pathway Board: |  |  | Clinical Lead: |  | Pathway Manager:
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - ie by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
Not started
On track
Delayed progress
Major concerns
Complete
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
Research
Workforce and Education incl. ACCEND
Status:

## Acute Oncology
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 16/7/25
GM Cancer Pathway Board: Acute Oncology |  |  | Clinical Lead: Caroline Wilson |  | Pathway Manager: Louise Farnworth
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
N/A
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
N/A
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
Priority: AO Strategy phase 1, Virtual MDTs | Software identified and developed to hold daily MDTs. |  | Software to be identified and developed |  | 2025-04-01 | 2026-03-31 | Complete
Priority: AO Strategy phase 1, Virtual MDTs | Individual trusts to introduce daily virtual MDTs |  | One trust at a time to be brought into the Daily Virtual MDTs. |  | 2025-04-01 | 2026-03-31 | Not started
AO Strategy phase 2, SDEC | Options paper to be developed for Phase 2 of the 5 year Acute Oncology Strategy |  | Options paper to be developed |  | 2025-04-01 | 2026-03-31 | On track
| Standardised service Specification developed |  | Working with Clatterbridge to develop a standardised service specification for Acute Oncology |  | 2025-04-01 | 2026-03-31 | Not started
| Comprehensive access to cancer intelligence to understand inequalities |  | Roll out data proforma to all remaining trusts |  | 2025-04-01 | 2026-03-31 | On track
Priority: AO Strategy phase 1, Virtual MDTs | Health economics report to be delivered at the end of phase 1 |  | Health economics report to de delivered at the end of phase 1 |  | 2025-04-01 | 2026-03-31 | On track
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Ensure that service users are included in all areas of AO Work programme and pathway board |  | Recruitment of 2nd patient carer rep for the PWB |  | 2025-04-01 | 2026-03-31 | On track
| Ensure that service users are included in all areas of AO Work programme and pathway board |  | Ensure there is service user representation in all work streams and sub-groups of the board |  | 2025-04-01 | 2026-03-31 | On track
Research
Workforce and Education incl. ACCEND
| Develop resources and engage with primary care on cancer emergencies and how to recognise acute side effects of treatment |  | 1. Working with Primary Care Lead and Early Diagnosis Team, deliver a presentation at Cancer Forum to educate GPs to recognise acute side effects of anti-cancer treatment that may result in an emergency presentation and combine with a patient impact video |  | 2025-04-01 | 2026-03-31 | Not started
|  |  | 2.Presentation to be recorded and uploaded to Gateway C with a fast facts and infographic to be developed |  | 2025-04-01 | 2026-03-31 | Not started
|  |  | 3. Ensure there is GP representation on the pathway board |  | 2025-04-01 | 2026-03-31 | On track
Status:

## Breast
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 16/07/2025
GM Cancer Pathway Board: Breast |  |  | Clinical Lead: Miss Clare Garnsey Deputy Clinical Lead: Dr Anne Armstrong |  | Pathway Manager: Claire Goldrick
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Suspected Cancer Referral Form: Annual review of referral form to ensure all relevant clinical information captured | NA | Form reviewed and approved by Pathway Board and shared with Early Diagnosis team to be uploaded to Primary Care systems | Claire Goldrick/ Caitlin Hudson | 2025-09-01 | 2025-11-30 | Not started
| Continue to deliver Primary Care education programme on management of breast symptoms. | NA | Continue to share and promote education materials on: - Mastalgia - Breast symptoms - Metastatic Breast Cancer symptoms | Clare Garnsey/ Claire Goldrick/ Caitlin Hudson | 2025-04-01 | 2026-03-31 | On track
|  |  | Develop educational materials to support: - Gynaecomastia and aesthetics using effective use of resource guidance. | Clare Garnsey/ Claire Goldrick/ Caitlin Hudson | 2025-08-01 | 2026-03-31 | Not started
| Priority 1: Working with the Early Diagnosis and Comms & Engagement Team, develop data driven assets to engage communities within Greater Manchester to improve symptomatic presentations. | NA | Work with the ED and Comms & Engagement teams to provide clinical input to the development of assets to support symptomatic presentation. | Clare Garnsey/ Claire Goldrick/ Ali Jones/ Caitlin Hudson/ Ali Barbuti | 2025-04-01 | 2025-08-31 | On track
| Improve awareness of lifestyle changes to support risk reduction for women without a diagnosis of breast cancer. | NA | Design and produce leaflet that can be shared with women who go through triple assessment without a cancer diagnosis. | Veronica Rafferty/ Claire Goldrick | 2025-09-01 | 2025-12-31 | Not started
| ETIP: Endocrine Therapy Improvement Plan: - Risk Reducing Endocrine Therapy toolkit: Continue to embed toolkit supporting Family History teams to increase the number of women at moderate/high risk of breast cancer offered and prescribed risk reducing endocrine therapy - Evidence based education for women and cancer workforce around the use of Hormone Replacement Therapy - Multi-layered education programme to support patients experiencing adverse side effects from Endocrine Therapy. | NA | 1. Continue to monitor implementation of risk-reducing toolkit: Audit currently ongoing, continue to monitor progress. | Clare Garnsey/ Angela Duckworth/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
|  |  | 2. Continue to support Family History teams and GPs with Extended Role to embed toolkit and monitor utility: - Quarterly meetings to discuss implementation - Provide education where necessary | Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
|  |  | 3. Continue to support Personalised Care innovation funded project to deliver clinic to support patients on Endocrine Therapy: - Provide clinical leadership and project management oversight and support - Support development of standardised documentation - Participate in project Task and Finish Group meetings - Continue to disseminate and promote Primary and Secondary Care educational materials - Support sustainability of project linking to wider Model of Care | Anne Armstrong/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
|  |  | 4. Develop leaflet re HRT for women at high risk of developing breast cancer | Clare Garnsey/ Claire Goldrick | 2025-07-01 | 2025-09-30 | On track
|  |  | 5. Utilise Gilead and PC Innovation funding to lead design of support materials for patients on exercise and lifestyle changes that can support symptom management. | Anne Armstrong/ Claire Goldrick | 2025-06-01 | 2026-03-31 | Not started
|  |  | 6. Develop, ratify and share Endocrine Therapy extension guidelines for patients with a breast cancer diagnosis | Anne Armstrong/ Claire Goldrick | 2025-07-01 | 2025-09-30 | On track
| Continue to engage and support the breast screening team |  | Continue to attend programme meetings, GM Cancer Alliance and screening team meetings regularly to share priorities, best practice and share information on current work programmes to address workforce and capacity issues jointly | Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
| Priority 2: Implementation of mastalgia pathway (continuation of project from November 22 - November 24). Planning guidance 24/25: All trusts must have suitable alternate mastalgia pathway in place | Yes | 1. Continue to support Trusts in Greater Manchester to utilise ASPIRE database to gather further evidence to support mastalgia pathway evaluation. Pull ASPIRE data to assess the pathway and determine safety of omitting mammograms in over 40s | Claire Garnsey/ Claire Robinson/ Claire Goldrick | 2025-04-01 | 2025-10-31 | On track
|  |  | 2. Disseminate mastalgia evaluation | Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2025-09-30 | Delayed progress
|  |  | 3. Continue regular communication with Primary Care and Locality Manager colleagues on implementation of mastalgia pathway, education and materials through PCN and other engagement events | Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
| Monitor compliance with Cancer Waiting Time Standards for Suspected and Cancer Not Suspected Breast referrals. | NA | Monitor current compliance and barriers to implementation through meetings with clinical and operational leads - Working with FDS team within alliance to address system fragility and barriers to delivery | Clare Garnsey/ Claire Goldrick/ Kerry Porter | 2025-04-01 | 2026-03-31 | On track
| Priority 3: National Planning Guidance 25/26: GIRFT recommended review of current practice for immediate reconstruction following mastectomy for early breast cancer patients | NA | 1. Develop survey to understand current practice Gather feedback and meet with trust leads to discuss next steps | Clare Garnsey/ Claire Goldrick | 2025-06-01 | 2025-09-30 | Not started
| Priority 3 continued: National Planning Guidance 2024/25: Support all trusts to understand their rates of re-excision following breast conserving surgery | NA | 2. Analyse results of audit (01Sp2024 - 28Feb2025) and develop actions to support improvement in variation | Clare Garnsey/ Claire Goldrick | 2025-05-01 | 2025-09-30 | Complete
| Priority 4: Develop Model of Care for breast cancer oncology services including Metastatic Breast Cancer to support service sustainability | NA | 1. Define and agree AO pathways for MBC patients; - New diagnosis at ED - Patient known with new issue - Patient not known but with history of BC | Anne Armstrong/ Claire Goldrick | 2025-06-01 | 2025-10-31 | Not started
|  |  | 2. Provide governance and support to Collaborative Working Partnership with Novartis to improve pathway efficiency and patient experience - Provide oversight and clinical leadership - Facilitate PPIE through small community - Ratify pathways and share mapping outcomes - Link to wider Model of Care strategy for SACT | Anne Armstrong/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
|  |  | 3. Participate in national pan-alliance breast oncology working group to address system fragility | Anne Armstrong/ Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
|  |  | 4. Develop education materials to support accurate recording of MBC data within MDTs | Claire Goldrick | 2025-04-01 | 2025-09-30 | Delayed progress
|  |  | 5. Work with Clinical Data Outcomes group to complete project identifying MBC patients utilising data from NDRS and event level data | Clare Garnsey/ Anne Armstrong/ Claire Goldrick | 2025-04-01 | 2025-07-31 | On track
|  |  | 6. Improve referral pathway for SACT patients by developing and rolling out a standardised referral form and supporting Christie roll out of e-referral system | Anne Armstrong/ Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2025-06-30 | Complete
|  |  | 7. Define clinic templates for all oncology clinics | Anne Armstrong/ Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2025-06-30 | On track
|  |  | 8. Support development of specific drug clinics e.g. HER2 | Anne Armstrong/ Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
|  |  | 9. Support delivery of PABC project | Anne Armstrong/ Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
| Ensure guidance for Paediatric referrals is up to date and available across GM. | NA | Review and update Paediatric guidelines | Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2025-06-30 | On track
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Share pathway specific Personalised Care performance data report with PWB - HNA, PCSP and EOTS - by Trust | NA | Share quarterly reports with Trust leads and Nursing and AHP Forum | Claire Liu/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
| Collate feedback from Nursing and AHP teams and patients on implementation of PSFU | NA | Develop and agree parameters of qualitative review of PSFU for breast cancer thought Nursing and AHP Forum | Claire Liu/ Claire Goldrick/ Andrea Webber | 2025-04-01 | 2025-07-31 | On track
| Develop patient information leaflet for PSFU |  | Design and develop PSFU leaflet | Claire Liu/ Claire Goldrick/ Andrea Webber | 2025-04-01 | 2025-07-31 | On track
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Ensure each project has appropriate PPIE representation and expand small community to provide a more inclusive and diverse Public and Patient Voice |  | PPIE team to lead expansion of breast small community | Naomi Roussak / Rebecca Finley | 2025-04-01 | 2026-03-31 | On track
Research
| Engage with research strategy to improve equity of access to clinical trials for patients diagnosed with breast cancer | NA | Engage with research clinical lead and wider GM breast research leads to discuss how to improve equity of access to research for patients across the region | Anne Armstrong/ Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
| Supporting the GM Cancer Alliance CARE project to improve access to clinical trials | NA | Provide any necessary clinical oversight and share learning through pathway board. Support wider engagement and communications through cancer alliance and supporting sustainability of community connections built during project | Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
Workforce and Education incl. ACCEND
| Continuation of NHS England funded project to evaluate GPs with Extended Role in breast cancer | NA | 1. Support GPCR programme within oncology by developing15 bespoke educational videos to support induction | Claire Goldrick | 2025-04-01 | 2025-05-30 | Complete
|  |  | 2. Complete evaluation, including operational feedback, job satisfaction through data collection and surveys | Clare Garnsey/ Claire Goldrick | 2025-04-01 | 2025-06-30 | On track
| Priority 5: Continue project to support Advanced Practice in Radiology by developing standards and an education framework to improve variation across GM. | NA | 1. Develop a roles and responsibilities framework for breast Advanced Practice | Clare Garnsey/ Claire Goldrick/ Claire Clarkson | 2025-04-01 | 2025-06-30 | On track
|  |  | 2. Map alignment of providers with framework and identify opportunities to reduce variation | Clare Garnsey/ Claire Goldrick/ Claire Clarkson/ Kerry Porter | 2025-09-01 | 2026-03-31 | Not started
|  |  | 3. Map education available to support standards including specific CPD resources relating to leadership and research - Ensure inclusion of cancer specific CPD, advanced communication skills and providing adequate psychological support to patients throughout the whole cancer pathway - Breast specific CPD to support knowledge and understanding of multi-disciplinary breast disease management | Clare Garnsey/ Claire Goldrick/ Claire Clarkson | 2025-04-01 | 2025-09-30 | On track
| Deliver GM system level education event for Breast Cancer | NA | Deliver education day on 5th June | Claire Goldrick/ Tilly Hewitt | 2025-04-01 | 2025-06-05 | Complete
| Continue to develop Nursing and AHP Forum for breast cancer to support engagement, personal development and service improvement | NA | Host quarterly meetings for all Nursing and AHP colleagues in GM - Gather feedback from forum to improve and sustain Forum | Claire Liu/ Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
| Improve relationship with operational colleagues across Greater Manchester supporting breast cancer services | NA | Organise 6 monthly meetings to provide feedback on work programme and discuss service pressures and development | Claire Goldrick | 2025-04-01 | 2026-03-31 | On track
| Continue to promote the breast ACCEND framework with Nursing and AHP Forum and Pathway Board. | NA | ACCEND framework promoted with Nursing and AHP Forum and Pathway Board | Claire Goldrick/ Claire Clarkson | 2025-04-01 | 2026-03-31 | On track
Status:

## Gynae
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 16/07/25
GM Cancer Pathway Board: Gynaecology |  |  | Clinical Lead: Nadia Ali-Ross |  | Pathway Manager: Louise Farnworth/Jennie Roche
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Cervical Cancer Awareness Campaign |  | Delivery of awareness campaign. Increase proportion of referrals from specific GP practices Qualitative evaluation on symptom knowledge and understanding risks | Nadia Ali Ross Louise Farnworth | 2025-04-01 | 2026-03-31 | Not started
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice |  | Review of form and pass to GM Cancer ED team for upload onto GM systems | Nadia Ali Ross | 2025-04-01 | 2026-03-31 | Not started
| Continue to engage and support the screening and immunisation team |  | Continue to attend programme meetings, GM Cancer Alliance and screening team meetings regularly to share priorities, best practice and share information on current work programmes to address workforce and capacity issues jointly | Nadia Ali Ross | 2025-04-01 | 2026-03-31 | On track
| Priority 1: Focus on IOTA training for Ovarian Cancers. Roll out project for primary and secondary care |  | IOTA scan training plan agreed as pathway board. IOTA training provided for appropriate clinicians with clear outcomes and impact on pathway | Helena O'Flynn | 2025-04-01 | 2026-03-31 | On track
| Self-referral for PMB in 2 localities in GM (NCA as provider) To scope and potentially implement a self referral system for post menopausal bleeding. NCA will be the secondary care provider. Development costs most likely required for the development of a self-access portal to support patient access |  | Plan to launch pilot in Q1, project milestones will be evaluating how many patients self-refer into the pathway. We will also monitor data on how many patients are diagnosed, and how many days this saved in the patients overall pathway | Helena O'Flynn Caitlin Hudson | 2025-04-01 | 2026-03-31 | On track
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
| Priority 2 Diagnostic Bundle - To develop a diagnostic bundle to streamline and provide guidance on diagnostic requests |  | 1) Creation of the diagnostic bundle | Nadia Ali Ross Clare Jordan | 2025-04-01 | 2026-03-31 | On track
|  |  | 2) Publication of the diagnostic bundle | Nadia Ali Ross Clare Jordan | 2025-04-01 | 2026-03-31 | Not started
|  |  | 3) Implementation of the diagnostic bundles | Nadia Ali Ross Clare Jordan | 2025-04-01 | 2026-03-31 | Not started
| Single Queue Diagnostics To explore the development and implementation of the use of single queue Hysteroscopy and Biopsy across Greater Manchester for Gynaecology patients |  | Scoping work to be undertaken for feasibility | Nadia Ali Ross | 2025-04-01 | 2026-03-31 | Not started
| Roll out of ovarian one stop clinic-Following successful pilot, roll out across GM |  | Scoping work to be undertaken for feasibility | James Benson | 2025-04-01 | 2026-03-31 | Not started
| PDL1 testing of Cervical Cancers |  | Rollout PDL1 testing for cervical cancers. Currently being outsourced outside region. To assess feasibility on in house or regional testing | Nadia Ali-Ross | 2025-04-01 | 2026-03-31 | On track
| Treatment Variation - To reduce the number of patients with Gynaecological cancers waiting more than 62 days from referral to curative treatment |  | Triaging, improvement of minimum dataset at point of referral | Nadia Ali-Ross Louise Farnworth James Benson | 2025-04-01 | 2026-03-31 | On track
| Step down policy |  | TBC | Nadia Ali- Ross James Benson | 2025-04-01 | 2026-03-31 | Not started
| Developing equity of access to robotic services across GM |  | 1.develop and implement a regional strategy across Greater Manchester (GM) to ensure equitable access to robotic-assisted clinical services 2. complete baseline equity audit 1to identify and address disparities in patient access | Nadia Ali- Ross James Benson | 2025-04-01 | 2026-03-31 | Not started
National Planning Guidance | Ovarian Cancers- 80% of women with stage 2 to 4, or unstaged ovarian cancer receiving treatment (any type) |  | 1. Validate Current Performance – Check each trust or local data to establish where each trust stand 2.Agree on Interventions – Especially where treatment uptake is below 80% 3. Report Routinely – Present Quarterly data at Pathway Board 4.Share & Improve – Compare with other regions, exchange best practices, and drive continuous improvement | Nadia Ali-Ross James Benson | 2025-04-01 | 2026-03-31 | On track
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries |  | New Treatment Summary templates developed (if required), approved at Pathway Board and disseminated through appropriate Trust forums. Updates by exception provided by PC team around low utilisation | Andrea Webber | 2025-04-01 | 2026-03-31 | On track
| Support development of digital Health and Wellbeing animation - for sexual support during and after treatment. |  | Health and Wellbeing animation video produced for sexual support during and after treatment. Resources promoted by Pathway Board and used widely across GM | Andrea Webber | 2025-04-01 | 2026-03-31 | On track
| Share pathway specific Personalised Care performance data report with PWB - HNA, PCSP and EOTS - by Trust. |  | Personalised Care information shared with Pathway Board, CNS leads agenda on CNS working group. PWB to facilitate discussion if required and issue to be addressed | Andrea Webber | 2025-04-01 | 2026-03-31 | On track
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Ensure appropriate PPIE representation for all board work programmes |  | Projects have a PPIE representative on the task and finish group where appropriate | Rebecca Finlay Louise Farnworth | 2025-04-01 | 2026-03-31 | On track
|  |  | Successful recruitment of further PPIE representation | Rebecca Finlay | 2025-04-01 | 2026-03-31 | On track
Research
| Feasibility assessment of a longitudinal study on the use of a progestogen intrauterine coil for endometrial protection in obese women, within the context of contraception and HRT, with potential integration into the Women’s Hub model |  | Complete a feasibility study assessing the clinical and practical viability of a longitudinal study on the progestogen intrauterine coil for endometrial protection in obese women, ensuring alignment with the Women’s Hub model where applicable | Emma Crosbie | 2025-04-01 | 2026-03-31 | Not started
Workforce and Education incl. ACCEND
| Primary Care Webpage - To develop a webpage within the GM Cancer website under Gynaecology PWB specifically for primary care workstreams. To provide easy access to all documents and educational offerings to primary care in one location |  | For all Primary Care colleagues to have access to a range of education topics to support Early Diagnosis. For this education to be widely promoted and accessed within PCNs | Jack Quinn | 2025-04-01 | 2026-03-31 | Not started
| Education Event - To host an education event for all Gynaecological Cancers for both primary and secondary care colleagues |  | Delivery of the education event Review of survey monkey following event to help guide future events | Jack Quinn Louise Farnworth | 2025-04-01 | 2026-03-31 | Not started
| Priority 3 Education for Care Homes, District Nursing and Carers |  | Development of a Vulva atlas | Cath Holland | 2025-04-01 | 2026-03-31 | On track
Status:

## Colorectal
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 08/04/2025
GM Cancer Pathway Board: Colorectal |  |  | Clinical Leads: Dr Roger Prudham & Mr Chelliah Selvasekar |  | Pathway Manager: Tom Anderton
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - ie by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Continue to work with key partners to support public messaging and engagement to ultimately increase public awareness of cancer symptoms and encourage timely presentation (including screening). |  | Engagement in Bowel Cancer Awareness month (April 2024). Resources shared across Trusts via Pathway Board. Engagement in symptom awareness communications all year round. | Alison Foxley / Mike Armstrong / Tom Anderton | 2025-04-01 | 2025-04-30 | Complete | Complete May 2025
| PRIORITY 1: Clinically support the ongoing implementation of FIT, driving innovations in this to increase FIT uptake and compliance. Examples outlined below of specific deliverables that the Pathway Board will lead to support this statement. |  | Engagement with relevant groups to support all FIT related initiatives requiring Pathway Board input. Pathway Board updates provided via PWB ED Reps (MA/AA/AJ). | Roger Prudham / Chelliah Selvasekar / Tom Anderton | 2025-04-01 | 2026-03-31 | On track | Awaiting further discussion with ED team on the work programme for the Early Diagnosis of Symptomatic Colorectal Cancer T+F Group - expect this to be a feature. Also awaiting update re continuation of funding Clinical Lead for Early Diagnosis of Symptomatic Colorectal Cancer
| SUB-PRIORITY: Clinically lead on the FIT 'Direct to Test' concept. |  | Innovative concept scoped and shared with relevant stakeholders as appropriate for further progression/testing. | Roger Prudham / Tom Anderton / Ali Jones / Mike Armstrong | 2025-04-01 | 2026-03-31 | On track | Following ED Symp TFG, 'Self Referral' FIT pathway is being proposed.
| SUB-PRIORITY: Pursue innovative proposals e.g. This Van Can 2.0 / FIT vending machine / asymptomatic FIT mailshots to target groups. |  | Innovative concepts from 23/24 reviewed and shared with relevant stakeholders as appropriate for further progression/testing. Findings of This Van Can 1.0 reviewed and discussed at Pathway Board to inform This Van Can 2.0 | Roger Prudham / Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| SUB-PRIORITY: Support recruitment of Pharmacy Fellow and provide clinical supervision to successful candidate with a view to defining and mobilising FIT & pharmacy initiative/project. This is working in collaboration with WF & ED Team and other colleagues. Funded by GM Training Hub. |  | Pharmacy fellow recruited. Pharmacy project defined. | Roger Prudham / Jack Quinn / Jess Docksey / Tom Anderton | 2025-04-01 | 2026-03-31 | On track | Funding secured from GM Training Hub 2024/25
| Work with ED Team to deliver GM colorectal education event focused on primary care and locality engagement and awareness (e.g webinar / F2F in person event). |  | Event / webinar(s) focused on primary care and locality engagement and awareness planned and delivered in collaboration with GM stakeholders. | Roger Prudham / Tom Anderton / Ali Jones / Mike Armstrong | 2025-04-01 | 31/09/25 | Delayed progress | PWB Lunch & Learn scheduled for June was stood down due to RP requring leave for a period of 3 weeks. TA currently in dsicussion with PK as we have agreed a 'virtual' session will be recorded instead of a 'Lunch & Learn' with a live audience.
| Review GM secondary care 'no FIT attached' pathway. |  | GM secondary care 'no FIT attached' pathway reviewed by appropriate stakeholders (inc. PWB) and shared for ongoing adoption. | Rachel Mitchell | 2025-04-01 | 2024-04-30 | Complete | Complete June 2025
| Annual review of suspected lower GI referral form with reminder to Pathway Board re: the importance of feeding back evidence of practices failing to comply with the agreed GM referral form. |  | Referral form reviewed and endorsed by PWB and shared with ED Team ready for system upload by December 2025. | Tom Anderton / Sarah Taylor / Mike Armstrong | 2025-04-01 | 2025-12-31 | Not started
| Evidence around menstruation and FIT reviewed with consideration as to whether we need to develop GM guidance around completing the FIT test. |  | Evidence based reviewed and presented to Pathway Board to inform a GM approach. | Sarah Taylor / Roger Prudham | 2025-04-01 | 2026-03-31 | Not started
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
| Engage with SQD Project, providing clinical input to scope out how single queue may potentially assist with the diagnostic waits in particular TAMIS / TEMS / ESD and EMR. |  | Engagement with the project, providing clinical/secondary care guidance and subject-matter expertise as appropriate. Progress updates to be provided at Pathway Boards. | Jenna Lane / Roger Prudham | 2025-04-01 | 2026-03-31 | On track | Awaiting update from Operational Performance team on 25/26 budget and also discussion on colorectal related plans more generally for 25/26
| PRIORITY 2 (a) Continue to design model for regional MDT for colorectal cancer patients with oligometastatic disease affecting the liver, lung, and peritoneum, (b) Strengthen case for change for this new MDT (c) Gain system support to progress to testing proof of concept and identify funding stream (d) Test delivery of this MDT via 6 month project. |  | Model designed and clinically agreed. Case for change drafted outlining benefits of MDT. System support attained and funding source identified. 6 month project to test proof of concept underway. | Tom Anderton / Roger Prudham / Chelliah Selvasekar | 2025-04-01 | 2026-03-31 | On track | Funding required (c.£150k to test proof of concept) - plan to engage pharma industry.
| Paper with guidance drafted to include the evidence in relation to diverticulitis (the management of diverticulitis and risk of cancer). Paper/position statement to be presented to Colorectal PWB. |  | Paper presented to Pathway Board and endorsed. | Roger Prudham | 2025-04-01 | 2026-03-31 | Not started
| Post-appendicitis imaging guidance drafted and presented to Colorectal PWB. |  | Paper presented to Pathway Board and endorsed. | Roger Prudham | 2025-04-01 | 2026-03-31 | Not started
| PRIORITY 3: Development of standardised GM Rectal MRI Radiology Reporting Template. |  | Template developed and ratified by appropriate stakeholders (Pathway Board, Imaging Network, GM Pathology Network, GM Diagnostics Network). | Claire Arthur | 2025-04-01 | 2026-03-31 | Complete
| Address concerns around the handling of MMR results to inform the updated SOP for Lynch testing in GM. |  | GM Lynch Syndrome SOP to be reviewed, refreshed and communciated to Trust Leads and Lynch Champions in GM. Existing education materials also distributed. | Sophie Walker | 2025-04-01 | 2026-03-31 | On track
| PRIORITY 4: Standardised treatment for early rectal cancer - Development of a position statement of appropriate evidence-based treatments for early rectal cancer with standards around assurance such as pathology support, oncology support and a robust data collection strategy. |  | Early Rectal Cancer Steering Group established with appropriate membership reflecting stakeholders involved in ERC. Evidence reviewed. Relevant audits conducted. GM SOP/position statement drafted to guide treatment options for patients. | Chelliah Selvasekar / Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| Non-operative management of rectal cancer guidelines to be updated following audit of outcomes. |  | Guidelines reviewed and refreshed and distributed to the GM Colorectal Pathway Board by late August 2025. | Claire Arthur / Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track
| Review clinical guidelines for Colorectal Cancer: Laparoscopic, Robotic and TaTME Surgery |  | Guidelines reviewed by appropriate stakeholders (inc. PWB) and shared for ongoing adoption. | Chelliah Selvasekar / Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track
| Review guidance for colorectal cancer laparoscopic resection |  | Guidelines reviewed by appropriate stakeholders (inc. PWB) and shared for ongoing adoption. | Chelliah Selvasekar / Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track
| Review position statement from Association of Laparoscopic Surgeons on Robotic Surgery |  | Guidelines reviewed by appropriate stakeholders (inc. PWB) and shared for ongoing adoption. | Chelliah Selvasekar / Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track
| Review guideline on competency in robotic colorectal surgery (2017) |  | Guidelines reviewed by appropriate stakeholders (inc. PWB) and shared for ongoing adoption. | Chelliah Selvasekar | 2025-04-01 | 2026-03-31 | On track
| Review enhanced recovery after surgery (ERAS) guidelines |  | Guidelines reviewed by appropriate stakeholders (inc. PWB) and shared for ongoing adoption. | Chelliah Selvasekar | 2025-04-01 | 2026-03-31 | Not started
| Review and consider the actions, opportunities and recommendations of NBOCA (2021) at a Pathway Board level to inform a regional view. |  | Audit findings presented to PWB. Trusts to review their own findings, identifying and addressing any discrepancies in data. NBOCA 'spotlight' sessions featured on PWB agenda throughout the year with discussion leading to identified actions for improvement. Themes identified for areas of work for 25/26 work programme. | Tom Anderton / Roger Prudham / Chelliah Selvasekar / Mike Braun | 2025-04-01 | 2026-03-31 | Not started
| Review approach to advanced rectal surgery in GM (Management of locally advanced (beyond TME) and recurrent rectal cancer) |  | Approach reviewed. Surgical model endorsed by Pathway Board. | Tom Anderton / Roger Prudham / Chelliah Selvasekar / Ali Jones | 2025-04-01 | 2026-03-31 | On track
| Work with Operational Performance team to pilot AirLogic Audit Tool with audit focused on Stage III colon cancer patients receiving adjuvant chemotherapy following major resection audit. |  | Clinically support template design. Findings shared with Pathway Board. Findings used to inform future audits around pathway optimisation e.g. audit into the acute management of colorectal cancer presenting as emergency in GM. | Roger Prudham . Chelliah Selvasekar / Lisa Galligan-Dawson | 2025-04-01 | 2026-03-31 | On track
| Conduct prospective audit into the acute management of colorectal cancer presenting as emergency in GM, in collaboration with all secondary care providers. |  | 6 month audit complete, data analysed, and report published and shared with Pathway Board with identified actions for improvement. | Chelliah Selvasekar / Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track | Update following clinial leads. Awiaitng system DPIA
| Development of diagnostics bundles for priority cohorts. |  | Diagnostic bundles drafted for four priority cohorts: 1) T3-4 non-metastatic colon cancer 2)Rectal cancer without solid organ metastasis 3)Colon cancer with synchronous metastatic disease 4)Rectal cancer with synchronous distant metastases. To be endorsed by PWB in June. | Clare Jordan / Chelliah Selvasekar | 2025-04-01 | 2026-03-31 | On track | Dependent on support of Project Manager for MDT Reform.
| Drafting of MDT recommendations and Standard Operating Procedure (SOP) to support consistent and effective MDT discussions. |  | SOP drafted and endorsed by Pathway Board (June 2025 meeting). | Clare Jordan / Chelliah Selvasekar | 2025-04-01 | 2026-03-31 | On track | Dependent on support of Project Manager for MDT Reform.
| Address communication issues in colorectal lung metastases pathway. |  | Actions to improve colorectal lung metastases pathway agreed with respective GM PWB Clinical Leads. Actions implemented. Improvements monitored over time and reviewed accordingly. | Tom Anderton / Sarah Sykes / Clare Jordan | 2025-04-01 | 2026-03-31 | On track
| Clinically support/advise on the findings from Operational Performance Team visits to secondary care trusts looking at variation particularly in terms of compliance with triage / STT guidance / FIT negative and CTC. |  | Visits to be conducted by Operational Performance Team. Findings to be reviewed. Mutual actions around improvement initiatives to be agreed by Pathway Board. | Roger Prudham . Chelliah Selvasekar / Lisa Galligan-Dawson / Pavi Brar | 2025-04-01 | 2025-08-31 | Delayed progress | Following a discussion with PB, sites vists have been pushed back by 1-2 months. Expectation is now these will be scheduled from September.
| Support the review of GM Lower GI Triage and Colonic Imaging Guidelines led by Operational Performance Team. |  | Guidelines reviewed by appropriate stakeholders (inc. PWB), updated and shared for ongoing adoption. | Pavi Brar | 2025-04-01 | 2026-03-31 | Not started
| Support the review guidelines for management of colorectal hepatic metastases. |  | Guidelines reviewed by appropriate stakeholders (inc. PWB), updated and shared for ongoing adoption. | Louise Farnworth | 2025-04-01 | 2026-03-31 | Not started
| Support the review of the Greater Manchester locally recurrent rectal cancer (LRRC) referral and treatment pathway. |  | Guidelines reviewed by appropriate stakeholders (inc. PWB), updated and shared for ongoing adoption. | Claire Arthur | 2025-04-01 | 2026-03-31 | Not started
| Colorectal Non Surgical Oncology Guidelines |  | Guidelines reviewed by appropriate stakeholders (inc. PWB), updated and shared for ongoing adoption. | Mike Braun / Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track
| Pathway for short course pre operative patients |  | Guidelines reviewed by appropriate stakeholders (inc. PWB), updated and shared for ongoing adoption. | Claire Arthur / Jaqie Lavelle | 2024-04-01 | 2026-03-31 | On track
| Review the GM Colonic Stenting Guidelines. |  | Guidelines reviewed by appropriate stakeholders (inc. PWB), updated and shared for ongoing adoption. | Roger Prudham / Chelliah Selvasekar | 2025-04-01 | 2026-03-31 | Not started
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | New Treatment Summary templates developed (if required), approved at Pathway Board and disseminated through appropriate Trust forums. Updates by exception provided by PC team around low utilisation. | Tom Anderton / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2025-04-01 | 2026-03-31 | On track
| Develop new treatment summary template for complex colorectal surgery. |  | Template developed, signed off by CNSs and endorsed at Pathway Board. | Tom Anderton / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2025-04-01 | 2026-03-31 | Complete
| Develop new treatment summary template for best supportive care. |  | Template developed, signed off by CNSs and endorsed at Pathway Board. | Tom Anderton / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2025-04-01 | 2026-03-31 | Complete
| Develop new treatment summary template for de-functioning stoma. |  | Template developed, signed off by CNSs and endorsed at Pathway Board. | Tom Anderton / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2025-04-01 | 2026-03-31 | Complete
| Review of existing treatment summary templates (signed off in 2022): -Watch and Wait -Low risk endoscopically removed cancers -Intermediate -TEMS or TAMIS -High Risk |  | Templates reviewed and endorsed by Pathway Board. | Tom Anderton / Amanda Coop / Sarah Sykes / Cheryl Pickup | 2025-04-01 | 2026-03-31 | On track
| Offer clinical advice, input and expertise to Cancer Improvement Collaborative (CIC) project to address the current 'Treatment Summary gap' in the colorectal metastatic pathways. |  | End of treatment summary equivalent developed for all CRC patients diagnosed with a re-occurrence. Patient voice education video developed for all staff to increase staff understanding. Poster with QR code linking to HWB signposting webpage to be placed across GM for all patients to scan. HWB webpage suitable for all patients (with a metastatic section) developed with links to HWB resources. | Andrea Webber / Roger Prudham / Chelliah Selvasekar | 2025-04-01 | 2026-03-31 | On track
| Review existing pathway for patients with heredity polyposis syndrome (FAP) in GM (clinically review existing SOP and understand commissioning arrangements) working with OG and HPB Pathway Board colleagues. |  | Current guidelines to be reviewed and refreshed by OG, HPB, LGI clinicians then ratified at PWB. Guidelines to then be shared widely for onward use. | Roger Prudham / James Britton / Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| Explore communication requirements between FAP MDT and cross-cutting tumour groups (OG / LGI / HPB) |  | Communication requirements outlined and necessary action taken to address any issues. | Roger Prudham / James Britton / Alex Riley | 2025-04-01 | 2026-03-31 | Not started
| Support business as usual reporting of personalised care performance for colorectal. |  | Standard agenda item included on CNS Forum to discuss in depth Personalised Care performance data to identify underperformance and appropriate actions. Issues by exception as identified by CNS group presented to PWB. | Katie Law / Andrea Webber | 2025-04-01 | 2026-03-31 | Not started
| Support Think Well with Cancer Lead to develop MDT referral pathway for specialist psychological MDT input. |  | Think Well psychological lead upskilled in knowledge of the MDT. Referral route for specialist review of cases and input into individual patient pathways to support their treatment plan developed. | Katie Law / Olivia Gunby | 2025-04-01 | 2026-03-31 | On track
| Support creation of a targeted prehabilitation triaging system for all patients diagnosed with cancer, advice and guidance to support these changes and associated educational/comms materials. |  | Clinical expert identified to attend and input into the stakeholder/steering group. Clinician given agenda time at PWB to feedback information and ratify any protocols/policies/materials created as necessary | Katie Law / Michelle Leach | 2025-04-01 | 2026-03-31 | Not started
| Support creation of VBA package including the importance of physical activity, diet and nutrition and smoking cessation. |  | Interested PWB member identified to attend and input into the stakeholder/steering group creating the VBA package. Identified PWB member given agenda time at PWB to feedback information and ratify any protocols/policies/materials created as necessary. | Katie Law / Michelle Leach | 2025-04-01 | 2026-03-31 | Not started
| Support the review of the Colorectal Prehab Pathway for GM. |  | Guidelines reviewed by appropriate stakeholders (inc. PWB) and shared for ongoing adoption. | Michelle Leach and Corie Jackson | 2025-04-01 | 2026-03-31 | On track | Review planned for Oct 25 (if funding for P4c continues - cyclical funding review in October)
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Expansion of small community to provide a more inclusive and diverse Public and Patient Voice. |  | Small community membership expanded. Tenure process in place. | Rebecca Finley | 2025-04-01 | 2026-03-31 | On track
| Development of 'Jargon Buster' for colorectal small community outlining key medical and NHS jargon. |  | Draft produced and reviewed by CNSs. Final version presented to Colorectal Small Community. | Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track
Research
| Offer clinical advice, input and expertise to Macmillan & Roche project to boost recruitment into clinical trials for those currently under-represented. |  | Clinical advice, input and expertise provided to project with Pathway Board updates when appropriate. | Roger Prudham / Claire Goldrick / David Thomson | 2025-04-01 | 2026-03-31 | Not started
Workforce and Education incl. ACCEND
| Continue to monitor impact of educational offerings in 2024/25 to support the implementation of the stepdown policy (Removing Patients from the Suspected Cancer Pathway Post-endoscopy). |  | Metrics regularly reviewed and updated, including: FDS performance for UGI and LGI; nos of cancer excluded for these pathways. | Tom Anderton / Alex Riley | 2025-04-01 | 2026-03-31 | On track
| Development of clinical content for GM Cancer in-house IDA eLearning module via the Academy for secondary care colleagues focusing on suspected cancer IDA. The target audience would be professionals from the following disciplines: general medicine, haematology, NSS, UGI, LGI colleagues. |  | Module clinical content developed. | Roger Prudham / Caitlin Hudson / Claire Clarkson | 2025-04-01 | 2026-03-31 | Not started
| Organisation and enrolment of 3 x 2-day Interpreting Blood Analysis courses for 30 LGI triage nurses/CNSs; 12-15 UGI triage nurses/CNSs; 6 involved in the NSS services. |  | 3 x courses organised with uptake from UGI, LGI and NSS nursing colleagues. | Tom Anderton / Claire Clarkson | 2025-04-01 | 2026-03-31 | On track
Pharmacy Fellow project - listed above under Early Diagnosis and Health Inequalities
| Priority 5: Development of GM Cancer Academy live webinar to support implementation of Standardised GM Rectal MRI Radiology Reporting Template. |  | Webinar content created. Live session delivered and impact evaluated. | Claire Arthur / Tom Anderton / Jess Docksey / Tilly Hewitt | 16/07//2025 | 2026-03-31 | Not started
| Explore workforce education requirements around patients with heredity polyposis syndrome (FAP), particularly for referring teams at front-end of pathway to ensure effective management of these patients through the pathway. This will consider education around the diagnosis of FAP and the understanding of genetic test results |  | Workforce requirements understood and education gaps addressed. | Tom Anderton / Alex Riley / Jess Docksey / Katie Law | 2025-04-01 | 2026-03-31 | Not started | Dependent on capacity within genomics team and WF + Ed team to drive this. Discussions ongoing.
| Develop online in-demand webinar and eLearning online module in collaboration with Cancer Academy to support the implementation of the stepdown policy (Removing Patients from the Suspected Cancer Pathway Post-endoscopy) |  | Webinars designed and delivered collaboratively between GM Cancer Academy and Colorectal PWB | Tom Anderton / Jess Docksey / Claire Clarkson / Alex Riley | 2025-04-01 | 2026-03-31 | On track
| Draft and submit posters for the Greater Manchester Cancer Conference 2025 to showcase work in the Poster Village alongside colleagues from across the region. |  | Poster drafted and submitted for: - colorectal oligometastatic pathway/MDT Contribution to collaborative posters developed by GM Cancer colleagues: - stepdown education (Jess Docksey) - This Van Can (Mike Armstrong) - MDT Reform (Clare Jordan) - SQD Complex Polypectomy (Jenna Lane) - CiC project (Andrea Webber) - Pharmacy Fellow (Jess Docksey/Jack Quinn) | Tom Anderton (and colleagues listed in column D) | 2025-04-01 | 2026-03-31 | On track
| Agree minimum data set around rectal scoping (how to describe a rectal lesion in a standardised way). Develop GM Cancer Academy webinar to support this and include in endoscopy reporting systems for providers. |  | Minimum dataset agreed and endorsed by PWB. Webinar designed and delivered collaboratively between GM Cancer Academy and Colorectal PWB. | Tom Anderton | 2025-04-01 | 2026-03-31 | Not started
Status:

## Head&Neck
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 09/07/2025
GM Cancer Pathway Board: Head and Neck |  |  | Clinical Lead: Tracey Ellis |  | Pathway Manager: Jane Cronin / Jennie Roche
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Develop accurate staging data that is able to provide accurate insights into early diagnosis performance across GM |  | No staging data currently available for Head and Neck patients in GM. Work with Early Diagnosis Team and Business Intelligence Team to develop data that provides accurate insights into performance. | Paul Keeling/ Phil Graham / Jane Cronin / Jennie Roche |  |  | On track
| Increase the number of Head & Neck cancers being diagnosed at earlier stage |  | (1) Working with GM Cancer Communications Programme, provide clinical input to develop resources to provide key messaging to target population on signs and symptoms of head & neck cancer. | Jane Cronin / Tracey Ellis / Caitlin Hudson / Jennie Roche / Phillipa Harper |  |  | On track
|  |  | (2) Communications campaign to be developed with the GM Cancer Communications Programme targeted to key areas of Greater Manchester where there is a higher incidence of Head & Neck Cancer patients. | Jane Cronin / Tracey Ellis / Caitlin Hudson / Jennie Roche / Phillipa Harper |  |  | Not started
|  |  | (3) Primary Care "Lunch & Learn" Webinar to be delivered. | Tracey Ellis / Jane Cronin / Paul Keeling |  |  | On track | Date booked 14/10/2025
| Identify barriers / challenges between primary & secondary care and improve referrals onto a urgent cancer pathway |  | (1) Complete an audit of triaging and advice & guidance at all Trusts across GM with results to be presented to the pathway board. | Jane Cronin / Caitlin Hudson / Jennie Roche |  |  | Not started
|  |  | (2) Deliver an in person workshop for primary & secondary care to review referral audits and quality of referrals with outcomes of workshop to be presented to pathway board for consideration of next steps. | Paul Keeling / Caitlin Hudson / Charles Crawford / Jane Cronin |  |  | Not started
|  |  | (3) Scope what education is required in primary care to improve quality of referrals. | Caitlin Hudson / Paul Keeling / Jane Cronin / Jennie Roche |  |  | Not started
|  |  | (4) Education & engagement event, based on scoping, to be delivered and evaluation to be undertaken and shared with the pathway board. | Paul Keeling / Caitlin Hudson / Charles Crawford / Jane Cronin / Tracey Ellis / Jennie Roche / Jack Quinn |  |  | Not started
|  |  | (5) Utilising learning from "This Van Can" projects, scope how community outreach projects could target groups that experience inequalities and present findings to pathway board. | Caitlin Hudson / Jane Cronin / Jennie Roche |  |  | Not started
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
| Treatment variation - Reduce the number of patients waiting more than 62 days from referral to curative treatment |  | (1) Deep dive audit of 104 day breaches for ENT to be undertaken with results and any key themes or variation to be presented to Pathway Board to consider areas of improvement to reduce breaches. | James Benson / Jane Cronin / Tracey Ellis / Jennie Roche |  |  | On track
|  |  | (2) Deep dive audit of 104 day breaches for Oral Surgery to be undertaken with results and key themes or variation to be presented to Pathway Board to consider areas of improvement to reduce breaches. | James Benson / Jane Cronin / Tracey Ellis / Jennie Roche |  |  | On track
Pathway Board Priority | Digital Cytology Pilot for Head & Neck Fine Needle Aspiration (FNA) Clinics - Pilot |  | (1) Pilot to be conducted at MFT - MRI for delivery of remote adequacy assessment and rapid diagnosis for head & neck ultrasound guided FNA's utilising digital cytology with pilot through one stop clinics. | David Shelton / Noreen Aktar / Guy Betts / Jane Cronin / Jennie Roche / Tracey Ellis | 2025-05-01 | 2025-10-31 | On track
|  |  | (2) Evaluation to be presented at Pathway Board with consideration to roll out across GM and whether this could be replicated for other neck lump tumour sites, e.g.; heamonc. | David Shelton / Noreen Aktar / Guy Betts / Jane Cronin / Jennie Roche / Tracey Ellis | 2025-05-01 | 2025-12-31 | Not started
|  |  | (3) Audit of delivery of FNA's in clinic across Trusts (to include kit / education requirements) with any barriers identified and presented to pathway board to scope requirements for potential wider roll out of Digital Cytology. | Jane Cronin / Jennie Roche / Tracey Ellis |  |  | Not started
|  |  | (4) Audit of FNA adequacy compliance rates for each Trust to be undertaken and presented to pathway board with actions for each Trust to increase adequacy rates to be agreed. | Jane Cronin / Jennie Roche / Tracey Ellis |  |  | Not started
(25/26) Planning Guidance | For each priority pathway, we will establish (or continue) a Cancer Alliance-led Pathway Implementation Group to track progress and support best practice. |  | (1) Cancer Alliances should identify a named Lead for the Head & Neck pathway, who will attend the Pathway Implementation Group to identify further opportunities for pathway improvement | Jennie Roche |  |  | Not started
|  |  | (2) Participate in Head & Neck Pathway Implementation Group to support pathway improvement and community interaction. This may include identifying targeted projects focused on improving performance on the Head & Neck pathway such as: one-stop surgery principles; regularly monitor PTLs and apply response demand/capacity solutions; streamlining links with other specialties such as ENT, MaxFacs depts and pathology. | Jennie Roche |  |  | Not started
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Review existing Treatment Summary templates, creating new templates where they are needed. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | (1) Review of existing Treatment Summary Templates and development of New Treatment Summary templates (if required), approved at Pathway Board. | Andrea Webber / Niki Jones / Jane Cronin / Jennie Roche |  | 2026-03-31 | On track
|  |  | (2) Results of audit of usage of Head & Neck Treatment Summaries to be presented to the Pathway Board by Personalised Care Lead. Pathway Board & Nursing & AHP Forum to support the uptake/increased use of Treatment Summaries across all Trusts. | Andrea Webber / Niki Jones / Jane Cronin / Jennie Roche |  | 2026-03-31 | On track
| Create health and wellbeing dietician content |  | Animation video created and dissemination across appropriate networks. Video accessible to all appropriate patients, carers and family members. | Freya Howle/ Lorna Wilson/ Clare Roberts |  | 2026-03-31 | On track
| Support "Think Well with Cancer" Lead to develop referral pathway for specialist psychological MDT input |  | Provide tumour specific input, as required, to Specialist Psychologist to scope pathway specific referral pathway. | Katie Law / Jennie Roche/ Jane Cronin / Tracey Ellis |  | 2026-03-31 | On track
| H&N - Thyroid - Audit BRAF reflex testing for anaplastic thyroid cancer |  | Re-audit data to be collated and presented to Pathway Board with action plan agreed to address any issues in implementation of pathway changes. | Kate Garcez / Jennie Roche / Jane Cronin Katie Law |  | 2026-03-31 | Not started
| Personalised Care Performance: Head & Neck performance personalised care data to be utilised to improve the usage of Holistic Needs Assessment (HNA), Personalised Care Support Plans (PCSP) and Treatment Summaries (TS) |  | Pathway Board Personalised Care Representative to bring any challenges / best practice or requests to the pathway board for input / discussion, minimum 2 x yearly. | Katie Law / Jennie Roche/ Jane Cronin |  | 2026-03-31 | On track
| Improving and standardising patient information for head & neck patients & carers |  | (1) Audit of current patient information across Greater Manchester to take place. | Niki Jones / Faye Madden / Deborah Ganderton / Jane Cronin / Jennie Roche / Rebecca Finley |  | 2026-03-31 | On track
|  |  | (2) Nursing & AHP Network to review patient information and co-produce with patient & carer representatives, standard GM information. | Niki Jones / Faye Madden / Deborah Ganderton / Jane Cronin / Jennie Roche / Rebecca Finley |  | 2026-03-31 | Not started
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Involve patients / carers in all aspects of the work of the Head & Neck Pathway Board |  | (1) Working with the Cancer Voices Programme, develop succession plan for Patient / carer representatives for the pathway board to ensure that patient / carer views are represented in the work of the board. |  |  |  | Not started
|  |  | (2) Working with the Cancer Voices Programme, develop an action plan to grow the Head & Neck Small Community to ensure that patient / carer views are represented in the work of the board. |  |  |  | Not started
|  |  | (3) Support the Head & Neck Small Community by attendance, as subject matter expert, by Pathway Manager or Clinical (min 1 per year). |  |  |  | Not started
Research
|  |  | Pathway Board research lead to update members of the board on all current research trials that are open to patients in Greater Manchester. |  |  |  | On track
Workforce and Education incl. ACCEND
Planning Guidance | The ACCEND Programme can help with upskilling, recruitment and retention, but requires local implementation supported by experienced nursing and Allied Health Professionals (AHP) workforce leaders in Alliances |  | Support the implementation of ACCEND & E-Portfolio through the Head & Neck Nursing & AHP Forum. ACCEND / E-Portfolio to become a standing agenda item. | Niki Jones / Jack Quinn / Jane Cronin / Jennie Roche |  |  | On track
| Scope an education & engagement event to promote excellent Skin practice across GM & promote the work of the Skin Pathway Board |  | Scoping to be undertaken to understand what education is required in Head & Neck Cancer Services in Secondary Care with a task & finish group to create the agenda based on feedback from previous event held in 2024 & scoping exercise. Education event to be delivered in 2026/27. | Jane Cronin / Tracey Ellis / Jennie Roche |  |  | Not started
|  |  | Education & engagement event for primary care, based on scoping, to be delivered and evaluation to be undertaken and shared with the pathway board. | Paul Keeling / Caitlin Hudson / Charles Crawford / Jane Cronin / Tracey Ellis / Jennie Roche / Jack Quinn |  |  | Not started
| Speech & Language Therapy |  | Pathway Board to support Phase II of the Speech & Language Therapist Workforce Development Programme by providing Clinical input and pathway board oversight, where required. | Jack Quinn / Jane Cronin / Tracey Ellis / Jennie Roche |  |  | On track
Status:

## HPB
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 16/7/25
GM Cancer Pathway Board: Hepato-pancreato-biliary |  |  | Clinical Lead: Joe Geraghty |  | Pathway Manager: Louise Farnworth
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
Awaiting confirmation if this can be supported with cross cutting teams | Public Awareness Campaign for Liver/Pancreatic Cancer - | Yes | Delivery of public awareness campaign. Comms hits. User feedback. To audit referrals 12 months post campaign launch. | Sophie Walker Louise Farnworth Joe Geraghty | 2025-09-01 | 2026-03-30 | Not started
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | Sophie walker | 2025-09-01 | 2026-03-30 | Not started
| Pancreatic Case Finding - Patients at high risk of developing pancreatic cancer - new onset diabetes, unexplained weight loss, aged >60 years |  | Identify patients at risk of pancreatic cancer for diagnostic investigation. | Sophie Walker | 2025-04-01 | 2026-03-30 | On track
| Supporting the EUROPAC study and implementation of high-risk surveillance for hereditary Pancreatic cancer to meet NG85 NICE guidance. |  | Coordinate with EUROPAC navigators to refer 500 patients (nationally) at high risk of hereditary pancreatic cancer into the EUROPAC surveillance programme. Q1 only. | Sophie walker | 2025-04-01 | 2026-03-30 | On track
| Liver Surveillance - support Liver Services to invite >80% of patients with cirrhosis/advanced fibrosis to 6-monthly ultrasound surveillance and support >60% of those invited to attend. Develop a plan to transition the commissioning of liver surveillance services to ICB. |  | Data reporting from all Trusts by end of Q1. Design digital recall system in Q2. Implement digital solution where they don’t already exist Q3. Work with Trusts to develop business case for ICB for 2026/27. | Sophie Walker | 2025-04-01 | 2026-03-30 | On track
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
| Treatment Variation - To reduce the number of patients with HPB cancers waiting more than 62 days from referral to curative treatment. | N/A | 1) To review data broken down by treatment type, referral type and locality. 2) Based on results of the data, to recommend sustainable solutions to improve 62 day performance in those areas highlighted as needing support. 3) Where applicable to focus on areas of deprivation and inequalities. | Millie Wadley Joe Geraghty | 2025-04-01 | 2026-03-30 | On track
?Priority 1 | Priority 1: Single Queue Diagnostics - To support the development and implementation of the use of single queue ERCP across Greater Manchester for HPB patients. | N/A | Development and implementation of single queue diagnostics for ERCP across Greater Manchester. | Millie Wadley Joe Geraghty | 2025-04-01 | 2026-03-30 | On track
?priority 2 | Priority 2: Implementing HPB Best Practice Timed Pathway for suspected HPB cancer as per pathway guidelines. |  | 1. Review current compliance to BPTP through developing key milestone data reflecting the patient pathway in a dashboard. | Millie Wadley Joe Geraghty | 2025-04-01 | 2026-03-30 | On track
|  |  | 2. Following the updated HPB best practice timed pathway with additional information on hepatocellular carcinoma and cholangiocarcinoma following further information from AMMF, Review current pathways and processes to identify opportunities to improve FDS. | Millie Wadley Joe Geraghty | 2025-04-01 | 2026-03-30 | Not started
| GM regional HPB Cancer guidelines. |  | Review and update regional guidelines for management of HPB Cancers. | Joe Geraghty Louise Farnworth | 2025-04-01 | 2026-03-30 | On track
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Genomics/ Germline testing |  | Develop mainstreaming Germline testing pathway for pancreatic cancers to reduce wait for outcome of genetic cancer. | Vicky Foy | 2025-04-01 | 2026-03-30 | Not started
|  |  | Develop GM specific patient information leaflet regarding tests being carried out | Vicky Foy | 2025-04-01 | 2026-03-30 | Not started
|  |  | Re-audit to monitor the impact of 24/25 pathway change. | Vicky Foy | 2025-04-01 | 2026-03-30 | On track
| Talking therapies |  | TBC | Sophie Bates | 2025-04-01 | 2026-03-30 | Not started
| FAP MDT - To improve communications through cross cutting teams for the FAP MDT. | N/A | 1) Review existing pathway for patients with heredity polyposis syndrome (FAP) in GM (clinically review existing SOP and understand commissioning arrangements) 2) Explore communication requirements between FAP MDT and cross-cutting tumour groups (OG / LGI / HPB) 3) Explore workforce education requirements particularly for referring teams at front-end of pathway to ensure effective management of these patients through the pathway. This will consider education around the diagnosis of FAP and the understanding of genetic test results | Alex Riley Rachel Mitchell Louise Farnworth James Britton Roger Prudham Joe Geraghty | 2025-04-01 | 2026-03-30 | Delayed progress
| Review existing Treatment Summary templates, creating new where there are gaps. Board members to support engagement internally within corresponding teams & Trusts with use of Treatment Summaries. |  | New Treatment Summary templates developed (if required), approved at Pathway Board and disseminated through appropriate Trust forums. Updates by exception provided by PC team around low utilisation. | Katie Law Louise Farnworth | 2025-04-01 | 2026-03-30 | On track
| Treatment summaries |  | Complete an audit to determine usage of Treatment summaries | Katie Law Louise Farnworth | 2025-04-01 | 2026-03-30 | On track
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Expansion of small community to provide a more inclusive and diverse Public and Patient Voice. |  | Small community membership expanded. Tenure process in place. | Rebecca Finley | 2025-04-01 | 2026-03-30 | On track
| PPIE engagement and rep for PWB |  | Identify patient carer rep for PWB | Rebecca Finley | 2025-04-01 | 2026-03-30 | On track
Research
Workforce and Education incl. ACCEND
?priority 4 | HPB-Education Event - To host an education event | N/A | Delivery of the education event. Review of survey monkey following event to help guide future events. |  | 2025-04-01 | 2026-03-30 | On track
| Continue to promote the HPB ACCEND framework with CNS Forum and Pathway Board. |  | ACCEND framework promoted with CNS Forum and Pathway Board. |  | 2025-04-01 | 2026-03-30 | On track
| HPB CNS Forum. |  | 1.Facilitate quarterly meetings for CNS forum to include education element and peer support. |  | 2025-04-01 | 2026-03-30 | On track
|  |  | 2. Work with the academy to build and promote e-portfolio for HPB. |  | 2025-04-01 | 2026-03-30 | On track
| Primary Care Webpage - To develop a webpage within the GM Cancer website under HPB PWB specifically for primary care workstreams. To provide easy access to all documents and educational offerings to primary care in one location. | N/A | Webpage go live. |  | 2025-04-01 | 2026-03-30 | On track
Status:

## Haematology
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 04/07/2025
GM Cancer Pathway Board: Haematology |  |  | Clinical Lead: Suzanne Roberts |  | Pathway Manager: Tom Anderton
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | Tom Anderton Suzanne Roberts Dan Clark | 2025-07-01 | 2025-12-31 | Not started
Priority 2 | Myeloma Emergency Presentations - To understand any barriers to early presentation for Myeloma patients. | N/A | 1) To complete a six month audit of all patients diagnosed with Myeloma to understand the barriers to early presentation. 2) Upon completion of analysis, agree any appropriate deliverables to support earlier presentation (i.e. primary care education/public awareness). | Tom Anderton Suzanne Roberts Dan Clark | 2025-04-01 | 2026-03-31 | On track
| Public Awareness Campaign/Community Outreach - To support the alliance's community outreach programme. | N/A | 1) To understand the community awareness requirements. 2) To develop content/update current content to support the generic public awareness campaign/community outreach programme. | Tom Anderton Suzanne Roberts Dan Clark | 2025-04-01 | 2026-03-31 | On track
| Primary Care Education - To support the ongoing delivery of primary care education. | N/A | 1) To co-host a monthly lunch and learn with primary care. 2) To attend a face to face primary care forum and offer educational content. | Craig Jones | 2025-04-01 | 2026-03-31 | On track
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/ clinical audits
Priority 1 | NHL - To reduce the number of patients with high grade NHL waiting more than 62 days. | N/A | 1) To analyse the outcomes of all site reviews to understand best practice and challenges to delivering the Lymphoma cancer pathway. 2) To draft a local best timed pathway to support performance and pathway improvements with the ability to monitor milestones within the Lymphoma pathway. 3) To review data on patients who presented purely on a haematological pathway to understand pathway bottlenecks. | Suzanne Roberts | 2025-04-01 | 2026-03-31 | On track
| Breach Analysis - To conduct a full breach analysis haematology. | N/A | 1) To conduct a full breach analysis of haematological patients with a focus on patients undergoing radiotherapy. 2) To share findings with the pathway board and agree improvements where appropriate. | Pavi Brar | 2025-04-01 | 2026-03-31 | Not started
| USS Core Biopsy - To ensure all services across GM do not have a single point of failure and support increased demand. | N/A | 1) To write an options appraisal to support the development of the USS FNA Service within Haematology offering either additional training to radiographers or a nurse led service. 2) To facilitate training of appropriate staff (whether that be additional radiographers or a nurse led service) to enhance USS FNA capacity. | Suzanne Roberts Pavi Brar | 2025-04-01 | 2026-03-31 | Not started
| Lymphoma CAR-T Pathway - To develop a pathway to support the referral of patients eligible for 2nd line CAR-T to the treating trusts. | N/A | 1) To develop a pathway for the referral process for 2nd line CAR-T Therapy. 2) To develop a crib sheet for eligibility for 2nd line CAR-T. 3) To promote the pathway through education with the academy. | Eleni Tholouli Ahmed Abdulgawad | 2025-04-01 | 2026-03-31 | On track
Priority 3 | SACT Board - To engage a group to support haematological SACT in order to develop GM guidelines and offer GM governance. | N/A | 1) To facilitate an initial meeting to understand the need and engagement. 2) To agree a feasible governance structure to support haematological SACT across GM. 3) To develop a work programme to support reduced variation across GM. | Suzanne Roberts Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| SACT Capacity and Demand - To undertake a capacity and demand audit of haematological SACT across GM. | N/A | 1) Review of current data available to support capacity and demand. 2) Agree structure to undertake capacity and demand audit. 3) Completion of capacity and demand audit. | Pavi Brar | 2025-04-01 | 2026-03-31 | Not started
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LWBC
| Complete the embedding of local accountability arrangements ('local agreements') for personalised care interventions and Personalised Stratified Follow Up (PSFU) pathways, including capabilities in digital tracking of PSFU patients and monitoring the sustained delivery of PSFU and personalised care benefits. | N/A | 1) Support business as usual reporting of personalised care performance by pathway 2) Support auditing the usage of the GM EOTS letter templates 3) Develop EOTS templates for all treatments 4) Endorse the use of infoflex to support delivery of PSFU. | Michelle Leach Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| Deliver co-produced improvement plans and agreements for sustainable commissioning and delivery, demonstrating community/system collaboration, for: a) psychosocial support - continued delivery of pre-existing plans; b) cancer prehabilitation (per NIHR/Macmillan guidance) - complete plan and begin delivery; c) behaviour change and other intervention(s) across the cancer | N/A | 1) Support Think Well with Cancer Lead to develop MDT referral pathway for specialist psychological MDT input. 2) Support creation of a targeted prehabilitation triaging system for all patients diagnosed with cancer, advice and guidance to support these changes and associated educational/comms materials. 3) Support creation of VBA package including the importance of physical activity, diet and nutrition and smoking cessation. 4) Support with the engagement and education of stakeholders by utilising any associated forums to ensure they are sharing and promoting the LWWC locality reports as a standard resource and any other materials produced to increase any form of physical activity/behaviour change | Michelle Leach Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| CLL PSFU - To support the implementation of CLL PSFU. | N/A | 1) To understand the barriers to implementation across all Greater Manchester trusts and support implementation where possible. 2) To ensure all trusts have developed a CLL PSFU SOP and undertaken Infoflex training. 3) To support trusts that are engaged in the implementation of the CLL PSFU Protocol. | Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| MGUS PSFU - To develop an MGUS PSFU Protocol. | N/A | 1) To design an MGUS follow up protocol for all GM providers. 2) To support trusts in the implementation of the MGUS PSFU Protocol. | Suzanne Roberts | 2025-04-01 | 2026-03-31 | Major concerns | Funding required. Will need to look externally for funding. To prioritise the implementation of CLL initially.
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| To support the alliance PPIE recruitment programme. | N/A | To continue to support the alliance PPIE recruitment programme utilising campaign materials where appropriate to support the development of a Haematology Small Community. | Tom Anderton Naomi Roussak | 2025-04-01 | 2026-03-31 | On track
| To develop a jargon buster to support patient and carer representatives coming to meetings. | N/A | Development and ratification of Jargon Buster to support patient and carer representatives. | Jaqie Lavelle Saeed Shakibaie | 2025-04-01 | 2026-03-31 | On track
Research
Workforce and Education
| AML Education Event - To host an education event supporting the delivery of cancer pathways to support patients with AML. | N/A | 1) Delivery of the education event. 2) Review of survey monkey following event to help guide future events. 3) Completion of an evaluation report. | Tom Anderton Eleni Tholouli Molly Pipping | 2025-04-01 | 2026-03-31 | On track
| Nursing Education Event - To host a nursing forum supporting education and engagement with Haem-Onc Pathway Board | N/A | 1) Delivery of nursing forum. 2) Improvement in engagement of nursing forums and pathway boards. | Tom Anderton Jaqie Lavelle | 2025-04-01 | 2026-03-31 | On track
Status:

## Lung
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 14/07/2025
GM Cancer Pathway Board: Lung |  |  | Clinical Lead: Louise Brown |  | Pathway Manager: Jane Cronin
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/26, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Increase knowledge and confidence in primary care - spotting signs & symptoms of lung cancer |  | (1) Review Primary Care Toolkit with links to existing resources available to primary care and share via PCN Newsletter to inform and educate primary care health professionals in early diagnosis of lung cancer. | Jane Cronin / Niki Jones | 2025-04-01 | 2026-03-31 | Complete
|  |  | (2) Develop a dedicated page on GM Cancer Alliance Lung Pathway Board webpage to host Primary Care Resources. | Niki Jones / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
|  |  | (3) Present at a Primary Care Cancer Leads meeting to provide education on the signs and symptoms of lung cancer and increase awareness and referrals of suspected lung cancers across GM. | Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
|  |  | (4) Deliver a primary care education event to increase confidence in primary care in spotting the signs and symptoms of lung cancer in smokers and never smokers, incorporating updates on symptomatic lung programme of work. | Louise Brown / Jane Cronin / Rehan Naseer / Michael Armstrong / Cancer Academy | 2025-09-01 | 2026-03-31 | Not started
Planning Guidance Timely presentations | Deliver campaigns to increase symptom knowledge and encourage earlier presentation, where challenges are at least in part related to/likely to be related to people not seeking help as early as they might |  | Clinical input to be provided by the Pathway Board, as required, to continue with and expand upon the business as usual, public and patient facing communications around signs and symptoms of lung cancer | Rehan Naseer / Michael Armstrong / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
Planning Guidance Primary Care | (1) Improving uptake of automated safety netting systems for patients offered first line cancer tests |  | Scope viability of proactive safety netting after a normal Chest X-Ray with results to be presented to the Lung Early Diagnosis working group and Pathway Board. | Rehan Naseer / Michael Armstrong / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
| (2) Developing Primary Care Network Dashboards to help shape local improvement activity |  | Scope the use of primary care dashboards, to target appropriate interventions to increase referrals of Primary Care requested Chest X-Rays. | Rehan Naseer / Michael Armstrong / Jane Cronin / Louise Brown | 2025-04-01 | 2026-03-31 | On track
| (3) Promoting wider use of Chest X-Rays in general practice to support lung cancer diagnosis, including in low risk but not no risk groups |  | (a) Create a standardised GM wide Non-medical Referrer application process to remove barriers for practice nurses and encourage uptake with a GM wide training package and application form, together with directory of contacts. Regular updates to be presented to pathway board to include number of non-medical referrers and increase in Chest X-Ray's. | Rehan Naseer / Michael Armstrong / Louise Brown / Jane Cronin | 2025-04-01 | 2025-10-30 | On track
|  |  | (b) Scope the development of a Chronic Obstructive Pulmonary Disease (COPD) review tool to be embedded in primary care as part of standard annual COPD reviews to increase Chest X-Ray's. | Rehan Naseer / Michael Armstrong / Louise Brown / Jane Cronin | 2025-04-01 | 2025-12-31 | On track
Planning Guidance Local Innovation | Identify, fund, support, and share learnings from real world implementation and evaluation of new locally developed innovations, or promising innovations from other localities |  | (1) Support with the wider roll out of lung symptom concern digital symptom validation and patient activation tool (Lung Aware v2) across GM, to include 3 additional languages, with regular updates to be presented to Pathway Board and support at Lung Early Diagnosis Working Group. | Rehan Naseer / Michael Armstrong / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
|  |  | (2) Pathway Board to support the development of a toolkit to enable expansion of the Self-referral Chest X-Ray (SRCXR) pilot. Toolkit to be presented to and agreed by the pathway board with support provided to rollout in 4 additional localities in GM (Salford, Manchester, Oldham, Trafford). | Rehan Naseer / Michael Armstrong / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
Pathway Board Priority | Optimise primary care referral pathway |  | Update clinical guidance for GP's for patients with normal CXR's, utilising the new data from AIRPORT Study and educate GP's and radiology on new guidance and new wording for safety netting on CXR reports. | Louise Brown / Rehan Naseer / Sarah Taylor / Mike Armstrong / Jane Cronin | 2025-05-01 | 2025-10-01 | On track
| Review and update of suspected lung cancer referral form (HSC205) in collaboration with commissioning and primary care colleagues |  | Form to be clinically reviewed and ratified by the pathway board by 12/2025. | Jane Cronin | 2025-09-01 | 2025-12-31 | Not started
| Lung Cancer Screening Programme - Expand the Lung Cancer Screening Programme and ensure sufficient diagnostic and treatment service capacity to meet this new demand |  | Ensure that Lung Cancer Screening Programme aligns with Lung Pathway Board deliverables around symptomatic lung pathways by regular updates to the pathway board by the Lung Cancer Screening Programme. | Louise Brown / Oliver Butterworth / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
Planning Guidance | Promote the National Cancer Waiting Times guidance, developing local Access and Inter-Provider Transfer policies across their geographies and providers |  | (1) Curator training "how to / tip sheet" to be developed by Business Intelligence Team and circulated to the Pathway Board Membership. | Philip Graham / Sarah Hulme / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
|  |  | (2) Curator training to be delivered to Pathway Board Trust Representatives / Nursing Leads / Operational Managers to include accessing Curator data, filtering data to Trust level, key reports, how to interpret data and how the data can be utilised to improve performance within Trusts. | Philip Graham / Sarah Hulme / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
Planning Guidance | Develop and deliver an Operational Performance Improvement Plan which will contribute to an improvement in Cancer Waiting Times performance across the three standards: Faster Diagnosis, 31 day Decision to Treat to Treatment and 62 day Urgent Referral to First Treatment Standards Plans should be clearly related to work on Faster Diagnosis pathways where relevant, alongside staging and treatment elements of the pathway and should include a particular focus on lung 62 day pathway performance, including the staging and treatment phases of the pathway |  | (1) Audit to be undertaken of any 62 day breaches where patients have been referred to One Stop Clinic for quarter 4 - 2024. | Matt Evison / Louise Brown / Jane Cronin | 2025-04-01 | 2025-09-30 | Not started
|  |  | (2) Audit to be presented to Pathway Board to identify any key themes (including reflex testing) with results to be circulated to local teams for awareness. | Matt Evison / Louise Brown / Jane Cronin | 2025-04-01 | 2025-12-31 | Not started
Planning Guidance - Treatment Variation & SACT | Implement national priority recommendations from clinical audit/GIRFT reports to reduce variation in treatment in trusts not meeting the NHS-wide target: Lung 70% of patients with NSCLC stage IIIb - IVb and PS 0-1 receiving systemic anti-cancer therapy (SACT) |  | Diagnostic Sub-Group Trust Representatives to feedback on local data accuracy challenges, (issues with good performance patients not being referred for treatment) - what are the local v's regional barriers with the potential to identify future improvement strategies. | Haval Balata / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
|  |  | MDT 4 x Sector Business Meeting to be held to review Thoracic MDT Toolkit and identify any areas of challenge or improvement. | Jane Cronin | 2025-04-01 | 2025-11-30 | On track
Pathway Board Priority | Implement a new "Rapid Small Cell Pathway" in Greater Manchester. Develop a standardised approach for the early identification of cases suspected from their CT scan, progress to biopsy asap (without waiting for other tests such as PET as with other lung cancer cases), agree rapid turnaround of pathological confirmation. Scoping to be undertaken of rapid turnaround of radiological suspicion |  | (1) Develop terms of reference and agree stakeholders for Small Cell Rapid Pathway Working Group. | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin | 2025-04-01 | 2025-05-01 | Complete
|  |  | (2) Undertake base line retrospective audit of small cell patients at each Trust (10 min per Trust) to include: route of presentation and presenting symptoms, timings along the pathway for radiology, pathology and diagnostic testing, treatment decisions, staging, performance score and clinical / radiological suspicion of small cell lung cancer. | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin | 2025-04-01 | 2025-05-01 | Complete
|  |  | (3) Utilising baseline audit agree through the working group what is within scope for the project. | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin | 2025-04-01 | 2025-06-30 | On track
|  |  | (4) Audit pathology turn around times and seek agreement from pathology on which teams can commit to 80% of small cell cases to be reported with IHC within 7 days of biopsy. | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin | 2025-05-01 | 2025-07-31 | On track
|  |  | (5) Consider the use of pre and post biopsy alerts with pathology. | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin | 2025-05-01 | 2025-07-31 | On track
|  |  | (6) Consider education and themes for Respiratory Teams to "Think Small Cell" and deliver a webinar, with the support of the Workforce & Education Programme, to Respiratory Teams across GM. | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin / Matilda Hewitt | 2025-07-01 | 2025-12-31 | Not started
|  |  | (7) Consider education and themes for Acute Oncology to "Think Small Cell". | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin | 2025-07-01 | 2025-12-31 | Not started
| Diagnostics |  | Lung Diagnostic Bundles to be reviewed by Diagnostic Sub-Group ensuring that any new testing, e.g.; ctDNA is included, as appropriate, taking into account impending national guidelines. | Haval Balata / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
| Treatment variation |  | (1) Support the update of the survivorship guidance in the context of maintenance oncology treatment post surgery/radiotherapy by providing clinical oversight. | Louise Brown/ Igor Randulfe / Jane Cronin / Jane Weir / Emma Halkyard | 2025-04-01 | 2026-03-31 | On track
|  |  | (2) Through the Pathway Board, agree timing/when to refer back to local teams and how to ensure local teams are updated in case patient attends acutely at their local trust. | Louise Brown/ Igor Randulfe / Jane Cronin / Jane Weir / Emma Halkyard | 2025-04-01 | 2026-03-31 | Not started
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
Planning Guidance Pathway Board Priority | Deliver Co-produced improvement plans and agreements for sustainable commissioning and delivery, demonstrating community/system collaboration for behaviour change and other intervention(s) across the cancer pathways that support increasing any form of physical activity |  | (1) Phase I - Pilot a specific intervention on empowering healthcare professionals and patients to support the increase of forms of physical activity for those patients who are not enrolled or not eligible for prehab for lung cancer. Pilot to be presented to the pathway board with the aim of wider roll out. | Louise Brown / Harriet Marsland / Lauren Carroll / Jane Cronin / Michelle Leach | 2025-04-01 | 2026-03-31 | On track
|  |  | (2) Phase II - to be co-produced with patient / carer representatives as an accessible resource to be given to patients / utilised in clinics (not necessarily specific to lung). | Louise Brown / Harriet Marsland / Lauren Carroll / Jane Cronin / Michelle Leach / Rebecca Finley | 2025-04-01 | 2026-03-31 | On track
| Patient information & psychosocial Support: Develop patient information |  | Scope the development of a red flag infographic for patients and consider use on treatment summary / part of survivorship. Infographic to be ratified by Pathway Board. | Jane Cronin / Louise Brown / Andrea Webber | 2025-04-01 | 2026-03-31 | Not started
| Genomics: Engage with Personalised Care team to deliver the GM Genomics Project |  | (1) Pathway board to provide support to the Genomics Clinical Lead and Project manager with regular updates to the pathway board and provide support to agree and implement project recommendations by engaging with the Lung pathology teams across Greater Manchester. | Mayuri Basnet / Lisa Heys / Jane Cronin | 2025-04-01 | 2025-09-30 | On track
|  |  | (2) Pathway Board to support the implementation of ctDNA clinical pathway (once added to the Test Registry) as business as usual through presentation and ratification at Diagnostic Sub-Group and Pathway Board, as required. | Jane Cronin / Louise Brown | 2025-04-01 | 2025-10-01 | On track
| Support "Think Well with Cancer" Lead to develop referral pathway for specialist psychological MDT input |  | Provide tumour specific input, as required, to Specialist Psychologist to scope pathway specific referral pathway. | Katie Law / Jennie Roche/ Jane Cronin / Tracey Ellis | 2025-04-01 | 2026-03-31 | Not started
| Personalised Care Performance: Lung performance personalised care data to be utilised to improve the usage of Holistic Needs Assessment (HNA), Personalised Care Support Plans (PCSP) and Treatment Summaries (TS) |  | (1) Results of audit of usage of Lung Treatment Summaries to be presented to the Nurse Led Sub-Group by Personalised Care Lead. Pathway Board & Nurse led sub-group to support the uptake/increased use of Treatment Summaries across all Trusts. | Michelle Leach / Jane Cronin / Emma Halkyard / Jane Weir | 2025-04-01 | 2026-03-31 | Not started
|  |  | (2) Scope development of a support document(s) for patients who will not receive curative treatment and are for best supportive care. To be utilised by diagnostic lung teams. | Andrea Webber / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
|  |  | (3) Scope development of a support document(s) for carers of patients who will not receive curative treatment and are for best supportive care. To be utilised by diagnostic lung teams. | Andrea Webber / Louise Brown / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Involve patients / carers in all aspects of the work of the Skin Pathway Board |  | (1) Working with the Cancer Voices Programme, develop succession plan for Patient / carer representatives for the pathway board to ensure that patient / carer views are represented in the work of the board. | Rebecca Finley / Jane Cronin / Niki Jones | 2025-04-01 | 2026-03-31 | On track
|  |  | (2) Working with the Cancer Voices Programme, develop an action plan to grow the Lung Small Community to ensure that patient / carer views are represented in the work of the board. | Rebecca Finley / Jane Cronin / Niki Jones | 2025-04-01 | 2026-03-31 | On track
|  |  | (3) Support the Lung Small Community by attendance, as subject matter expert, by Pathway Manager or Clinical (min 1 per year). | Jane Cronin / Louise Brown | 2025-04-01 | 2026-03-31 | On track
Research
|  |  | Pathway Board research lead to update members of the board on all current research trials that are open to patients in Greater Manchester. | Igor Randulfe / Phil Crosbie / Ashley Horne / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
|  |  | Scope the implementation of a GM wide Trials Finder for all Lung Trials that are open to recruitment in Greater Manchester. | Igor Randulfe / Phil Crosbie / Ashley Horne / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
Workforce and Education incl. ACCEND
| Consider new workforce models to improve the turnaround times in lung genomics |  | Support the pilot of a new workforce model for a genomic co-ordinator at NCA - Salford. Evaluation of pilot to be presented at the Lung Pathology Group. | Mayuri Basnet / Lisa Heyes / Jane Cronin | 2025-04-01 | 2025-09-30 | On track
| The ACCEND Programme can help with upskilling, recruitment and retention, but requires local implementation supported by experienced nursing and Allied Health Professionals (AHP) workforce leaders in Alliances |  | Support the implementation of ACCEND & E-Portfolio through the Lung Nurse Led Sub-Group. ACCEND / E-Portfolio to become a standing agenda item. | Jane Weir / Emma Halkyard / Jane Cronin / Claire Clarkson | 2025-04-01 | 2026-03-31 | On track
Pathway Board Priority | Standardised induction for lung Cancer nurses across GM |  | Through the Nurse Led Sub-Group and with the support of the Workforce & Development Programme, develop a standardised induction programme for new Lung Cancer Nurses across GM | Jane Weir / Emma Halkyard / Jane Cronin / Claire Clarkson | 2025-04-01 | 2026-03-31 | On track
|  |  | Deliver a webinar on "Think Small Cell" to Respiratory Teams across GM (as above) | Emma Halkyard / Karen Hodgson / Louise Brown / Jane Cronin / Matilda Hewitt | 2025-07-01 | 2025-12-31 | Not started
| Explore the introduction of new workforce models in the Lung Pathway |  | Consider how the utilisation of GP's with cancer roles in the lung pathway could optimise the pathway for patients. | Jane Cronin / Louise Brown / Jess Docksey | 2025-04-01 | 2026-03-31 | Not started
Status:

## Neuro-oncology
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 16/07/2025
GM Cancer Pathway Board: Neuro-oncology |  |  | Clinical Lead: Prof Catherine McBain |  | Pathway Manager: Tom Anderton
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Suspected Cancer Referral Form: Annual review of referral form to ensure all relevant clinical information captured | NA | Form reviewed and approved by Pathway Board and shared with Early Diagnosis team to be uploaded to Primary Care systems. | Tom Anderton/ Caitlin Hudson | 2025-09-01 | 2025-12-01 | Not started
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
| Review compliance with Faster Diagnosis Standard and 62 Day Treatment Cancer Waiting Time Standards for Brain and CNS tumours | NA | Monitor current compliance to FDS and 62 day Cancer Waiting Time standards. Escalate through meetings with clinical and operational leads if necessary to address barriers. | Tom Anderton | 2025-04-01 | 2026-03-31 | On track
| Priority 1: Review the Low Grade Glioma pathway to identify opportunities to reduce duplication and optimise support for patients | Yes - TBC | Develop and deliver a pilot for a virtual AHP/Nurse led holistic clinic for patients with Low-Grade Glioma in follow-up: - Agree clinic eligibility criteria and develop clinic template for virtual clinic - Operationalise clinic - Clinic to run for 4 months (or approx. 30 patients) - Develop and agree evaluation plan to assess the acceptability and feasibility of the clinic, including patient needs (patient reported outcomes/ patient satisfaction). | Lindsey Suddell/Sara Robson/ Tom Anderton | 2025-09-01 | 2026-03-31 | Not started
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Share pathway specific Personalised Care performance data report with Pathway Board - HNA, PCSP and EOTS - by Trust | NA | Share quarterly reports with Neuro-oncology team for review. | Tom Anderton | 2025-04-01 | 2026-03-31 | Not started
| Priority 2: Understand the provision of neuro-rehabilitation services across Greater Manchester | NA | - Review current neuro-rehabilitation services across Greater Manchester by creating a mapping document with a view to optimising services, including the number of patients accessing the service, in patient and outpatient services, waiting times and inclusion/exclusion criteria. - Develop a 1 page service overview including mapping document to highlight current areas of good practice, variation in access to services and areas for improvement for the ICB - Clinical AHP team to continue to provide bespoke education to community and ED teams - education provided to be mapped. - Share best practice guidance for management of Neuro-oncology patients across Greater Manchester | Lindsay Suddel/ Sara Robson/ Julie Emerson Tom Anderton | 2025-07-01 | 2025-10-31 | Not started
| Priority 3: Understand the provision of support for symptomatic and supportive care for patients across Greater Manchester following a brain or CNS tumour diagnosis | NA | Review the current provision of services for patients of symptomatic and supportive care for patients in GM including numbers of patients, patient need, pathway and services available. Once services are mapped, bring together stakeholders from across GM to discuss how services can be improved. | Catherine McBain/ Tom Anderton | 2025-07-01 | 2025-10-31 | Not started
| Improve Acute Oncology pathway for patients with Brain Metastases | NA | Working with AO pathway board, define optimal pathway for patients with brain metastases (linking to GM metastatic strategy). - Develop pathway document - Identify changes to be implemented - Identify method to monitor changes and identify education needs to sustain changes | Jennifer King/ Claire Barker/ Chantelle Davies Tom Anderton | 2025-06-01 | 2026-03-31 | On track
|  |  | Continue to support the optimisation of the Neuro-oncology MDT: - Share relevant communications across system - Support development and roll out of any relevant education | Jennifer King/ Claire Barker/ Chantelle Davies Tom Anderton | 2025-06-01 | 2026-03-31 | On track
| Improve Acute Oncology pathway for patients with Brain Tumours who are not suitable for neuro-surgery | NA | Working with AO pathway board, define optimal pathway for patients unsuitable for surgery: - Develop pathway document - Identify changes to be implemented - Identify method to monitor changes and identify education needs to sustain changes | Catherine McBain/ Tom Anderton | 2025-09-01 | 2025-12-31 | Not started
| Understand current provision of psychological support for patients with brain tumours | NA | Mapping exercise to understand current tiers of provision across each locality. Following mapping exercise, identify education needs and develop plan to upskill wider cancer workforce. | Catherine McBain/ Tom Anderton | 2025-09-01 | 2025-12-31 | Not started
| Review prehabilitation offers across GM to understand if resources can be applicable to Neuro-oncology patients | NA | Discuss provision with Personalised Care team to understand if prehabilitation can be offered to Neuro-oncology patients. | Lindsey Suddel/ Tom Anderton | 2025-09-01 | 2025-12-31 | Not started
| Improve the pathway for speech and language therapy for patients in Greater Manchester | NA | - Develop and share patient information leaflet. - Review appropriate screening tool to assess high level cognitive communication needs throughout the pathway. - Review findings from Training Needs Analysis to understand education needs and develop education plan. | Julie Emerson/ Tom Anderton | 2025-04-01 | 2025-10-31 | Delayed progress
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Priority 4: Re-establish the Neuro-oncology small community, ensuring appropriate PPIE representation by providing a more inclusive and diverse Public and Patient Voice. | NA | PPIE team to lead development of Neuro-oncology small community. | Naomi Roussak / Rebecca Finley/ Tom Anderton | 2025-04-01 | 2025-09-30 | On track
Research
Workforce and Education incl. ACCEND
| Develop continence guidance and education to improve timely support for patients with brain and CNS tumours | NA | Ratify content for continence module and develop any further education or documentation necessary to upskill workforce. | Catherine McBain/ Tom Anderton | 2025-04-01 | 2025-07-31 | Delayed progress
| Review of available education for Primary and Secondary Care and community colleagues on referrals and symptom management for patients with brain and CNS tumours | NA | - Undertake a review of available education on GatewayC, Tessa Jowell and various other platforms on headaches, seizures and steroid management. - Ensure education is easily accessible on GM Cancer website. - To further identify additional education that would further support the pathway for patients including improving referrals to Secondary Care, steroid management and patients not suitable for further treatment and agree development plan. | AHP/Nursing team/ Tom Anderton | 2025-06-01 | 2025-08-21 | Not started
| Develop educational webinar to support Primary and Secondary Care and community colleagues on referrals and symptom management for patients with brain and CNS tumours | NA | Webinars designed and delivered collaboratively between GM Cancer Academy and Colorectal PWB. | AHP/Nursing team/ Tom Anderton / Claire Clarkson | 2025-06-01 | 2026-03-31 | Not started
Status:

## Skin
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 14/07/2025
GM Cancer Pathway Board: Skin |  |  | Clinical Lead: Stephanie Ogden |  | Pathway Manager: Jane Cronin
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - ie by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Deliver a "Sun Awareness Week" Campaign (12th May to 18th May 2025) |  | Working with GM Cancer Communications Programme, provide key messaging to target population to deliver a Sun Awareness Week utilising "Sun Smart" Resources to be shared across the system. | Jane Cronin / Phillipa Harper | 2025-04-01 | 2025-05-20 | Complete
Pathway Board priority | Raise public awareness of signs & symptoms of skin cancer including sun safety and skin cancer prevention |  | Working with GM Cancer Comms Team, pilot a "grass roots sports" prevention and awareness of signs and symptoms campaign by providing bespoke social media packs to grass root sports clubs across Greater Manchester. | Jane Cronin / Phillipa Harper | 2025-04-01 | 2025-08-30 | On track
| Roll out a Sun Awareness Accredited Programme in GM Schools utilising a national SKCIN Accreditation Programme |  | Building on the work done in 2023/24 - Case Study to be shared with 0-19 Commissioners & Early Years Commissioners to increase the uptake of the sun safe accreditation in early years and key stage I & II in Greater Manchester. | Jane Cronin / Stephanie Ogden | 2025-04-01 | 2025-05-01 | Complete
| Review and update of suspected skin cancer referral form (HSC205) in collaboration with commissioning and primary care colleagues |  | Form to be clinically reviewed and ratified by the pathway board by 12/25 taking into account the Dermatology Single Point of Access skin cancer referral template. | Jane Cronin | 2025-09-01 | 2025-12-31 | Not started
| Develop robust plans to review and improve referral practice in primary care |  | (1) Working with the GM Dermatology Programme to improve the quality of Suspected Cancer Referrals in primary care by providing clinical input and review feedback to support adaptation and continued improvement of the interactive referral template. | Jane Cronin / Stephanie Ogden | 2025-04-01 | 2026-03-31 | On track
Pathway Board priority |  |  | (2) Scope what data is available to understand where highest referring PCN's / GP Practices are and compare against conversion rates / referral quality. | Jane Cronin / Stephanie Ogden / Paul Keeling / Eejay Whitehead | 2025-04-01 | 2025-09-30 | Not started
|  |  | (3) Skin Clinical Lead to present at a Primary Care Network Cancer Lead Meeting on benign and non-benign skin leasions to embed existing primary care education. | Stephanie Ogden / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
|  |  | (4) Primary Care "Lunch & Learn" Webinar to be delivered. | Jane Cronin / Stephanie Ogden / Paul Keeling | 2025-09-01 | 2026-03-31 | Not started
|  |  | (6) Provide education to primary care by reviewing information on skin cancer through Gateway C and GM Academy and updating, if required. | Stephanie Ogden / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
Skin National Priority Pathway Planning Guidance | Overcoming seasonality to support more consistent performance across the year, including a continued focus on skin performance in providers where FDS skin performance was below 75% within individual providers in 2024/25 (from April to September 2024) |  | (1) Through the pathway board membership, scope what mitigations are in place for increase in seasonal referrals and share with pathway board. | Jane Cronin / Stephanie Ogden | 2025-04-01 | 2025-06-30 | Not started
|  |  | (2) Working with the GM Comms Team, develop a communications strategy for a winter "signs & symptoms" public comms campaign, using data to target high risk groups. Comms campaign evaluation to be presented at pathway board. | Jane Cronin / Stephanie Ogden / Phillipa Harper | 2025-04-01 | 2026-03-31 | Not started
| GM Dermatology Programme |  | Working alongside the GM Dermatology Programme, provide clinical input and pathway board oversight to cancer activity, including implementation of Dermatology Model of care which includes; review of single point of access / dynamic referral template in primary care and roll out of community dermatology. | Stephanie Ogden / Jane Cronin | 2025-04-01 | 2026-03-31 | On track
Planning Guidance | Promote the National Cancer Waiting Times guidance, developing local Access and Inter-Provider Transfer policies across their geographies and providers |  | (1) Curator training "how to / tip sheet" to be developed by Business Intelligence Team and circulated to the Pathway Board Membership. | Philip Graham / Sarah Hulme / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
|  |  | (2) Curator training to be delivered to Pathway Board Trust Representatives / Nursing Leads & Operational Managers to include accessing Curator data, filtering data to Trust level, key reports, how to interpret data and how the data can be utilised to improve performance within Trusts. | Philip Graham / Sarah Hulme / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
Planning Guidance | Reducing the FDS gap between those who have cancer ruled out and those who are diagnosed with cancer will be a new focus for 25/26 |  | (1) Audit Urgent Cancer Referral step down letters in use across Greater Manchester. | Stephanie Ogden / Jane Cronin | 2025-05-01 | 2025-08-30 | Not started
|  |  | (2) Develop standardised Greater Manchester Urgent Cancer Referral step down letter to be presented to and ratified by the Pathway Board. | Stephanie Ogden / Jane Cronin | 2025-07-01 | 2025-09-30 | Not started
Planning Guidance Pathway Board Priority | Complete the rollout of teledermatology to over 50% of USC referrals in all applicable services. Optimise teledermatology pathways to achieve benefits realisation and ensure services have BAU funding mechanisms in place by Q2 |  | (1) Clinical input and system wide support to be provided by the pathway board in the mobilisation of the teledermatology pilots in Greater Manchester. | Kerry Porter / Jane Cronin / Stephanie Ogden | 2025-05-01 | 2026-03-31 | On track
|  |  | (2) Significant updates on the teledermatology pilots to be presented to the pathway board to provide shared learning and clinical input. Teledermatology highlight report to be a standing agenda item at the pathway board. | Kerry Porter / Jane Cronin / Stephanie Ogden | 2025-05-01 | 2026-03-31 | On track
|  |  | (3) Evaluation of the GM teledermatology pilots to be brought to the Skin Pathway Board with a GM wide single platform for teledermatology to be explored. | Kerry Porter / Jane Cronin / Stephanie Ogden | 2025-04-01 | 2026-03-31 | On track
|  |  | (4) Review of inclusion / exclusion criteria for Greater Manchester to be undertaken and agreed through the Pathway board. | Kerry Porter / Jane Cronin / Stephanie Ogden | 2025-04-01 | 2025-09-30 | Not started
|  |  | (5a) Data to be gathered across GM on Consultant image review before face 2 face appointment v's straight to face 2 face appointment and presented to Pathway Board. | Kerry Porter / Jane Cronin / Stephanie Ogden | 2025-05-01 | 2025-12-31 | Not started
|  |  | (5b) Data on Consultant image review to be utilised to agree best practice to optimise capacity through Pathway Board and agreed as a GM standard. | Kerry Porter / Jane Cronin / Stephanie Ogden | 2025-05-01 | 2025-12-31 | Not started
Planning Guidance | Expand opportunities for one-stop surgery on the skin pathway to improve dermatologist capacity |  | Scope current One-Stop Clinics and capacity across GM with results to be presented at Pathway Board. | Kerry Porter / Jane Cronin / Stephanie Ogden | 2028-05-01 | 2025-08-30 | Not started
| Roll out the MDT streamlining guidance |  | Working with the MDT Project Manager, provide clinical input and pathway board oversight into review of order of SSMDT list, grouping patients i.e. melanoma, SCC etc. Hold an MDT Workshop and develop and implement SOC pathways. | Clare Jordan / Patricio Serra / Jane Cronin | 2025-04-01 | 2025-09-30 | On track
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Genomics: Engage with Personalised Care team to deliver the GM Genomics Project. |  | Pathway board to provide support to the Genomics Clinical Lead and Project manager with regular updates to the pathway board and support to agree and implement project recommendations by engaging with the skin pathology teams across Greater Manchester, including outsourcing. | Lynne Jamieson / Katie Law / Jane Cronin | 2025-04-01 | 2025-09-30 | On track
| Genomics: Melanoma - reaudit to monitor impact of pathway change implemented in 24/25 |  | Re-audit data to be collated and presented to pathway board with action plan to address issues in implementation of pathway changes. | Lynne Jamieson / Katie Law / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
| Support "Think Well with Cancer" Lead to develop referral pathway for specialist psychological MDT input |  | Provide tumour specific input, as required, to specialist phychologist to scope pathway specific referal pathway. | Lynne Jamieson / Katie Law / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
| Personalised Care |  | Results of audit of usage of Skin Treatment Summaries to be presented to the Pathway Board by Personalised Care Representative. Pathway Board & Nursing & AHP Forum to support the uptake/increased use of Treatment Summaries across all Trusts. | Andrea Webber / Katie Law / Jane Cronin | 2025-04-01 | 2026-03-31 | Not started
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Involve patients / carers in all aspects of the work of the Skin Pathway Board |  | (1) Working with the Cancer Voices Programme, develop succession plan for Patient / carer representatives for the pathway board to ensure that patient / carer views are represented in the work of the board. |  | 2025-04-01 | 2026-03-31 | Not started
|  |  | (2) Working with the Cancer Voices Programme, develop an action plan to grow the Skin Small Community to ensure that patient / carer views are represented in the work of the board. |  | 2025-04-01 | 2026-03-31 | Not started
|  |  | (3) Support the Skin Small Community by attendance, as subject matter expert, by Pathway Manager or Clinical Lead (min 1 per year). |  | 2025-04-01 | 2026-03-31 | Not started
Research
|  |  | Pathway Board Research Lead to update members of the board on all current research trials that are open to patients and how to access them in Greater Manchester by standing agenda item at Pathway Board. |  | 2025-04-01 | 2026-03-31 | Not started
Workforce and Education incl. ACCEND
| Deliver an education & engagement event to promote excellent Skin practice across GM & promote the work of the Skin Pathway Board |  | (1) Scoping to be undertaken to understand what education is required in Skin Cancer Services in Secondary Care with a task & finish group to create the agenda based on feedback from previous event held in 2024 & scoping exercise. | Jane Cronin / Matilda Hewitt | 2025-04-01 | 2025-04-30 | Complete
|  |  | (2) Education & engagement event to be delivered and evaluation to be undertaken and shared with the pathway board. | Jane Cronin / Matilda Hewitt | 2025-04-01 | 2025-09-30 | On track
Planning Guidance | The ACCEND Programme can help with upskilling, recruitment and retention, but requires local implementation supported by experienced nursing and Allied Health Professionals (AHP) workforce leaders in Alliances |  | Support the implementation of ACCEND & E-Porfolio through the Skin Nursing and AHP Forum. Workshop to be held with feedback on implementation and any barriers. ACCEND / E-Portfolio to become a standing agenda item for the forum. | Clare Clarkson / Jane Cronin | 2025-04-01 | 2025-03-31 | On track
Planning Guidance Pathway Board Priority | Support the development and training for non-medical practitioners in performing skin surgery procedures |  | (1) Scoping exercise to be undertaken to understand the different roles / skills Skin CNS / Nursing Staff currently have (operating / nurse led follow up etc). | Clare Clarkson / Jane Cronin / Stephanie Ogden | 2025-04-01 | 2025-06-30 | Not started
|  |  | (2) Develop a GM Framework, linked to ACCEND, to assist with upskilling non-medical practitioners in performing skin surgery procedures. | Clare Clarkson / Jane Cronin / Stephanie Ogden | 2025-04-01 | 2025-12-31 | Not started
|  |  | (3) Present through the Nurse & AHP Network and Pathway Board to share best practice for nurse led innovations. | Clare Clarkson / Jane Cronin / Stephanie Ogden | 2025-04-01 | 2026-03-31 | Not started
Pathway Board Priority | Explore the introduction of new workforce Models in the Skin Pathway |  | Pilot the use of alternative workforce in the Skin pathway by utilising GP's with Cancer Roles (GPCR) in secondary care. | Jane Cronin / Louise Brown / Jess Docksey | 2025-05-01 | 2026-03-31 | Not started
Status:

## OG
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated: 04/07/2025
GM Cancer Pathway Board: Oesophagogastric |  |  | Clinical Lead: Javed Sultan |  | Pathway Manager: Alex Riley
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - ie by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice. | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | James Britton Sophie Walker | 2025-07-01 | 2025-12-01 | Not started
| Barrett's Guidance - To develop a guidance document to support primary care and pharmacy education on Barrett's oesophagus, supporting patients in primary care and the importance of PPI therapy. | N/A | 1) Development of guidance document. 2) Launch and education on guidance document at Primary Care Forum. | James Britton Sophie Walker | 2025-04-01 | 2026-03-30 | On track
| Dont Ignore The Burn - To continue to support the "always on" campaign for Don’t Ignore The Burn. | N/A | To review staging data and agree whether an additional targeted approach should be considered for localities in the lower percentages. | Alex Riley Sophie Walker | 2025-04-01 | 2026-03-30 | Complete
| Cytosponge in Primary Care - To pilot a Barrett's case finding project in at risk cohorts of patients using the sponge test by delivering a mobile outreach clinic for at risk cohort to be invited to undergo testing. | EIA Completed | Delivery of mobile outreach clinics across Greater Manchester. Local evaluation to review uptake of testing along with percentage of cases found. | James Britton Sophie Walker | 2025-04-01 | 2025-05-31 | On track
| Primary Care Education - To support the ongoing delivery of primary care education. | N/A | 1) To co-host a monthly lunch and learn with primary care. 2) To attend a face to face primary care forum and offer educational content. | James Britton | 2025-04-01 | 2026-03-31 | On track
| Public Awareness Campaign/Community Outreach - To support the alliance's community outreach programme. | N/A | 1) To understand the community awareness requirements. 2) To develop content/update current content to support the generic public awareness campaign/community outreach programme. | Alex Riley James Britton Sophie Walker | 2025-04-01 | 2026-03-31 | On track
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
Priority 1 | One Stop Clinic - To continue the development of the one stop clinic pathway and support implementation of the one stop clinic at NCA for high risk patients to see a multidisciplinary team in one visit to support 62 day performance. | EIA Completed | 1) Launch of the one stop clinic. 2) Improvement in 62 day performance. 3) To complete the evaluation of the implementation of one stop against the key metrics agreed via the Lung One Stop Model. 3) Review financing and sustainability plan for BAU post 12 months implementation. | Alison Kaye Javed Sultan | 2025-04-01 | 2026-03-31 | On track
| MDT Reform - To streamline MDT processes across Greater Manchester. | N/A | 1) To launch the revised OG MDT SOP including the ratified processes and Standards of Care. 2) To continue to monitor the potential to implement local pre-meets. 3) To agree measures to monitor the impact of the reform project. | Chris Grocock Clare Jordan | 2025-04-01 | 2026-03-31 | On track
| To understand the processes to the front end pathway for NCA and MFT to support the implementation of MDT Reform and the one stop clinic. | N/A | 1) To understand current practises for NCA and MFT from referral to MDT. 2) To develop a pathway with clear patient accountability which will support MDT reform and the One Stop Clinic Model. | Alison Kaye | 2025-04-01 | 2026-03-31 | Not started
| DPYD Testing - To implement pathway changes to support DPYD request at MDT to support timely oncology review. | N/A | 1) Understand practises from other tumour groups. 2) Change in practise to requesting the test. 3) Improvement in time to treat for Oncology. | Alex Riley | 2025-04-01 | 2026-03-31 | On track
Priority 3 | Treatment Variation - To reduce the number of patients with OG cancer waiting more than 62 days from referral to curative treatment. | N/A | 1) To review data broken down by treatment type, referral type and locality. 2) Based on results of the data, to recommend sustainable solutions to improve 62 day performance in those areas highlighted as needing support. 3) Where applicable to focus on areas of deprivation and inequalities. | Javed Sultan Jack Thompson | 2025-04-01 | 2026-03-31 | On track
| Radiotherapy Stricture Service - To support the development of the Radiotherapy Stricture Service in line with the Prevention of Future Deaths Order. | N/A | 1) To audit the current service to feedback to the ICB on the pathway implementation from 24/25. 2) To support the Christie in returning to support the hub and spoke model by developing standard protocols and governance structures. 3) To review commissioning of the RT Stricture Service. | James Britton | 2025-04-01 | 2026-03-31 | On track
| High Risk T1a/T1b Surveillance Protocol - To develop a GM standard protocol for the management of patients with High Risk T1a/T1b disease. | N/A | 1) To develop a surveillance protocol suitable for patients across Greater Manchester in line with current research. 2) To complete an audit of patients with High Risk T1a/T1b disease to understand the impact of a surveillance protocol on services. 3) To support implementation of protocol across Greater Manchester | James Britton | 2025-04-01 | 2026-03-31 | Complete
| Subepithelial Lesion SoC - To develop a Supepithelial Lesion SoC to support the diagnostic bundles and reduce variation in practise and diagnostic testing in GM. | N/A | 1) Development of SoC 2) Launch of SoC 3) Education to be provided to support understanding of the pathway. | James Britton | 2025-04-01 | 2026-03-31 | On track
| GNET SoC - To develop a GNET SoC to support the diagnostic bundles and reduce variation in practise and diagnostic testing in GM. | N/A | 1) Development of SoC 2) Launch of SoC 3) Education to be provided to support understanding of the pathway. | James Britton | 2025-04-01 | 2026-03-31 | Complete
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Complete the embedding of local accountability arrangements ('local agreements') for personalised care interventions and Personalised Stratified Follow Up (PSFU) pathways, including capabilities in digital tracking of PSFU patients and monitoring the sustained delivery of PSFU and personalised care benefits. | N/A | 1) Support business as usual reporting of personalised care performance by pathway 2) Support auditing the usage of the GM EOTS letter templates 3) Develop EOTS templates for all treatments 4) Endorse the use of infoflex to support delivery of PSFU. | Katie Law Alex Riley | 2025-04-01 | 2026-03-31 | On track
| Deliver co-produced improvement plans and agreements for sustainable commissioning and delivery, demonstrating community/system collaboration, for: a) psychosocial support - continued delivery of pre-existing plans; b) cancer prehabilitation (per NIHR/Macmillan guidance) - complete plan and begin delivery; c) behaviour change and other intervention(s) across the cancer | N/A | 1) Support Think Well with Cancer Lead to develop MDT referral pathway for specialist psychological MDT input. 2) Support creation of a targeted prehabilitation triaging system for all patients diagnosed with cancer, advice and guidance to support these changes and associated educational/comms materials. 3) Support creation of VBA package including the importance of physical activity, diet and nutrition and smoking cessation. 4) Support with the engagement and education of stakeholders by utilising any associated forums to ensure they are sharing and promoting the LWWC locality reports as a standard resource and any other materials produced to increase any form of physical activity/behaviour change | Katie Law Alex Riley | 2025-04-01 | 2026-03-31 | On track
| FAP MDT - To improve communications through cross cutting teams for the FAP MDT. | N/A | 1) Review existing pathway for patients with heredity polyposis syndrome (FAP) in GM (clinically review existing SOP and understand commissioning arrangements) 2) Explore communication requirements between FAP MDT and cross-cutting tumour groups (OG / LGI / HPB) 3) Explore workforce education requirements particularly for referring teams at front-end of pathway to ensure effective management of these patients through the pathway. This will consider education around the diagnosis of FAP and the understanding of genetic test results | Alex Riley Rachel Mitchell Louise Farnworth James Britton Roger Prudham Joe Geraghty | 2025-04-01 | 2026-03-31 | Delayed progress
| Treatment Summaries - To develop a Barrett's oesophagus treatment summary to support the communication and ongoing management of patients in primary care. | N/A | Development and launch of use of a Barrett's Oesophagus treatment summary. | James Britton | 2025-04-01 | 2026-03-31 | On track
Priority 2 | Barrett's Surveillance Database - To source and implement a database to support the surveillance of Barrett's Oesophagus across Greater Manchester. | N/A | 1) To source funding to develop infoflex design. 2) To agree Surveillance Protocol. 3) Implementation of use of Surveillance Database. | James Britton | 2025-04-01 | 2026-03-31 | Major concerns | Will need to explore funding options to complete work. On hold whilst finance discussions continue
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| Small Communities - To increase the referral rate to the small community for oesophageal cancer patients. | N/A | 1) To continue to reach out to local organisations to promote Greater Manchester Cancer Alliance and the OG Small Community. 2) To consider extending the small community to include patients with Barrett's Oesophagus. | Alex Riley Naomi Roussak | 2025-04-01 | 2026-03-31 | On track
| Barrett's Oesophagus - To review the Barrett's Oesophagus patient information leaflet and support the development of a patient animation explaining the disease. | N/A | 1) To review Barrett's Oesophagus patient leaflet and update where necessary. 2) To develop patient animation. | James Britton Alex Riley Sophie Walker | 2025-04-01 | 2026-03-31 | On track
Research
Workforce and Education incl. ACCEND
| Blocked Feeding Jej Management - To support MMU in the development of a blocked feeding jej module. | N/A | To offer clinical review of module content. | Javed Sultan | 2025-04-01 | 2026-03-31 | Not started
| Endoscopy Education Package - To develop an endoscopy education package to support the delivery of new endoscopy pathways including Dedicated Barrett's Surveillance Programmes, Gastric Polyp Management and Squamous Dysplasia Management. | N/A | Delivery of education event potentially including live endoscopy, webinars and e-learning modules. | James Britton Alex Riley Tilly Hewitt | 2025-04-01 | 2026-03-31 | On track
Status:

## Urology
Greater Manchester Cancer Pathway Board Work Programme 2025.26 |  |  |  | Last updated:04/07/2025
GM Cancer Pathway Board: Urology |  |  | Clinical Lead: Jeremy Oates |  | Pathway Manager: Alex Riley
Link to NHS Long Term Plan/Planning guidance | Deliverable SMART (describes what the PWB is going to deliver), please be specific and include 'innovation' and 'health inequalities' where appropriate | PWB developed EIA (n/a, yes or no) if yes, incl. expected completion date & add to EIA register | Measure SMART (the output/ evidence that the deliverable is completed/the measure for success in year - i.e. by 31/3/25, add a note if this is part of a deliverable spans across financial years). To note if addressing health inequalities, or is innovation | Responsibility - Named lead i.e. a PWB member or other lead | Planned Start Date (in year) | Planned End Date (in year) | Progress (keep in work programme once complete) | Comments/mitigation add only if status is amber or red
Early Diagnosis and Health Inequalities incl. timely presentation, primary care, local innovation and screening
| Suspected Cancer Referral Form - Yearly review of form to ensure meets current best practice | N/A | Review of form and passed to GM Cancer ED team for upload onto GM systems. | Alex Riley Craig Jones Sophie Walker | 2025-07-01 | 2025-12-31 | Not started
| Blood in Pee - To continue to support the "always on" campaign for Blood in Pee | N/A | To review staging data and agree whether an additional targeted approach should be considered for localities in the lower percentages. To utilise material during awareness months. | Alex Riley Craig Jones Sophie Walker | 2025-04-01 | 2026-03-31 | Complete
Priority 1 | Prostate Cancer Case Finding - To utilise the findings of the Brinnington Case Finding Pilot to develop a toolkit for primary care to replicate this project | Yes | 1) Review of Brinnington Case Finding Pilot. 2) Development of toolkit. | Alex Riley Craig Jones Sophie Walker | 2025-04-01 | 2026-03-31 | On track
| Public Awareness Campaign/Community Outreach - To support the alliance's community outreach programme | N/A | 1) To understand the community awareness requirements. 2) To develop content/update current content to support the generic public awareness campaign/community outreach programme. | Alex Riley Craig Jones Sophie Walker | 2025-04-01 | 2026-03-31 | On track
| Primary Care Education - To support the ongoing delivery of primary care education | N/A | 1) To co-host a monthly lunch and learn with primary care. 2) To attend a face to face primary care forum and offer educational content. | Craig Jones | 2025-04-01 | 2026-03-31 | On track
Faster Diagnosis, including BPTP, Operational Improvement, Treatment Variation - GIRFT/SACT/NATCAN/clinical audits
Priority 3 - pending finance but continue planning. | One Stop Clinic - To develop a Pelvic One Stop Clinic model to support sustainable improvements in 62 day and 31 day performance for both Prostate and Bladder patients | Yes | 1) Development of One Stop Clinic model. 2) Implementation of pilot sector. | James Dyer Performance PM TBC | 2025-04-01 | 2026-03-31 | Not started
| Nurse Led LATP Clinics - Embedding and optimising of nurse led LATP clinics across GM | N/A | 1) To complete capacity and demand audit to review what additional resource is required to enable nurse led clinics. 2) To continue to embed nurse led clinics once training has been completed. 3) To support providers on embedding and optimising. | Alex Riley | 2025-04-01 | 2026-03-31 | On track
| Bladder Pathway Improvements - To continue to deliver on the agreed actions from the 24/25 Workshop to improve performance and patient experience within the bladder pathway | N/A | 1) Implementation of the TURBT Prioritisation SOP. 2) Audit of implementation and performance status to ensure equitable. 3) Development of a patient animation to support knowledge and understanding of the Haematuria clinic. | James Dyer Alex Riley | 2025-04-01 | 2025-12-31 | On track
| Daycase Utilisation - To review the use of daycase for Urological procedures and optimise utilisation | N/A | 1) To attend all sites to understand current practises and barriers to the use of daycase. 2) To support optimal utilisation. | Karen Hodgson Millie Wadley | 2025-04-01 | 2026-03-31 | Not started
| LATP SQD - To support the role out of LATP SQD across Greater Manchester | N/A | Following implementation of LATP SQD across the South Sector, evaluation to be developed and consideration given to full role out across all sites in Greater Manchester. | Millie Wadley Paul Cleavland | 2025-04-01 | 2026-03-31 | On track
Priority 2 | MDT Reform - To streamline MDT processes across Greater Manchester | N/A | Deliverables to be confirmed at workshop on 18th March. | Sot Tolofari | 2025-04-01 | 2026-03-31 | On track
| Breach Analysis - To conduct breach analysis for Urology across all GM trusts | N/A | 1) To conduct a breach analysis of each tumour type. 2) To share findings of analysis with pathway board. 3) To agree plans to support improvement in breaches. | Karen Hodgson | 2025-04-01 | 2026-03-31 | On track
| TULA Audit - To conduct a GM wide TULA audit to ensure TULA is being used to its maximum potential and reduce variation of access across GM. | N/A | 1) To undertake an audit of the use of TULA across GM. 2) To ensure equity of access to TULA across all GM sites. | Alex Riley | 2025-04-01 | 2026-03-31 | Not started
| RCC Pathway - To develop a GM Standardised RCC pathway to support access to adjuvant therapies | N/A | 1) To map out RCC Pathway's across GM. 2) To develop a GM standard RCC pathway. 3) To provide education on the pathway and the need for timely referrals for adjuvant therapy. 4) To launch the pathway at the education event in June 2025. | Alex Riley Sot Tolofari Tom Waddell | 2025-04-01 | 2025-06-30 | On track
| One Stop Haematuria Clinics - To reduce variation of access to one stop haematuria clinics across GM | N/A | 1) To understand the current practise across all providers for haematuria clinics. 2) To support trusts in delivery of one stop haematuria clinics. | Alex Riley Sot Tolofari | 2025-04-01 | 2026-03-31 | Not started
Treatment and Care including: Personalised Care, PSFU, Psychosocial Support, Prehab & Physical activity, Genomics, LW&BC
| Complete the embedding of local accountability arrangements ('local agreements') for personalised care interventions and Personalised Stratified Follow Up (PSFU) pathways, including capabilities in digital tracking of PSFU patients and monitoring the sustained delivery of PSFU and personalised care benefits | N/A | 1) Support business as usual reporting of personalised care performance by pathway 2) Support auditing the usage of the GM EOTS letter templates 3) Develop EOTS templates for all treatments 4) Endorse the use of infoflex to support delivery of PSFU. | Michelle Leach Alex Riley | 2025-04-01 | 2026-03-31 | On track
| Deliver co-produced improvement plans and agreements for sustainable commissioning and delivery, demonstrating community/system collaboration, for: a) psychosocial support - continued delivery of pre-existing plans; b) cancer prehabilitation (per NIHR/Macmillan guidance) - complete plan and begin delivery; c) behaviour change and other intervention(s) across the cancer | N/A | 1) Support Think Well with Cancer Lead to develop MDT referral pathway for specialist psychological MDT input. 2) Support creation of a targeted prehabilitation triaging system for all patients diagnosed with cancer, advice and guidance to support these changes and associated educational/comms materials. 3) Support creation of VBA package including the importance of physical activity, diet and nutrition and smoking cessation. 4) Support with the engagement and education of stakeholders by utilising any associated forums to ensure they are sharing and promoting the LWWC locality reports as a standard resource and any other materials produced to increase any form of physical activity/behaviour change | Michelle Leach Alex Riley | 2025-04-01 | 2026-03-31 | On track
| Personalised Care - To support the role out of the renal PSFU protocol | N/A | Following successful pilot implementation at NCA to role out Renal PSFU Protocol across all GM Sites. | Sot Tolofari Andrea Webber | 2025-04-01 | 2026-03-31 | On track
| Remote PSA Sampling - To pilot the use of the remote PSA sampling kits for prostate surveillance patients | N/A | 1) To expand the pilot of the use of the remote PSA sampling kits across Greater Manchester. 2) To develop a business case to support BAU. | Alex Riley Sot Tolofari | 2025-04-01 | 2026-03-31 | Major concerns | £200k required to move this project forward. Will explore other funding options such as Pharma/Research Grants/Innovation.
Patient and Public Engagement and Involvement, Community Engagement and Experience of Care
| To increase the referral rate to the small community for bladder and renal patients | N/A | 1) To continue to reach out to local organisations to promote the Greater Manchester Cancer Alliance and the Urology Small Community. | Alex Riley Naomi Roussak | 2025-04-01 | 2026-03-31 | On track
Research
Workforce and Education incl. ACCEND
| Urology Education Event - To host an education event to discuss the future of Urological cancer pathways across Greater Manchester | N/A | 1) Delivery of the education event. 2) Review of survey monkey following event to help guide future events. 3) Completion of an evaluation report. | Alex Riley Tilly Hewitt Harry Rudman | 2025-04-01 | 2025-06-30 | Complete | Education event scheduled for Monday 23rd June 2025. Funding via Academy.
| Adjuvant Therapies Webinar - To review the content of the adjuvant therapies webinar and ensure this aligns with the development of the RCC Pathway | N/A | 1) Review of webinar content. 2) Updated webinar if required. | Tom Waddell | 2025-04-01 | 2025-06-30 | On track
Status: