## Risk Register
GM Cancer Alliance Risk Register March 2025
CC= Cross cutting, Wf&Ed = Workforce & Education, FD Opl = Faster Diagnosis & Operations Performance, PC = Personalised Care, C&E = Communications & Engagement
RISK REGISTER
Risk Number | Source | Risk Category | Risk Type | Date risk added | Risk Owner | Risk Description | Inherent Risk Score |  |  | Trend | Risk Proximity | Controls | Gaps in Controls | Current Risk Score |  |  | Actions | Action Owner | Completion Date for actions | Assurances | Gaps in Assurances | Target Risk Score (anticipated score when mitigation complete) |  |  | Functional Area (optional) | Geographical Location (optional) | Last reviewed | Risk Target Date | Open/ Closed | Date and Reasons for Closure
Number to identify risk | The source of the risk (e.g. Manager, Committee, Board meeting etc..) | Alignment to one of 13 risk categories (for GMPMO to complete) | Alignment to one of 3 risk types: 1.Organisation 2.System wide 3. Both | Date when the risk was added to the risk register | Job title of the person responsible for the management, monitoring, control and escalation | A statement describing the risk event, cause and impact | Likelihood | Impact | RAG Status | The trend indicates any change in the current risk score in the form of an arrow | Timescale as to when the risk will occur | Please describe the controls in place to manage/reduce the risk | Please describe any gaps in controls to manage/reduce the risk | Likelihood | Impact | RAG Status | The actions and activities planned to take place that will when implemented or completed reduce, eliminate or minimise the risk | Job title of the person responsible for completing the action | Each action should have a completion date set | Please describe the assurance(s) in place to manage/reduce the risk | Please describe any gaps in the assurance(s) in place to manage/reduce the risk | Likelihood | Impact | RAG Status | A functional area within a regional team or a service area within a directorate | Where the risk is attributed to | Date when the risk was last reviewed and/or updated | Date risk will be mitigated by | Select Current Status of Risk | Reasons outlining why the risk was closed
| FD OpI |  |  | 06.03.23 | GM Cancer Performance Director | There is a risk that If the recovery programme of work is not delivered in line with 23-24 plans, then the cancer alliance and GM system will not deliver the end of March 24 backlog reduction planning requirement |  |  |  | ↔ | 3-6 Mths | Weekly / fortnightly performance meetings with key trusts Targeted intervention and financial support Weekly performance monitoring and standard agenda item at PAG / SSRAG/GM COOs |  | 4 | 5 | 20 | Full work programme developed to support delivery; however it is acknowledged that with competing operational pressures, delivery will be challenging Additional insourced capacity to be arranged and funded through additional tiered trust funding Re-directed funding to support additional activity, additional tiering funded activity commenced Focussed interventions to support year end delivery - including NCA support / SOP provision and weekly tracking and reporting. Concern on potential impact of PET wait times which have deteriorated significantly. Currently under investigation | GM Cancer Performance Director | 31.03.24 | GM Cancer PAG / SSRAG FDS, OP, TV Programme Board GM Cancer Board |  | 3 | 5 | 15 |  |  | 2024-04-23 |  | Closed | Target date for delivery reached. New year has different requirements
| FD OpI |  |  | 2024-03-31 | Director of Performance | If the fragility of the dermatology service is not resolved, there will be a detrimental impact on the operational performance metrics. Skin accounts for 1/3 of the GM backlog, and c70% at the largest provider of dermatology. The volume of patients has the potential to impact the year end delivery for Greater Manchester and England | 4 | 3 | 12 | ↔ | 0-3 months and ongoing | GM Cancer unable to mitigate sustainability risk of the GM dermatology service |  | 5 | 4 | 20 | GM wide work programme under sustainable services. GM lead provider proposal currently being discussed Trust Provider Collaborative / Integrated Care Board GM Cancer - tele-dermatology project, additional funded activity, operational management support to deliver year end position . Increased discussions and work to recover NCA (Northern Care Alliance) position with the Trust, including weekly oversight meetings attended by the cancer alliance Although performance at NCA has improved, this is due to unsustainable additionality. Derm programme to update GM Cancer Board. Derm programme to re-commission IS provider in Oldham following removal of cancer from commissioning specification, and no solution to capacity challenges as a result of the closure of Tameside. | Director of Performance | Cancer Alliance actions complete | Faster Diagnosis Standard, Operational Performance Programme Board, National Tiering calls |  | 4 | 3 | 12 |  |  | 25.02.25 |  | Open
| Wf & Ed |  |  | 2022-06-23 | Programme Director for Workforce and Education | If there is not sufficient workforce capacity in the system then we will not be able to deliver the recovery of cancer services and the long term plan ambitions for cancer. | 5 | 4 | 20 | ↔ | 12+ Mths | Representation at the Greater Manchester (GM) People and Culture System Group to ensure alignment with the GM People and Culture strategic activities, and to allow for risks to be escalated accordingly. Member of the NW Retention and Oversight group which sets the directive for providers regionally. Links made with GM Human Reseource Directors Group to align activity. Updates provided to GM Cancer Workforce and Education Programme Board and GM Cancer Board. Strong links with the regional and national NHSE (NHS England)Cancer and Diagnostics Workforce leads. |  | 4 | 5 | 20 | • GM Cancer workforce and education delivery plan for 25/26 has been aligned to GM People and Culture strategy, NHS Long Term Workforce Plan and GM system programmes •Implementation of ACCEND continues across all providers to support retention of the non medical cancer workforce. Q4 review meetings are taking place this month to discuss progress and plans for 25/26A system-wide board took place in January involving Chief Nurses and Chief AHPs to discuss scale and spread of ACCEND • GM CNS and AHP away day took place to support adoption of ACCEND and improve integration across the two professional groups •Phase 2 of the speech and language therapy workforce project to address inequity in access for head and neck cancer patients will form part of the GM Community Services review - Sustainable services pillar • Cancer academy continues to develop education offers to support the development of the cancer workforce. | Programme Director for Workforce and Education | 2025-03-31 | GM Cancer Workforce and Education Programme Board. GM Cancer Board. GM People and Culture System Group. |  | 4 | 3 | 12 |  |  | 17.3.25 |  | Open
| F/All |  |  | 2023-03-06 | Director of Commissioning & Early Diagnosis | If the Cancer Alliance do not ensure clear exit strategies are in place once Alliance SDF or Targeted funding has expired, the Alliance will put the Greater Manchester system at significant financial risk and risk ongoing delivery of improvement projects implemented by the Alliance | 3 | 5 | 15 | ↔ | 6-9 Mths | Inclusion of all 2024-25 impact included in 2025-26 commissioning intentions and planning process at Integrated Care Board level |  | 4 | 4 | 16 | All Programme Leads to ensure exit strategies in place as part of the 2025-26 planning process Sustainability element to all PAG (Programme Assurance Group) reports now in place | Director of Commissioning & Early Diagnosis | 31.3.25 | Impact of Cancer Alliance projects quantified and included in planning process for 2025-26 DoC&ED member of the GM Commissioning Oversight Group |  | 2 | 2 | 4 |  |  | 2025-02-20 |  | Open
| CC |  |  | 2023-10-03 | Director of Commissioning & Early Diagnosis | IF the Cancer Alliance projects add operational and / or financial pressure to the GM system given the underlying operational and financial challenges THEN the delivery of the NHS Cancer Programme priorities and targets will be affected. This includes ongoing funding of projects to sustain services once the Cancer Alliance funding allocation to providers and partners in NHS GM ends | 5 | 5 | 25 | ↔ | 6-9 Mths | Representation of the Cancer Alliance and their work programmes at DOFs (Directors of Finance), COOs (Chief Operating Officers), TPC (Trust Provider Collaborative) etc Working closely with the system to understand supportive measures that the Cancer Alliance can implement Updates provided at GM Cancer Board Cancer Alliance included in the membership of the NHS GM Commissioning Oversight Group |  | 4 | 4 | 16 | Standing item in all PAG (Programme Assurance Group)reports for visibility and discussion of financial challenges and sustainable funding requirements. Financial tracking of individual budgets ongoing and forecasting exercise completed for 2024-25 Monthly review of Cancer Alliance SDF (Service/Strategic Development Funding) spend through NHS GM finance team | Director of Commissioning & Early Diagnosis | 31.3.25 | SSRAG (strategy and System Risk Assurance Group and PAG (Programme Assurance Group) updates from specific projects and system updates impacting on Cancer Alliance work programme - standing items |  | 3 | 3 | 9 |  |  | 2025-02-20 |  | Open
| FD OpI |  |  | 06.03.23 | GM Cancer Performance Director | If the recovery programme of work is not delivered in line with 23-24 plans, then the cancer alliance and GM system will not deliver the end of March 24 FDS planning requirement |  |  |  | ↔ | 3-6 Mths | Weekly / fortnightly performance meetings with key trusts Targeted intervention and financial support Weekly performance monitoring and standard agenda item at PAG / SSRAG/GM COOs |  | 3 | 5 | 15 | Full work programme developed to support delivery; however it is acknowledged that with competing operational pressures, delivery will be challenging Focussed improvement work has improved the December 23 reportable position but the end of March position is not yet certain and still at risk | GM Cancer Performance Director | 31.03.24 | GM Cancer PAG / SSRAG FDS, OP, TV Programme Board GM Cancer Board |  | 2 | 5 | 10 |  |  | 2024-04-23 |  | closed | Target date for delivery reached. New year has different requirements
| FD OpI |  |  | 21.07.23 | Director of Performance | If there is not an ICB plan to fund the NSS pathway sustainably, then there is a risk to the service being withdrawn in its current delivery, and an impact on the reputation of the cancer alliance |  |  |  | ↔ | 0-3 months and ongoing | Unable to mitigate further at present. Gap in controls is decision outside Cancer Alliance. Completion date is accurate, and now causing significant concern for providers Q1 funding from cancer alliance allocation and Q2 ICB |  | 3 | 4 | 12 | Meeting with DD 14.07.23. Agreement to take business case to ICB National forum attendance regarding sustainability funding. DD also invited Call with national deputy director about national team approach and NSS national evaluation Paper to SSRAG encompassing information from national letter Paper to ICB WC 16.10.23 27.11.23 - Awaiting ICB feedback CA funded Q1. Q2 funded by ICB. No decision about Q3 or 4 Re-escalated to ICB June 24 | Director of Performance | 31.12.23 | Escalated increased risk to June PAG. And ICS via DD 14.07.23 and national team 18.07.23. All SRAGG & PAG meetings GM Cancer Board |  | 3 | 4 | 12 |  |  | 2024-07-22 |  | CLosed | 24/25 funding agreed. 25/26 will form part of the normal contracting meeting
| FD Opl |  |  | 2024-04-24 | Director of Performance | If the improvement plans are not delivered in full, then there is a risk that the interim target of 70% for the 62 day RTT (Referral to Treatment) will not be achieved, which will lead to continual failure of the 62 day constitutional standard | 4 | 4 | 16 | ↔ | 0-3 months and ongoing | Focussed oversight on delivery of all actions Regular meetings with Trusts Highlight report / dashboard monitoring progress to COOs (chief Operating Officres), EMDs (Exective Medical Directors), TPC (Trust Provider Collaboratives), Cancer Board |  | 4 | 4 | 16 | Delivery of the cancer alliance work plan related to FDS and Operational Performance Delivery of the three accelerated improvement initiatives through Trust Provider Collaborative; front end pathway, Single Queue Diagnostics expansion and optimisation, surgical pathway improvement Continuous monitoring of reported performance and local data to predict trends and enable corrective action to be taken National tiering calls for under performing Trusts Targeted investment to support improvement Trust level action plans for improvement and delivery to reduce variation Performance Improvement Plans in place aligned with enforced ICB (Integrated Care Board) undertakings Risk remains elevated due to MFT(Manchester Foundation Trust), delays / inability to enact all plans and forecasted perfromance, and therefore this risks the GM overall position. Director of Performance providing dedicated support 1 day a week commencing January - extended to end March 25. Three times weekly meetings in place with key specialities Weekly forecasting in place | Director of Performance | 2025-03-31 | GM Cancer SSRAG (strategy and System Risk Assurance Group and PAG (Programme Assurance Group) Faster Diagnosis Standard, Operational Performance, Treatment Variation Programme Board GM Cancer Board TPC ICB MFT recovery meeting and regional tier 2 meeting |  | 2 | 4 | 8 |  |  | 25.02.25 |  | Open
| CC |  |  | 2024-11-26 | Director of Commissioning & Early Diagnosis | IF the application of the STAR process and and additional scrutiny / governance to financial transactions by the Greater Manchester ICB is applied to the GM Cancer Alliance funding THEN there is a risk to the timeliness of funding transfers to support Cancer Alliance delivery which could delay project progress. Still awaiting final outcome of 2024-25 SDF | 4 | 4 | 16 | ↔ | 0-3 Mths | Assigned SLT lead to work with NHS GM on this issue and the submission and tracking of STAR forms |  | 4 | 4 | 16 | Director of Commissioning and Early Diagnosis with direct working relationship with Chief Officers for Commissioning and System Improvement in NHS GM to track progress and ensure governance processes are adhered to and flowing | Director of Commissioning & Early Diagnosis | 2025-03-31 | DC&ED leading with Christie finance colleagues and SLT Funding transfer confirmed 16/1/2025 |  | 2 | 2 | 4 |  |  | 2025-02-20 |  | Open
| FD Opl |  |  | 2023-08-29 | Director of Performance | If NICE (National Institute for Clinical Excellence)continue to approve drugs at the current rate then there is likely to be issues in deliverability impacting operational performance of pathways (mainly but not limited to SACT (Systemic anti-cancer therapy) and reflex testing) | 4 | 3 | 12 | ↔ | 6-9 Mths | Not able to mitigate the introduction of NICE (National Institute for Health & Care Excellence) pathways / treatments |  | 4 | 3 | 12 | Horizon scanningscompleted by Cancer Alliance - no new immediate concerns. To be reviewed periodically. NHSE (NHS England) also planning to publish a NICE (National Institure for Health & Care Excellence) roadmap. | Director of Performance | 30.04.24 | Not Applicable - Internal discussion presently |  | 4 | 3 | 12 |  |  | 25.02.25 |  | Open
| FD OpI |  |  | 2024-05-20 | Director of Performance | If the ICB (Integrated Care Board) are not able to provide timely access to the Greater Manchester system support required to deliver Cancer Alliance priorities, then Cancer transformation will be delayed (i.e. specialist Business Intelligence, Information Governance support) | 4 | 3 | 12 | ↔ | 0-3 months and ongoing | Not able to mitigate |  | 4 | 3 | 12 | Prioritisation of requests with ICB (Integrated Care Board) Leads Funding support offered Ongoing dialogue with ICB colleagues | Director of Performance | 30.09.24 | GM Cancer SSRAG (strategy and System Risk Assurance Group and PAG (Programme Assurance Group) Faster Diagnosis Standard, Operational Performance, Treatment Variation Programme Board |  | 4 | 3 | 12 |  |  | 25.02.25 |  | Open
| FD OpI | O |  | 2024-06-24 | Director of Performance | If the Greater Manchester Diagnostic Programme do not deliver expedited transformational improvement, then the Cancer Performance Improvement Plan (and planning targets) can only be delivered through finding additional capacity from WLI (waiting list initiatves) and Insourcing/outsourcing, which will be limited due to finance, workforce availability and meeting critical mass in insourcing/outsourcing | 3 | 3 | 9 | ↔ | 3-6 Mths | Not able to mitigate, as outside of direct control of Cancer Alliance. Will continue to monitor and engage with the team |  | 4 | 3 | 12 | Programme being managed through Diagnostic Programme Board PIP (Performance IM[provement Plans) in place for Diagnostic Programme Interdependency explicit on Cancer PIP Risk explicit on Cancer PIP Cancer Alliance lead for Digital Pathology | Director of Performance | 31.03.25 | SSRAG (strategy and System Risk Assurance Group and PAG (Programme Assurance Group) Performance Improvement Plan (PIP) Oversight through ICB GM Cancer Board - via oversight of PIP |  | 1 | 2 | 2 |  |  | 25.02.25 |  | Open
| CC |  |  | 2023-06-23 | Director of Commissioning & Early Diagnosis | If the wider Greater Manchester system stakeholders are not engaged in and supportive of the design and delivery of the Greater Manchester Cancer Alliance Delivery Plan for 2025-6 then the achievement of the national and Greater Manchester priorities for cancer will be impacted. | 2 | 4 | 8 | ↔ | 6-9 Mths | Representation of the Cancer Alliance and their work programmes at GM Programme Directors meeting, DOFs (Directors of Finance), COOs (Chief Operating Officres), TPC (Trust Provider Collaborative) etc. Cancer Alliance Pathway and Programme Board meetings with wide stakeholder representation from across GM Cancer Alliance Delivery Plan to be presented to and signed off by Cancer Board and via NHS Greater Manchester governance for 2025-6 |  | 4 | 4 | 16 | Maintain the profile of the Cancer Alliance programme within the GM system. Regular Pathway and Programme Board meetings with reports on progress and risk to GM Cancer Assurance Group. Regular progress report to GM Cancer Board, localities/Deputy Place Based Leads and Trust Provider Collaborative. | Director of Commissioning & Early Diagnosis | 31.3.26 | Programme Assurance Group reports and Cancer Board | GM visibility and assurance | 1 | 3 | 3 |  |  | 2025-02-26 |  | Open
| Wf & Ed |  |  | 2023-10-02 | Programme Director for Workforce and Education | If all trusts continue to reduce head count, freeze recruitment / secondment opportunities then this will impact the delivery of all Cancer Alliance programmes, including delivery of the cancer workforce strategy - particularly around growing and developing the workforce to meet the increased demand for cancer services. | 4 | 4 | 16 | ↔ | 3-6 Mths | Representation of the Cancer Alliance and their work programmes at GM Programme Directors meeting, DOFs (Directors of Finance), COOs (Chief Operating Officres), TPC (Trust Provider Collaborative), People and Culture System Group. |  | 3 | 4 | 12 | GM Cancer Managing Director meets regularly with ICS (Integrated Care System) Executive team to ensure cancer remains high on the list of priorities and to discuss the potential impact of the new measures on the Cancer Alliance programmes of work / achieving national cancer standards. Programme Director for workforce and education is working with the ICB (Integrated Care Board)to establish governance routes so that specific workforce risks are escalated to the right forums. The wf and ed team will be partnering with providers to provide more direct support / bespoke approach to wf challenges and wf planning given capacity constraints across the system. | Programme Director for Workforce and Education | 2025-03-31 | Programme Assurance Group reports and Cancer Board |  | 3 | 3 | 9 |  |  | 17.3.25 |  | Open
| CC |  |  | 2024-06-24 | Associate Director | If the cancer Alliance do not deliver on the priorities outlined in the NHS LTP (National Health Service Long Term Plan) and the annual operational planning guidance then this will negatively impact on the reputation of the organisation. | 3 | 3 | 9 | ↔ | 6-9 Mths | Identified SLT (Senior Leadership Team) Lead for each domain within the planning guidance responsible for delivery oversight incl budget and flagging of associated risks to delivery Strong system links in existence to support delivery and escalation Monthly updates provided at Assurance Group re progress, risk and financial position Reports presented to each GM Cancer Board Quarterly assurance meetings with North West & National Cancer Programme |  | 3 | 3 | 9 | Identified SLT (Senior Leadership Team) Lead for each domain within the planning guidance responsible for delivery oversight incl budget and flagging of associated risks to delivery Strong system links in existence to support delivery and escalation Monthly updates provided at Assurance Group re progress, risk and financial position Reports presented to each GM Cancer Board Quarterly assurance meetings with NW & National Cancer Programme Consideration given to reducing risk once Q3 submission made but decision follwoing discussion at SSRAG was to remain as is | Associate Director | 2025-03-31 | SSRAG (strategy and System Risk Assurance Group and PAG (Programme Assurance Group) discussions GM Cancer Boards Quarterly assurance meetings with NW & National Cancer Programme Risks fed into QPC |  | 2 | 3 | 6 |  |  | 2025-03-14 |  | Open
| CC |  |  | 23.6.23 | Associate Director | If the cancer Alliance do not deliver on recovery of cancer services and the priorities outlined in the NHS LTP and the annual operational planning guidance then this will negatively impact on the reputation of the organisation. |  |  |  | ↓ | 3-6 Mths | Identified SMT Lead for each domain within the planning guidance responsible for delivery oversight incl budget and flagging of associated risks to delivery Strong system links in existence to support delivery and escalation Monthly updates provided at Assurance Group re progress, risk and financial position |  | 2 | 4 | 8 | Identified SMT Lead for each domain within the planning guidance responsible for delivery oversight incl budget and flagging of associated risks to delivery Strong system links in existence to support delivery and escalation Monthly updates provided at Assurance Group re progress, risk and financial position | Associate Director | 2023-11-28 | SSRAG discussion |  | 2 | 4 | 8 |  |  | 2023-11-27 |  | Closed | All mitigations implemented
| PC |  |  | 2024-07-17 | Programme Director for Personalised Care | If all GM Trusts are not delivering PSFU (Personalised Stratified Follow-up) for Breast, Colorectal, Prostate and Endo then we are non-compliant with 24/25 planning guidance and evaluation of PSFU/infoflex will be delayed | 3 | 2 | 6 | ↔ | 6-9 Mths | Included details of timelines for implementation by Trust and Tumour group within 24/25 narrative submission Meetings being held with Trusts regularly to agree training schedule for Clinical Nurse Specialist teams Escalated concerns over Trusts not using infoflex where it is available to chair of Cancer Board in June 2024 Continued delays with full implementation of Personalised Stratified Follow Up (PSFU) will be noted in Quarter 1 return for 24/25 cancer planning guidance Weekly stand up calls stood down - Project Manager continues to meet individually with Bolton and Christie to support go live Smaller scale qualitative evaluation of the impact of using a dRMS (digital remote monitoring system) to support delivery of PSFU (Personalised Stratified Follow Up)approved at Cancer Board (Jul) - to be completed and presented back in November (to inform funding decision) Developed upload template for PSFU data to be included in PC dashboard - to be tested in Nov/Dec which will then be an automated process each month | n/a | 3 | 3 | 9 | Some Clinical Nurse Specialist teams where infoflex is live and they have been trained are reporting not using the platform due to staffing pressures - have escalated to chair of Cancer Board given dependence on utilisation for impact/benefits realisation evaluation of PSFU (Personalised Stratified follow-up) Consulted with Lead Cancer Nursess, National Live Well with Cancer and specific Pathway Clinical Leads on PSFU (Personalised Stratified follow-up)/infoflex evaluation proposal to be presented to July Cancer Board which will include recommendation of qualitative evaluation given we will not have access to enough data within timeframe. Christie & Bolton only Trusts remaining to go live - Bolton planned end of August, Christie planned early October (booked with Civica awaiting confirmation from Christie team). Feedback from Bolton Breast team when delivering demo and training that they will not use infoflex until funding post March is confirmed. Programme Director for Personalised Care & Performance Director to meet with Alex Cotterel to discuss impact on PSFU & Single Queue Diagnostics. Bolton now live with infoflex - continuing to meet and train Clinical Nurse Specialist teams on how to use system to support PSFU delivery Meetings with all Trusts being organised in Jan/Feb 2025 to identify remaining challenges to full implementation to agree if further support from Alliance is needed in 25/26. Shared evaluation completed in Oct with findings and recommendation that all GM NHS Trusts continue to use infoflex to deliver PSFU was approved. Alliance agreed to commit to fund infoflex for 25/26 - letters to be sent to all GM Trusts confirming funding for 25/26 including an ask to provide assurance on whether they intend to fund post 25/26 and if not how the plan to delivery PSFU. Meetings with all GM Trusts arranged for Jan/Feb 2025 to review current position of rollout and barriers/blockers. Confirmed project support with not continue into 25/26 and instead offered Trusts direct funding to resolve current barriers. Collating proposed solutions across GM and liasing with each Trust - requested a high level summary of cost and deliverable (which would support full operationalisation of PSFU) before approval of funding. 25/26 planning workshop held with Trust PC leads - escalated concerns with vacancy freeze and lack of CCCs funded within Trusts to support delivery of PSFU. | Programme Director for Personalised Care | 2024-10-30 | SSRAG (strategy and System Risk Assurance Group and PAG (Programme Assurance Group) Cancer Board Individual meetings with Trusts when required if escalating challenges with implementing or utilising infoflex Highest risk on PCDG risk log - Nov - requested that all Trust Personalised Care Leads also ensure this risk is noted on Trust risk logs where appropriate SLT agreed at SSRAG to escalate benefits of supporting infoflex (the dRMS) and highlight patient safety risk identified through evaluation (presented to Cancer Board in Nov) to not using a dRMS Individual Trust meetings to review current position and discuss key barriers/challenges and what would be needed to overcome then that the Alliance could support with direct funding |  | 2 | 1 | 2 |  |  | 2025-03-17 |  | Open
| FD OpI |  |  | 06.03.23 | GM Cancer Performance Director | If industrial action continues at the planned rate, there will be a significant impact to cancer delivery impacting operational performance baselines, and pathway milestones as well as the ability to meet planning requirements. There is a risk to increased harm as a result of elongated pathways Risk closed as no other IA planned currently. New risk to be added if new IA is planned |  |  |  | ↔ | 0-3 Mths | Not able to mitigate risk of IA. |  | 2 | 3 | 6 | Unable to mitigate the industrial action risk, but national discussions suggest less likelihood of IA. Ongoing work to maintain the profile of cancer delivery for those with cancer and those suspected of having cancer and awaiting outpatients, diagnostics and reporting as well as treatment, to ensure recovery from IA is prioritised to cancer Risk likelihood decreased to 3 - given new discussions to resolve have commenced and no current strike dates announced | GM Cancer Performance Director | 31.03.24 | GM Cancer PAG / SSRAG FDS, OP, TV Programme Board GM Cancer Board |  | 1 | 4 | 4 |  |  | 2024-10-21 |  | Closed | No IA planned and resolution seems in place. Will open a new risk if any further suggestion on impact
| C&E |  |  | 2023-07-23 | Communications and engagement lead | If we do not secure a new solution for our patient representative database, we will lose the ability to hold our patient representative data and enrol new members into the Greater Manchester Cancer Voices Community | 3 | 4 | 12 | ↔ | 0-3 months and ongoing | We have commissioned a new database and are ensuring it is IG compliant before transferring our existing volunteers across to it and recruiting new volunteers | Christie IG colleagues were required to approve the system | 3 | 2 | 6 | Current provider Sundown has advised they plan to decommission the current database holding our patient and carer representative database. Communications &Engagement lead is meeting with Sundown team w/c 24/07/23 to understand timescales and alternative solutions. Communications & Engagment lead has contacted digital services for advice. Patient & Public Involvement and Engagement team are drawing up a new brief for potential tender exercise. Funding is available to find a new appropriate solution, ideally from current Christie systems. Update Aug 23: Met with digital services and supplier to discuss next steps including technical spec, IG requirements and key milestones. Assurance received that current server will not be decommissioned until an alternative solution is in place. Update Nov 23: SoW proposal has been prepared and reviewed by Digital Front Door. Current database now has some issues with manual workarounds in place until a new solution is agreed and brought into place. Further supplier options to be explored. Cost implications circa £30k (available within budget) - service was previously pro bono meaning no secure SLAs contracted. Update March 24: Solution identified with GasMark8 to link into current Cancer Academy web hosting/database. Digital Services being consulted with a view to implement within next 3 months. Update June 2024. GasMark8 appointed and now working on new database. Delivery is expected later this summer. Update Sept 24. Database in final stages of development / testing and team working with Gas Mark 8 / Christie Digital Services to ensure all compliance in place. Update Oct 24: the registration form is finalised but launch delayed due to hold up with IG approval. Additional paperwork being reviewed by Christie Digital Services/IG on 31 October due to sensitive nature of data collected. Database is being developed/improved in background, but won't prevent us from using the registration form once live. Expected to go live early November if approved. November 2024 update: Christie IG has approved the system and we are now working to transfer our current volunteers across in the coming weeks. This process requires engagement from our volunteers to update their profiles, therefore we are expecting this to be completed by the end of January 2025 at which point this risk can be removed from the risk register. January 2025 update: as November 2024 update, we are on track to complete and have a meeting with the provider w/c 6 January to ensure everything runs smoothly. | Communications and engagement lead | 2025-01-31 | Escalating to July SSRAG (strategy and System Risk Assurance Group) 2023 Engaged Digital Services July/August who have been supporting throughout review process | N/A | 3 | 2 | 6 | N/A | N/A | 2025-02-28 | 2025-03-31 | Open
| FD OpI |  |  | 2024-04-24 | Director of Performance | If the improvement plans are not delivered in full, then there is a risk that the FDS (Faster Diagnosis Standard) target of 77% will not be delivered | 2 | 3 | 6 | ↔ | 0-3 months and ongoing | Focussed oversight on delivery of all actions Regular meetings with Trusts Highlight report / dashboard monitoring progress to COOs (Chief Operating Officres), EMDs (Executive Medical Directors), TPC (Trust Provider Collaborative), Cancer Board Weekly forecasting in place |  | 2 | 3 | 6 | Delivery of the cancer alliance work plan related to FDS (Faster Diagnosis Standard) Delivery of the front end pathway accelerated pathway work through TPC (Trust Provider Collaborative) Continuous monitoring of reported performance and local data to predict trends and enable corrective action to be taken National tiering calls for under performing Trusts Trust level action plans for improvement and delivery to reduce variation NCA (Northern Care Alliance) recovery plan needs to be delivered in full and on time. Concern raised over this and risk raised accordingly As NCA performance and GM performance is now on track, the risk has been reduced | Director of Performance | 30.09.24 | GM Cancer SSRAG (strategy and System Risk Assurance Group and PAG (Programme Assurance Group) Faster Diagnosis Standard, Operational Performance, Treatment Variation Programme Board GM Cancer Board Trust Provider Collaborative |  | 1 | 3 | 3 |  |  | 25.02.25 |  | Open
| FD OpI |  |  | 2022-10-05 | Programme Director for Transformation | If there is a lack of engagement with managing referrals into breast services including the re-direction of non urgent symptoms into alternative pathways e.g. mastalgia, along with inability to expand the breast cancer workforce (specifically radiology), then there will be a failure to meet cancer waiting time standards across Greater Manchester for breast which will significantly impact the overall performance for all tumour groups | 5 | 4 | 20 | ↔ | 0-3 Mths | 0.4 WTE (whole time equaivalent) Project Manager to implement mastalgia pathway (end date Oct24), extended 4hrs per week until Mar25. NHS England funding to employ GPERs (GPs with Extended Roles) across GM. 5 GPERs in trusts (Wigan, Bolton, Tameside, East.Cheshire and Manchester Foundation Trust North). 6 further GPERs (0.2WTE) employed at The Christie to support oncology. Funding to be spent by Mar25. . Radiology workforce development plan agreed at ICB now focusing on Advanced Practice to address variation following lack of funding. Delivery group establised to confirm standards and develop education framework. . Executive meeting to address oncology fragility, breast pathway board developed successful CWP with Novartis to support pathway efficiency – £350k to support 4xBand 4 WTE navigator roles and 0.4WTE (whole time equivalent) Band7/8 Project Manager for 24 months .The overall breast model of care that incorporates all aims to reduce fragility is closely managed and monitored by the GM Cancer Breast Pathway Board |  | 2 | 3 | 6 | Mastalgia pathway implementation ongoing from Nov22, pathway live in 5/6 Trusts. Project Manager to continue 4hours per week from Nov24-Mar25 to focus on education and quality. ERS Code enabled at Wigan, pathway has been launched. . GPER (GPs with Extended Roles) Pilot funded by NHS England from Nov22 - Mar25: GPERs 0.4WTE (whole time equivalent) in post at Bolton, Wigan, Tameside, E. Cheshire, Manchester Fundation Trust North. Expansion to oncology (6xGPERs 0.2WTE) recruitment completed, start dates to be confirmed. . Radiology fragility remains, delivery group formed to address variation in Enhanced/Advanced radiography practice. To agree standards across Greater Manchester and share with trusts and develop education plan to support career development. . Oncology service fragility ongoing, highlighted at exec level, clinical team expanded. Novartis Clinical Web Portal to streamline pathways ongoing from May24, pathway navigators employed starting by Dec24. . Resilience plans for breast services agreed in Feb22 with Provider Federation Board, further confirmation of Model of Care agreed in Feb24 through Integrated Care Board Sustainable Services Board including plans to end reconfiguration plans. . Services remain fragile with lack of investment in estates, any further development must be inline with estate development. .Risk reviewed at spotlight session SSRAG 27/11/24, with all mitigation measures discussed. Decision that residual has been reached with any ongoing breast workforce risk to be included and monitored via the Alliance's Workforce Programme Board risk register and can be escalated to the ICB Workforce risk register by Suzanne Lilley. Breast service overall risk to be raised at the ICB Health and Care Board by Ali Jones. Breast pathway to be monitored via the Breast Pathway Board ongoing with any new emerging system-wide issues/risks to be brought back to SSRAG as required. To close risk January 2025. +R27 | Programme Director for Transformation | 2025-03-31 | .Presented at Provider Federation Board late 2021 .Discussed/monitored at GM Cancer Programme Assurance Group and SSRAG (strategy and System Risk Assurance Group) monthly meetings ongoing (SSRAG focus session on this breast risk 26.7.2023) .Discussed/reviewed at GM Cancer Breast Pathway Board meetings ongoing with further funding and progress on all aspects. .Risk score has reduced to 8 with a residual of 6 as per discussion at SSRAG (strategy and System Risk Assurance Group) 240424. Agenda item for focus session at SSRAG 27/11/24. .Risk reviewed at spotlight session SSRAG 27/11/24, with all mitigation measures discussed. Decision that residual has been reached with any ongoing breast workforce risk to be included and monitored via the Alliance's Workforce Programme Board risk register and can be escalated to the ICB Workforce risk register by Suzanne Lilley. Breast service overall risk to be raised at the ICB Health and Care Board by Ali Jones. Breast pathway to be monitored via the Breast Pathway Board ongoing with any new emerging system-wide issues/risks to be brought back to SSRAG as required. To close risk January 2025. | No gaps identified | 2 | 3 | 6 |  |  | 2025-02-05 | 2025-03-31 | Closed | Residual score reached with notes in column R and U, risk closed 05/02/25
| Wf & Ed |  |  | 2022-11-21 | Programme Director for Workforce and Education | If all Greater Manchester trusts take part in the planned industrial strike for numerous different professional groups then this will impact on all Greater Manchester Cancer programmes of work | 3 | 5 | 15 | ↓ | 0-3 Mths | Representation of the Cancer Alliance and their work programmes at GM Programme Directors meeting, DOFs (Directors of Finance), COOs (Chief Operating Officers), TPC (Trust Provider Collaboratives) etc. |  | 2 | 3 | 6 | Unable to mitigate the industrial action risk, but national discussions suggest less likelihood of Industrial Action. Ongoing work to progress delivery of the cancer workforce and education strategy. Risk likelihood decreased to 2 - given no current strike dates announced | Programme Director for Workforce and Education | 2025-03-31 |  |  | 1 | 4 | 4 |  |  | 2024-10-20 |  | Closed | No IA planned and resolution seems in place. Will open a new risk if any further suggestion on impact
| C&E |  |  | 2023-04-19 | Communications and engagement lead | If we do not have a robust structure and policies in place for managing our online social media community, our campaigns may attract negative attention and abusive comments detracting from important NHS messaging and dissuading members of the public from engaging with NHS services. | 2 | 3 | 6 | ↔ | 0-3 months and ongoing | We have a social media policy in place on our website | N/A | 2 | 3 | 6 | A social media internal policy has been developed for review which includes who should manage channels and how they should manage negative engagement from our audience. It also contains information regarding escalation. An external statement/social media policy has also been developed which, once approved, will be published on our website, which demonstrates to users what type of content may be hidden or deleted and when users may be blocked from our channels, to demonstrate a transparent and fair approach. A health inequalities statement has also been developed, awaiting sign off, to publish on our website, to explain our approach to health inequalities and why some projects may take a targeted approach or use targeted messaging. April 24 update: All policies approved and published on website. Social community constantly monitored by Communications team. These policies were developed and approved by SMT and are now being used and published on our website. (Published beginning of June 23) These have also been shared with other Alliance comms teams for info and with Christie comms Community guidelines https://gmcancer.org.uk/our-social-media-community-guidelines/ Health inequalities statement https://gmcancer.org.uk/our-health-inequalities-statement/ November 2024 update: this remains on the risk register due to the nature of social media ever-changing, however we are confident that the risk is mitigated to the best of our ability currently and we continue to monitor. If this changes, we will update the risk register with new risks, actions and controls etc. | Communications and engagement lead | 2024-05-20 | Escalated to March Programme Assurance Group and April Senior Leadership Team meeting. Ongoing review, no additional risk. | N/A | 2 | 2 | 4 | N/A | N/A | 2025-02-18 | Ongoing | Open
| CC |  |  | 2023-11-27 | Associate Director | IF the funding from the Cancer Alliance offererd to GM NHS to support the financial position of the ICB is accepted THEN there will be a negative impact on the delivery of the deliverables of the cancer programme |  |  |  | ↓ | 3-6 Mths | Monthly review of programmes to confirm on track for delivery and within budget at Programme Assurance Group and GM Cancer Board Quarterly reporting to the Regional and National Cancer Programme Teams Strong links with ICB, DOFs, COOs etc |  | 1 | 4 | 4 | Detailed review of current forecasting positions for all programmes undertaken Discussions had with ICB finance colleagues Priority given to retaining funding associated with operational performance Slippage of some programmes acknowledged were risk is lower Proposal of funding 'offer' presented to SMT, assurance group and GM Cancer Board Finance update including end of year forecasting reported to Cancer Board on 29/01/24 | Associate Director | 2024-04-01 | Escalated at GM Cancer Board on 27/11/23 |  | 1 | 4 | 4 |  |  | 2024-04-22 |  | Closed | New financial year with new priorities with associated funding
| PC |  |  | 23.6.23 | Programme Director for Personalised Care | If data is not accurate then we will not be able to reliably report performance to NHSE. |  |  |  | ↓ | 0-3 Mths | GM KPI document shared with PCDG for approval. Final version will be revised to reflect 24/25 planning guidance then final endorsement from Programme Board to inform performance dashboard which will be reviewed as standing agenda item in 24/25 |  | 3 | 1 | 3 | Escalated requirement to report data via COSD to Cancer Board in July. MFT reported data should be included within COSD by end of Q2 however this is slightly delay & the Christie have escalated concern with initial timeline (1 year) to implement changes required in CWP to enable data to flow to COSD submission KPI document shared with PCDG and received positive feedback from LCN forum as it is helping to raise profile and importance of personalised care. GM KPI document updated based on feedback from Trusts and removed KPI1 as unable to assign responsibility to Trusts therefore KPI would not offer useful performance information. Director and BI lead to escalate to National team ask of guidance on how to monitor given ask in 24/25 draft planning guidance. Draft KPI curator dashboard to be reviewed 24/1. MFT now submitting data to COSD from HIVE (issues with historic data visibility on cancerstats). Christie still unable to submit data but progressing with wider CWP and COSD reporting update Christie confirmed they would incorporate the HNA data into the COSD rebuild being carried out to meet the v10 specification. This remains on track to be completed by the July 2024 deadline. CLOSE RISK | Programme Director for Personalised Care |  | Updates provided at PAG and SSRAG |  | 3 | 1 | 3 |  |  | 2024-04-18 |  | Closed
| FD OpI |  |  | 06.03.23 | GM Cancer Performance Director | If the financial deficit for NSS is not resolved, then there will be a significant shortfall in resource for allocation in FD OpI that will prevent planned improvement work (funds pre-committed to NSS / RDC and planning guidance now requests differing focus) |  |  |  | ↔ | 0-3 Mths |  |  | 1 | 3 | 3 | Budget allocated from FDS and OP, reducing the investment in these areas. However, at present all essential projects are funded, and so the risk has been reduced at present. Sustainability funding plan required for BAU transfer April 24. | GM Cancer Performance Director |  | N/A - Internal discussion presently |  | 1 | 3 | 3 |  |  | 2023-11-27 |  | Closed | No longer an in year risk
| FD OpI |  |  | 2024-07-22 | Director of Performance | If the FDS / Operational Performance work programme team is not able to secure the resources needed to execute the improvement work (fill vacancies), then there is a risk to the delivery of the planning requirements, TPC requirements and Integrated Care Board undertakings | 2 | 3 | 6 | ↔ | 3-6 Mths | Prioritisation of work within team |  | 2 | 3 | 6 | All posts now filled. Risk not closed due to pending maternity leave | Director of Performance | 2024-09-01 | Added to risk register and SSRAG 24.07.24 |  | 1 | 1 | 1 |  |  | 25.02.25 |  | Open
| PC |  |  | 2023-08-25 | Programme Director for Personalised Care | If funding is not approved to support GM infoflex after March 2024 then we will not have a DRMS supporting PSFU in GM and national implementation of Breast, Colorectal, Prostate and Endometrial pathways will be impacted |  |  |  | ↓ | 3-6 Mths | Representation of the Cancer Alliance and their work programmes at DOFs, COOs, TPC etc. Director presented at GM CIOs, GM DoFs and GM COOs an update and request and requirement for funding with the risks associated with not supporting a DRMS in GM Updates provided GM Personalised Care Programme Board and at GM Cancer Board |  | 1 | 1 | 1 | Requested quotes to develop an application blueprint / migration plan for InfoFlex Application which would support suggested future plans to move the hosting arrangements of the platform away from GM Digital DDE support infoflex as a viable DRMS to deliver PSFU as a national requirement but recognise that the decision re; continued funding sits with Trusts Decision by Trusts requested from GM CIOs (after attending & presenting update) Presented update to COOs who challenged whether infoflex was the the DRMS of choice that they want to support for GM. Requested that we explore other options (eg somerset) although this process was completed back in 2021 and infoflex was agreed by GM. Re-procurement process already begun as was necessary given 3 year contract renewal. Will work with Christie digital front door team (leading on re-procurement for GM) and ARP to expediate process. COOs were also unwilling to commit Trust funding in the long term for a DRMS and would request this to be funded by the ICB Service Specification and outcome measures in draft so Trusts can put systems in place now ready for April 2024. operational audit to be completed again to ensure we plan for where is support is required in Q4. Funding now agreed for 24/25. Funding will need to be secured from 2025 onwards and the Alliance will support by completing an evaluation of impact and benefits however this is reliant on Trusts going live with infoflex as a priority. Risk can be closed after PC Board in December if approved. Updated at PC Board in December and Alliance PM is working with civica and Trust BI teams on go live plans & training of clinical teams CLOSE RISK | Programme Director for Personalised Care | 2023-12-04 | Personalised Care Programme Board (Dec) |  | 2 | 3 | 6 |  |  | 2024-01-23 |  | Closed | risk changed as funding provided by Alliance for 24/25
| PC |  | System wide | 2024-07-16 | Programme Director for Personalised Care | If ORCHA (Organisation for the Review of Care and Health Apps) does not deliver on the Government accessibility requirements for public sector bodies (WCAG2.1 standards - Web Content Accessibility Guidelines) or have appropriate actions in place to ensure they are working towards it recorded clearly on the website then we will be in breach of these nationally set requirements as the commissioning body | 2 | 2 | 4 | ↓ | 6-9 Mths | Regular weekly meetings with ORCHA (Organisation for the Review of Care and Health Apps). Legislation due to change in September so will revisit | n/a | 1 | 1 | 1 | ORCHA (Organisation for the Review of Care and Health Apps) officially launched 9th July. Flagged concern with ORCHA and comms team met with them to agreed the following: • ORCHA will correct the missing alt tags on the homepage - completed • ORCHA will change FAQs on the dropdown so it doesn’t have an apostrophe (not accessibility – just to match rest of instances) - completed • ORCHA will provide some guidance on their timeframes for achieving compliance with WCAG 2.1 standards (Web Content Accessibility Guidelines)- ORCHA progressing slowly but there are delays due to reduced resource internally Will not be funding extension of current platform give funding rescrictions and lack of engagement and usage across GM in comparison to the cost per annum for the platform. Continuing to work with ORCHA on potential external funding opportunities and direct comms with some of the highest used apps on platform. | Programme Director for Personalised Care | 2024-10-01 | Escalated to SSRAG (strategy and System Risk Assurance Group) 24th July | N/A | 1 | 1 | 1 |  |  | 2025-02-24 |  | Closed | 2025-02-24
| C&ED |  |  | 2025-02-26 | Director of Commissioning & Early Diagnosis | If the GM system do not acknowledge and support Early Cancer Diagnosis as a priroity in 2025-6 from a resource perspective then there is a risk to delivery of the NHSE Cancer Programme planning priorities for 2025-6 | 3 | 4 | 12 | New | 0-3 months and ongoing | Ongoing engagement at a Place, TPC and GM system level to outline the priority and impact of ED work programme |  | 3 | 4 | 12 |  | Director of Commissioning & Early Diagnosis |  |  | Sign off of plans for 2025-6 and confirmation of funding allocation and transaction | 2 | 2 | 4
| C&ED |  |  | 2025-02-26 | Director of Commissioning & Early Diagnosis | IF the GM ICB do not approve the GM Cancer Alliance Delivery Plan for 2025-6 and release the SDF to support delivery, then the Cancer Alliance will be restricted in terms of delivery against national priorities and constitutional standards | 4 | 4 | 16 | New |  | Ensure engagement with and approval by GM system governance and leaders |  | 4 | 4 | 16
| C&E | 1 | 4 | 2025-01-20 | Communications and engagement lead | The website currently does not fully meet accessibility compliance. It is compulsory for public sector organisations to achieve this and we could be inspected, and potentially fined if we are not found to be aiming for compliance. | 2 | 3 | 6 | New |  | Covered within actions. We are mitigating via regular accessibility reviews and resolving issues. | N/A | 2 | 3 | 6 | Actions we are taking: • We have done a significant amount of work over summer 2025 and reduced the number of issues from 12,022 to 1,734. • We will update our accessibility statement on the website to reflect known issues and give a timeline for resolving them. • We have engaged Shaw Trust on retainer for 12 months to provide regular accessibility reviews to enable us to resolve all remaining issues. • We have implemented a two-tier sign off process for any new content or edited content on the website – allowing the comms team to review and approve edits made by the wider team before they go live. | Communications and engagement lead | 2025-12-31 | Added to risk register and SSRAG 22/1/2025 | N/A | 1 | 1 | 1 |  |  | 2025-02-28 | Ongoing | Open

## Issues Log (Open)
Issue log template |  |  |  | Issue Log
Template: NHS GM Issue Log
Issue Ref | Risk Ref | Date Issue Added | Issue Owner | Issue Description | Priority Score | Impact | Resolution / Actions Plans | Action Owner | Due Date for Actions | Progress Against Action | Assurances | Is Escalation needed? | Last reviewed | Expected Date of Resolution | Open / Resolved | Date Closed | Reasons for Closure
A unique coding that allows the issue to be easily identified | If the issue stems from a risk, give the Risk ID | Date when the issue was added to the issue log | Job title of the person responsible for the management, monitoring, control and escalation where appropriate, of the identified issue | A statement describing the issue | A measure of the issue's priority from 0-5 | Describe the consequences of the issue | The actions and activities planned to take place that will when implemented or completed reduce, eliminate or minimise the issue | Job title of the person responsible for completing the action | Each action should have a completion date set | Provide a progress update on the resolution or action plans | Internal assurance / evidence (e.g. Board reporting, sub-committee and programme governance) and external assurance / evidence (e.g. planned or received audits or reviews) that the issue is being effectively managed | Does the issue need to be escalated to achieve the desired resolution outcome? | Date when the issue was last reviewed and/or updated | The date the issue is expected to be resolved | Select current status of issue | Date issue was closed | Reasons outlining why the issue was closed

## Lists
Risk Type | Risk Proximity
1. Organisation | 0-3 months
2. System wide | 3-6 months
3. Both | 6-9 months
12 + months
Risk Category
1.System design & operating model | Trend | Open
2.Political | New | Closed
3.Stakeholder relations | ↔
4.Governance, accountability and functions | ↑
5.Communications and Engagement | ↓
6.Workforce
7.Technology
8.Sustainability
9.Estates
10.Quality and Safety
11.Finance
12.Operational Performance
13.Catastrophic Events – force majeure