## Slide 1
Early Diagnosis
Ali Jones
Director of Commissioning & Early Diagnosis
8th January 2025

## Slide 2
Key Updates/Successes: Early Diagnosis
Programme | Update
Long Term Plan Ambition: 75% by 2028 | Rapid Cancer Registration Data (RCRD) Stage 1 & 2 diagnosis – Using the previous 12 month average Aug-23 – Jul-24, GM = 58.3% and England = 58.67%. Continued improvement in GM position. Detail in following 2 slides. Strategy complete and to be presented to Cancer Board January 2025.
Pharmacy Referral Pilot | 12 Pharmacists have joined the pilot, 7 have completed the necessary training mandated prior to undertaking any consultations that may result in a suspected cancer referral to secondary care. The volume of consultations by all Community Pharmacists involved in the pilot across all 4 Cancer Alliances totals 63 (October 2024) with the approximately half being for skin, a pathway not included in the GM pilot. 1 consultation thus far in GM. Monitoring and reporting of the pilot in GM will continue together with the support being offered and this includes another webinar for pilot sites later in January. The pilot is due to finish by the end of March 2025.
Targeted Lung Health Checks | Continue to see improvements across invites, LHCs, and CT scans YTD. 84% LHCs, 87% scans through M9. ​ GM PCN rollout continues with cohort 1 now concluded.​ 3 incidents ongoing within the programme. 1 in relation to radiology reporting and 2 in relation to recall of patients for surveillance scans (approx. 900 pts affected). Harm to be assessed in due course. ​163 lung cancers diagnosed YTD with 130 stage I/II (79.75%). 2025-6 trajectories to be submitted to NHSE 22/1/25 but will be reviewed and potentially revised on sight of 2025-6 planning guidance and national funding model.
FIT | November 2024 data released Friday 3rd January – see separate slide
Innovation & Pathway Boards | Colorectal: mobile community outreach project launched Piccadilly Gardens 28th November 2024. Upper GI: Procurement concluded for Upper GI capsule sponge project - InPhase confirmed as selected provider. Comms required for project identified and agreed with T&F group. ​ January 2025: Map van route according to at-risk population per locality.; SOP to go to OG pathway board for approval. ​ Gynae: Ovarian cancer project to commence M12 in conjunction with the Dianne Oxberry Trust and Ovarian Cancer UK. Early Diagnosis Task & Finish Group established and first meeting held.

## Slide 3
Faecal Immunochemical Testing
37 of 65 PCNs above the required level in advance of the Q4 target
5 localities above the required level in advance of the Q4 target

## Slide 4
75% Long Term Plan Ambition
GM Cancer Alliance 58.3% (5,238 of 8,983 cancers diagnosed at stage 1 or 2)
England 58.67%

## Slide 5
Using the 12-month rolling position for July 24 and comparing this to the 12-month rolling average in July 23, we have seen improvements across the majority of tumour groups recorded in the RCRD. When looking at all cancers, GM has improved by 1.5 percentage points in comparison to England at +1.0pp.
GM outperformed the England average improvements in early diagnosis for the following tumour groups:
Colorectal: England: -0.1pp, GM: +4.9pp
Haematological: England: +0.5pp, GM: +8.7pp
Melanoma: England: +1.8pp, GM: +2.0pp
OG Cancers: England: +0.4pp, GM: +3.7pp
Urological (excl. prostate): England: +1.6pp, GM: +4.8pp
Uterine: England: -1.3pp, GM: +2.2pp
Improvements for breast and gynae (combined) were in line with the national trends.
Overall increase for lung (+3.2pp) lower than seen nationally (+4.4pp). But GM are 2nd nationally of the 20 Cancer Alliances for early-stage lung diagnosis and 6.7% above the England average.
The biggest declines were seen for:
Ovarian: England: +2.7pp, GM: -6.5pp
UGI (Pancreatic only): England: -1.0pp, GM: -4.5pp
GM Progress with Early Stage Diagnosis

## Slide 6
Financial Position M8: SDF (Early Diagnosis)
Programme | Allocation 24-25 | Spend M8 | Notes
Early Diagnosis: Pay | 1,553,469 | 1,019,842 | Includes income from NHS GM and CRUK
Early Diagnosis: Non Pay | 427,129 | 224,502 | Full spend profiled across 2024/5
Timely presentation & Inequalities | 572,750 | 289,725 | Full spend profiled across 2024/5
Primary Care | 483,900 | 331,864 | Full spend profiled across 2024/5
FIT | 562,000 | 391,717 | Full spend profiled across 2024/5
Innovation & Pathway Improvements | 740,000 | 30,040 | Full spend profiled across 2024/5
Allocations to other work programmes | 276,624 | 276,624 | Transfer complete
TOTAL | 4,615,872 | 2,564,314 | 
Financial Position M8: Targeted Funding
Programme | Allocation 2023-24 | Spend M7 | Notes
Community Pharmacy | 75,000 | 0 | To be retained for NHS GM position
Targeted Lung Health Checks | 170,601 | 100,671 | 
Cancer Vaccine Launchpad | 5,580 | 0 | 
Liver case finding and surveillance | 434,641 | 454,190 | Includes pass-through payments for PCN projects
TOTAL | 685,822 | 297,146 | 

## Slide 7
Risks/Issues to Escalate
IF the MFT data completeness issues are not addressed and resolved THEN the GM staging data will be missing a considerable proportion of staged cancers. This will have an effect from a symptomatic referral perspective for those localities referring to MFT but also for screening patients (bowel, breast and cervical). The draft planning guidance for 2025-6 includes this:
Cancer Alliances will need to set out a summary of their priority areas of need, underpinned by data, which should form the rationale for the local and targeted interventions that will be delivered. As a minimum this must consider Rapid Cancer Registration staging data by tumour type, all-cancer deprivation and ICB (based on 12-month rolling averages) to determine the priority areas of focus for improvement. This should consider any 'outliers' or worsening trends in earlier diagnosis, particularly for tumour sites with high volume of late diagnoses.
Cancer Alliances with staging completeness below 80% to set out actions that will be undertaken to increase staging completeness.
Staging completeness - Q4 (up to Sept) 2024 Alliance staging completeness rate to be included in the Alliance planning template (available from public staging dashboard in early January). Alliances with staging completeness below 80% to set out actions that will be undertaken to increase staging completeness in 2025/2026.
GM Q2 2024-5 data completes for staging data 69.6%
Means unless there are significant improvements, we will be asked to provide an action plan
4 of our 7 providers are under the 80% benchmark
MFT the lowest of the GM Trusts and the only one below 70%
Action: AJ and LGD to agree approach to resolving this issue with input from BI and ED teams.

## Slide 8
No decisions
Decisions for Assurance Group