## Slide 1
Cancer Pathways – PAG
Susan Todd
Programme Director - Transformation
09.07.2025

## Slide 2
Key Updates/Successes
Pathway Board | Update
Recruitment | Jeremy Oates started 1/7/25 as Urological Cancer Clinical Lead (and thank you Sotonye Tolofari) Rachel Mitchell now on mat leave until summer 26, Jennie Roche back from mat leave 7/7/25
Colorectal Roger Prudham, Chelliah Selvasekar Tom Anderton | Handover with TA complete with RM commencing Mat leave from 18/6/25 Our second cohort of 2-day ‘interpreting blood analysis’ course complete. 14/18 delegates in attendance with our next session being held in September. Currently fully booked with a waiting list The first GM Early Rectal Cancer Steering Group was held on 23/06/25. Good attendance & engagement from stakeholders. Group consensus to define what we mean by ‘rectal cancer’ and define ‘early rectal cancer’ providing a clear position statement. Actions are currently being worked up to progress GM MR Rectal Reporting Template v1.2 ratified by PWB and ERC Steering Group x3 new Treatment Summary templates for: Complex Colorectal Surgery, Best Supportive Care & De-functioning Stoma have been ratified by PWB and circulated with all CNSs to embed and use
Breast Clare Garnsey Anne Armstrong Claire Goldrick | Education Day 5th June, over 100 attendees from across GM, very well received Attended Moon Shot Lobular Breast Cancer roundtable Referral forms for oncology services active, two engagement meetings held to encourage uptake Ongoing work on the MBC data project with the Clinical Outcomes Group Continue to work on HSJ Report and Pan-Alliance service optimisation paper
Neuro-oncology Catherine McBain Claire Goldrick / Tom Anderton | Handover with TA in progress Survey shared to identify educational needs for workforce on rehabilitation needs for patients with brain tumours Continuing to support brain mets working group to improve pathways and referrals to MDT
Research David Thomson Claire Goldrick | Continue to work on BRIDGE programme, level 1 education module in development, level 2 working group established and conversations for AI in development. Uptake to cultural competency training has been low and escalated to R&I Director

## Slide 3
Pathway Board | Update
HPB Joe Geraghty Louise Farnworth | HPB Education event confirmed for February 2025- this will be a full day event with breakout sessions to maximise attendance and relevance for all professionals involved in the HPB pathway Primary Care Webinar confirmed to take place in July and speaker to deliver this has been identified
Acute Oncology Caroline Wilson Louise Farnworth | Virtual daily MDT oversight group established, with 2 meetings held. This group will monitor project progress, ensure timelines are met, and provide a forum for raising issues and escalations First CNS working group for the daily virtual MDT held. Each GM site has nominated a CNS ‘champion’ to represent their team and provide feedback on the MDT process Meeting held with GM Cancer Alliance and The Christie to discuss the future of Acute Oncology services in Greater Manchester and East and Mid Cheshire and how The Christie NHS Foundation Trust and the Greater Manchester Cancer Alliance can work together to provide equitable access to high quality urgent care for patients experiencing a cancer-related medical emergency
Oesophago-gastric Javed Sultan Alex Riley | Initial feedback from OG One Stop Clinic is positive with good patient experience & improvements in treatment times The Don’t Ignore the Burn campaign ran throughout Men’s Health Awareness Week in June utilising resources already developed to continue to raise awareness of signs and symptoms of OG cancer The Barrett’s Case finding pilot has finished its community outreach campaign, now in process of evaluating results
Urology Sotonye Tolofari Jeremy Oates (1/7/25-) Alex Riley | Mr Sotonye Tolofari tenure as clinical lead for Urology ended 30/6/25, Mr Jeremy Oates started as new CL 1/7/25 Urology Education event 23rd June 2025. A wide range of engagement with lots of discussions. The alliance has taken back suggestions for more in-depth discussions such as a Renal Case Finding and Testicular awareness work Analysis of the LATP Capacity and Demand audit has been completed showing the use of a single system across GM would support a reduction in capacity needs across GM
Haemato-oncology Suzanne Roberts Alex Riley | GM have joined the NHSE working group to develop Haematology Best Timed Pathways The Haem board will support the Digital Cytology pilot which will support the Lymphoma pathways Tameside reviewing their patient cohort to go live with CLL on infoflex. This should provide evidence to support other trusts going live
Key Updates/Successes

## Slide 4
Key Updates/Successes
Pathway Board | Update
Lung Louise Brown Jane Cronin | ctDNA education in interpretation of reports underway Rapid Small Cell project to present at Lung Pathology Sub-Group & Pathway Board to agree pathology rapid alerts and turn-around times New recommendations for primary care for patients with normal Chest X-Rays presented to PCN Meeting before wider comms roll out across primary care
Skin Stephanie Ogden Jane Cronin | Skin successful in GPCR’s x 2 to link with new community services (based at Salford) Nursing Workforce Skills audit underway to be used to develop a GM Framework linked to ACCEND, to upskill non-medical practitioners in performing skin surgery Follow-up ACCEND workshop to be held July to continue work on Framework Genomics Project presented at NHS Genomics Medicine Service
Gynaecology Nadia Ali-Ross Louise Farnworth | PMB Hysteroscopy audit has finished, findings being reviewed, will be presented at next PWB (July), action TBC. All meetings with cross cutting teams to finalise and agree deliverables for 25/26 work programme has now taken place Engagement with other regions across England underway to explore the use of IOTA and O-RADS, and to identify key benefits of each reporting model
Head and Neck Tracey Ellis Jane Cronin | Cancer Vaccine Launch Pad Southampton presented at Pathway Board, request for H&N sites across GM to express interest in being involved as a system approach. Christie involved in BNT113-01 trial, meeting with Christie arranged to discuss next steps. Aware Colorectal already have sites across GM Digital Rose Pilot started 05/05/2025 (first 2 weeks internal validation of digital images with glass slides). Working with Haem Pathway Manager for retrospective audit of Lymphoma cases so evaluation of effect of Digital Rose on Lymphoma pathway can be understood. Site visit by pathway manager / clinical lead to take place
MDT Reform Susi Penney Clare Jordan | Skin MDT Reform project recommenced following transferral of MDT lead funding to the Christie, MDT Referral form drafted and shared for feedback Cancer MDT directory drafted in ghost mode on the Cancer Alliance webpage, this page will be password protected to allow access to NHS staff only. Awaiting penetration test and DPIA before making page live

## Slide 5
Progress on Sustainability
Issue | Mitigating actions
No Decisions for Assurance Group
Risks/Issues to Escalate
Issue | Mitigating actions

## Slide 6
Pathway Boards – July 2025

## Slide 7
Questions?